## 00_Control
PTBC / TBC Governance Tracker — TASK-004
Control | Value
Task | TASK-004 — Stand Up PTBC / TBC Governance Tracker (Phase P0 — Discovery & Governance); depends on TASK-002
Programme | AHDA Regional Project Management Platform (RPMO)
Issue date | 2026-09-18
Tracker status | ISSUED — 0 of 48 PTBC values approved; 0 of 511 source TBCs resolved; acceptance of the tracker by the requirements governance lead pending (see ptbc-tbc-tracker.md §9)
Owner | Requirements governance lead (14B-F-008 owner) / PMO
Sources and precedence | Per TASK-001 (docs/baseline/controlled-source-baseline.md). Register wording: CSB-14A §19.2 (rank 2) = CSB-BP2 Appendix F.2 (rank 3) = CSB-14B-RTM 08_PTBC_Impact — verified identical for all 48 rows on 2026-09-18. Source TBCs: CSB-14B-RTM 14_Source_TBC (511 rows). Gate classes: CSB-14A §19.3 as normalised by Step 14B Assessment v1.1 §8. Packages/planning gates: CSB-15 11_TBC_PTBC_Gates and 02_Build_Packages. Task register: AHDA_RPMO_Platform_Implementation_Plan.xlsx (Implementation Plan, Open Questions, Architecture Decisions, Release Checklist). Task packages/waves: TASK-003 cross-reference Appendix A.
Rule | No task, ADR, runbook, seed script, fixture or test invents an AHDA value. A value exists only when the PTBC row shows Status = APPROVED with a decision reference, signatory and date. Until then the task builds the mechanism and marks the value TBC with the PTBC ID.
Sheets | 01_PTBC_Register (48) · 02_Source_TBC_Register (511) · 03_Task_Links (676 task↔PTBC rows, 94 tasks) · 04_Open_Questions (10) · 05_Gate_Summary · 06_Findings · 07_Status_Vocabulary
How to update | 1) Value approved: fill Status, Approved value / decision reference, Approved by, Approval date on the PTBC row; set the same on each source TBC the decision resolves (02_Source_TBC_Register). 2) Never edit the "as recorded" columns; a wording change goes through CSB-14A / CSB-BP2 change control. 3) A new task that touches a gated value gets a 03_Task_Links row citing the PTBC ID. 4) Re-issue the Tracker status line and commit on a chore/task-004-* branch.

## 01_PTBC_Register
PTBC ID | Category | Consolidated theme (as recorded) | Source specs / families (as recorded) | Source specs (expanded) | Resolution gate (as recorded) | Gate class (CSB-14A §19.3) | Step 15 planning gate | Step 15 issue category | Integrated treatment (as recorded) | Value restriction (CSB-15) | Status | Working baseline in workbook (NOT an approved value) | Approved value / decision reference | Approved by (AHDA function) | Approval date | Accountable AHDA function (proposed) | Source TBC count | Source TBC IDs (14B crosswalk) | Affected RTM rows (14B) | Step 15 packages | Waves | Workbook tasks (03_Task_Links) | Open Questions | ADRs | Release Checklist gates | Notes
PTBC-001 | Business Governance | Approval authority matrices and decision limits | WF-01/WF-03/WF-08/WF-09/WF-10/WF-11 | WF-01; WF-03; WF-08; WF-09; WF-10; WF-11 | Before UAT | BEFORE UAT | Before UAT | B — Authority / policy decision | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office (OQ-005) | 19 | TBC-CFG-010; TBC-CFG-025; TBC-PCR-07; TBC-CHG-002; TBC-CHG-012; TBC-SUS-002; TBC-SUS-003; TBC-CLO-001; TBC-CLO-002; TBC-APR-001; TBC-APR-006; TBC-APR-007; TBC-APR-008; TBC-APR-011; TBC-APR-012; TBC-APR-013; TBC-APR-014; TBC-APR-015; TBC-APR-016 | 18 | BPK-011; BPK-014; BPK-015; BPK-020; BPK-024; BPK-025 | W2; W3; W4; W5; W6 | TASK-008; TASK-025; TASK-035; TASK-036; TASK-041; TASK-042; TASK-043; TASK-045; TASK-046; TASK-047; TASK-054; TASK-060; TASK-061; TASK-062; TASK-063; TASK-064; TASK-065 | OQ-005
PTBC-002 | Business Governance | Project Activation authority and readiness policy | WF-01, WF-03, FG-04 | WF-01; WF-03; FG-04 | Before UAT | BEFORE UAT | Before UAT | B — Authority / policy decision | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. | Exact approved authority/value/provider; no production default inferred. | OPEN | Fast-track past Under Review flagged as Open Question by TASK-041 AC — no rule assumed |  |  |  | AHDA Business Sponsor / Portfolio Office | 1 | TBC-CFG-028 | 0 | BPK-014; BPK-015; BPK-007 | W1; W2; W3 | TASK-008; TASK-025; TASK-027; TASK-034; TASK-041; TASK-042; TASK-043; TASK-045; TASK-046; TASK-047; TASK-054 |  |  |  | Zero affected RTM rows (14B v1.1 §8 analytical gap; does not block the gate).
PTBC-003 | Business Governance | External Entity participation eligibility and onboarding authority | WF-01, WF-13, FG-03 | WF-01; WF-13; FG-03 | Before External UAT | BEFORE UAT | Before External UAT | B — Authority / policy decision | Which Projects/Entity types/users may participate and who may grant access. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT (Identity) / Business Sponsor (OQ-007) | 24 | TBC-RPT-26; TBC-IAM-006; TBC-PCR-02; TBC-ISS-010; TBC-CHG-013; TBC-SUS-012; TBC-CLO-020; TBC-APR-010; TBC-DOC-006; TBC-EXT-001; TBC-EXT-002; TBC-EXT-003; TBC-EXT-006; TBC-EXT-007; TBC-EXT-008; TBC-EXT-009; TBC-EXT-010; TBC-EXT-012; TBC-EXT-013; TBC-EXT-016; TBC-EXT-017; TBC-EXT-018; TBC-EXT-021; TBC-EXT-025 | 15 | BPK-006; BPK-014; BPK-023 | W1; W2; W5 | TASK-008; TASK-025; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-041; TASK-042; TASK-043; TASK-066; TASK-067; TASK-068; TASK-079; TASK-081 | OQ-007
PTBC-004 | Business Governance | Completion/Closure readiness criteria and disposition policy | WF-10 | WF-10 | Before closeout UAT | BEFORE UAT | Before closeout UAT | B — Authority / policy decision | Exact criteria by Project classification and acceptable open obligations. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 33 | TBC-CFG-013; TBC-PRG-019; TBC-SCH-015; TBC-TSK-005; TBC-TSK-016; TBC-MIL-015; TBC-RSK-013; TBC-RSK-018; TBC-ISS-013; TBC-CHG-018; TBC-CLO-001; TBC-CLO-002; TBC-CLO-003; TBC-CLO-004; TBC-CLO-005; TBC-CLO-007; TBC-CLO-009; TBC-CLO-010; TBC-CLO-011; TBC-CLO-012; TBC-CLO-013; TBC-CLO-014; TBC-CLO-015; TBC-CLO-016; TBC-CLO-017; TBC-CLO-018; TBC-CLO-020; TBC-CLO-022; TBC-DOC-019; TBC-EXT-020; PERF-TBC-007; PERF-TBC-025; PERF-TBC-026 | 75 | BPK-025 | W6 | TASK-063; TASK-064; TASK-065
PTBC-005 | Business Governance | Suspension/Resumption reasons, readiness and review governance | WF-09 | WF-09 | Before suspension UAT | BEFORE UAT | Before suspension UAT | B — Authority / policy decision | Exact categories, review cadence and authority. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 14 | TBC-CFG-012; TBC-MIL-014; TBC-RSK-017; TBC-SUS-001; TBC-SUS-002; TBC-SUS-005; TBC-SUS-006; TBC-SUS-008; TBC-SUS-009; TBC-SUS-011; TBC-SUS-014; TBC-SUS-015; TBC-SUS-019; TBC-SUS-020 | 57 | BPK-024 | W5 | TASK-062; TASK-064; TASK-065
PTBC-006 | Business Governance | Milestone achievement evidence/review governance | WF-05 | WF-05 | Before milestone UAT | BEFORE UAT | Before milestone UAT | B — Authority / policy decision | Which milestone classes require evidence/acceptance/rejection options. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 8 | TBC-SCH-011; TBC-MIL-001; TBC-MIL-002; TBC-MIL-003; TBC-MIL-004; TBC-MIL-009; TBC-MIL-012; TBC-MIL-013 | 6 | BPK-017 | W4 | TASK-050; TASK-051; TASK-054
PTBC-007 | Business Governance | Risk acceptance/escalation authority | WF-06 | WF-06 | Before risk UAT | BEFORE UAT | Before risk UAT | B — Authority / policy decision | Who may accept residual risk/escalation by rating/context. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 3 | TBC-PRG-023; TBC-RSK-010; TBC-CLO-008 | 2 | BPK-018 | W3 | TASK-055; TASK-056; TASK-059
PTBC-008 | Business Governance | Issue/Challenge severity-priority/escalation governance | WF-07 | WF-07 | Before concern UAT | BEFORE UAT | Before concern UAT | B — Authority / policy decision | Final labels, minimum priority rules and escalation authorities. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 0 |  | 2 | BPK-019 | W3 | TASK-057; TASK-058; TASK-059 |  |  |  | Zero source TBCs in the 14B crosswalk although WF-07 TBC-ISS-003/004/016 are its subject — see 06_Findings 004-F-002.
PTBC-009 | Business Governance | Change materiality/threshold governance | WF-08, FG-04 | WF-08; FG-04 | Before change UAT | BEFORE UAT | Before change UAT | B — Authority / policy decision | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office (OQ-005) | 18 | TBC-CFG-008; TBC-SCH-013; TBC-MIL-011; TBC-ISS-011; TBC-CHG-001; TBC-CHG-002; TBC-CHG-007; TBC-CHG-008; TBC-CHG-010; TBC-CHG-011; TBC-CHG-016; TBC-CHG-017; TBC-CHG-022; TBC-CHG-023; TBC-CHG-024; TBC-APR-002; PERF-TBC-014; PERF-TBC-022 | 50 | BPK-020; BPK-007 | W1; W4 | TASK-008; TASK-025; TASK-027; TASK-034; TASK-035; TASK-060; TASK-061; TASK-065 | OQ-005
PTBC-010 | Business Governance | Dashboard/Report publication authority and SoD | FG-01, FG-02, FG-04 | FG-01; FG-02; FG-04 | Before admin UAT | BEFORE UAT | Before admin UAT | B — Authority / policy decision | Who validates/publishes official dashboards/reports and whether dual control required. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 6 | TBC-DSH-023; TBC-RPT-04; TBC-INT-20; TBC-PRG-020; PERF-TBC-012; PERF-TBC-021 | 2 | BPK-026; BPK-027; BPK-007 | W1; W5 | TASK-008; TASK-025; TASK-027; TASK-034; TASK-069; TASK-070; TASK-071; TASK-072
PTBC-011 | Business Governance | Audit Reviewer, retention-hold and disposal authorities | FG-06 | FG-06 | Before audit/records UAT | BEFORE UAT | Before audit/records UAT | B — Authority / policy decision | Named permission/assignment authorities and SoD. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 20 | TBC-AUD-01; TBC-AUD-02; TBC-AUD-03; TBC-AUD-04; TBC-AUD-05; TBC-AUD-06; TBC-AUD-07; TBC-AUD-10; TBC-AUD-13; TBC-AUD-14; TBC-AUD-17; TBC-AUD-18; TBC-AUD-19; TBC-AUD-21; TBC-AUD-24; TBC-AUD-31; TBC-ISS-007; TBC-CLO-013; TBC-APR-002; TBC-DOC-007 | 13 | BPK-008; BPK-028 | W1; W5 | TASK-033; TASK-073; TASK-074; TASK-083
PTBC-012 | Business Governance | Sensitive read/export audit policy | FG-02, FG-06 | FG-02; FG-06 | Before production | BEFORE PRODUCTION | Before production | B — Authority / policy decision | Which views/downloads require enhanced audit. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Portfolio Office | 1 | TBC-DSH-018 | 1 | BPK-027; BPK-028 | W5 | TASK-033; TASK-071; TASK-072; TASK-073; TASK-074
PTBC-013 | Configuration | Project type/classification/priority/sector/location catalogues | WF-01, FG-04 | WF-01; FG-04 | Before UAT data load | BEFORE UAT | Before UAT data load | A — Configurable value | Final AHDA master values and labels. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 20 | TBC-CFG-002; TBC-CFG-003; TBC-CFG-006; TBC-CFG-009; TBC-CFG-016; TBC-CFG-017; TBC-CFG-018; TBC-CFG-019; TBC-CFG-022; TBC-CFG-029; TBC-CFG-030; TBC-PCR-01; TBC-PCR-09; TBC-PCR-11; TBC-PCR-13; TBC-PCR-14; TBC-TSK-008; TBC-CLO-010; TBC-CLO-018; PERF-TBC-013 | 36 | BPK-014; BPK-007 | W1; W2 | TASK-008; TASK-025; TASK-027; TASK-034; TASK-041; TASK-042; TASK-043
PTBC-014 | Configuration | Business calendar, timezone and working-day policy | WF-02/WF-03/WF-11/FG-04 | WF-02; WF-03; WF-11; FG-04 | Before SLA/schedule UAT | BEFORE UAT | Before SLA/schedule UAT | A — Configurable value | Shared business calendar plus schedule-specific working-time mapping. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 16 | TBC-RPT-17; TBC-CFG-011; TBC-CFG-015; TBC-PCR-05; TBC-PRG-002; TBC-SCH-001; TBC-SCH-002; TBC-TSK-010; TBC-MIL-008; TBC-RSK-019; TBC-ISS-005; TBC-SUS-018; TBC-CLO-025; TBC-APR-004; TBC-APR-013; TBC-EXT-014 | 3 | BPK-007; BPK-015; BPK-022; BPK-011 | W1; W2; W3; W4 | TASK-008; TASK-025; TASK-027; TASK-034; TASK-035; TASK-036; TASK-044; TASK-045; TASK-046; TASK-047; TASK-054
PTBC-015 | Configuration | Schedule Health thresholds and calendar override policy | WF-03 | WF-03 | Before schedule UAT | BEFORE UAT | Before schedule UAT | A — Configurable value | Warning/critical thresholds and allowed overrides. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 9 | TBC-SCH-002; TBC-SCH-003; TBC-SCH-007; TBC-SCH-009; TBC-SCH-010; TBC-SCH-012; TBC-SCH-014; TBC-SCH-017; TBC-SCH-018 | 7 | BPK-015 | W3 | TASK-045; TASK-046; TASK-047; TASK-054
PTBC-016 | Configuration | Task priority/category/reminder/blocked thresholds | WF-04 | WF-04 | Before task UAT | BEFORE UAT | Before task UAT | A — Configurable value | Operational values remain configurable. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 9 | TBC-TSK-002; TBC-TSK-004; TBC-TSK-007; TBC-TSK-009; TBC-TSK-011; TBC-TSK-012; TBC-TSK-013; TBC-TSK-015; TBC-TSK-018 | 11 | BPK-016 | W3 | TASK-048; TASK-049; TASK-054
PTBC-017 | Configuration | Risk scales/dimensions/matrix | WF-06, FG-04 | WF-06; FG-04 | Before risk UAT | BEFORE UAT | Before risk UAT | A — Configurable value | Probability/Impact labels, quantitative descriptions, 5x5 cell→rating mapping. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Risk & Portfolio Office (OQ-006) | 13 | TBC-CFG-004; TBC-CFG-005; TBC-RSK-001; TBC-RSK-002; TBC-RSK-003; TBC-RSK-004; TBC-RSK-005; TBC-RSK-006; TBC-RSK-007; TBC-RSK-011; TBC-RSK-012; TBC-RSK-014; TBC-RSK-015 | 8 | BPK-018 | W3 | TASK-034; TASK-052; TASK-055; TASK-056; TASK-059 | OQ-006
PTBC-018 | Configuration | Issue/Challenge categories/severity/priority master data | WF-07, FG-04 | WF-07; FG-04 | Before concern UAT | BEFORE UAT | Before concern UAT | A — Configurable value | Final categories, dimension labels and presentation. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 8 | TBC-CFG-007; TBC-ISS-001; TBC-ISS-002; TBC-ISS-003; TBC-ISS-004; TBC-ISS-006; TBC-ISS-008; TBC-ISS-009 | 10 | BPK-019 | W3 | TASK-034; TASK-057; TASK-058; TASK-059
PTBC-019 | Configuration | Evidence/document categories and mandatory evidence policies | WF-01–10/WF-12/FG-04 | WF-01; WF-02; WF-03; WF-04; WF-05; WF-06; WF-07; WF-08; WF-09; WF-10; WF-12; FG-04 | Before workflow UAT | BEFORE UAT | Before workflow UAT | A — Configurable value | Final categories and requirement rules by workflow/classification. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 27 | TBC-RPT-10; TBC-CFG-014; TBC-CFG-021; TBC-PRG-016; TBC-TSK-006; TBC-SUS-007; TBC-CLO-006; TBC-DOC-001; TBC-DOC-002; TBC-DOC-004; TBC-DOC-005; TBC-DOC-009; TBC-DOC-010; TBC-DOC-011; TBC-DOC-013; TBC-DOC-014; TBC-DOC-016; TBC-DOC-017; TBC-DOC-020; TBC-DOC-021; TBC-DOC-022; TBC-DOC-023; TBC-DOC-024; TBC-DOC-026; TBC-DOC-028; TBC-DOC-029; TBC-EXT-019 | 15 | BPK-010; BPK-014; BPK-017; BPK-025 | W2; W4; W6 | TASK-008; TASK-025; TASK-034; TASK-037; TASK-038; TASK-041; TASK-042; TASK-043; TASK-044; TASK-045; TASK-046; TASK-047; TASK-048; TASK-049; TASK-050; TASK-051; TASK-054; TASK-055; TASK-056; TASK-057; TASK-058; TASK-059; TASK-060; TASK-061; TASK-062; TASK-063; TASK-064; TASK-065
PTBC-020 | Configuration | Notification reminder offsets/escalation timing | WF-15 + source workflows | WF-15; WF-01; WF-02; WF-03; WF-04; WF-05; WF-06; WF-07; WF-08; WF-09; WF-10; WF-11; WF-12; WF-13; WF-14 | Before notification UAT | BEFORE UAT | Before notification UAT | A — Configurable value | Exact offsets/recurrence/recipient escalation levels. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 51 | TBC-RPT-28; TBC-CFG-011; TBC-INT-26; TBC-AUD-26; TBC-PCR-05; TBC-PCR-06; TBC-PCR-07; TBC-PCR-08; TBC-PRG-003; TBC-PRG-004; TBC-PRG-005; TBC-PRG-026; TBC-SCH-004; TBC-SCH-005; TBC-SCH-006; TBC-TSK-001; TBC-TSK-003; TBC-TSK-018; TBC-MIL-005; TBC-MIL-006; TBC-MIL-007; TBC-MIL-014; TBC-RSK-008; TBC-RSK-009; TBC-ISS-005; TBC-ISS-006; TBC-ISS-007; TBC-ISS-012; TBC-CHG-004; TBC-CHG-005; TBC-CHG-006; TBC-SUS-004; TBC-SUS-010; TBC-SUS-018; TBC-CLO-003; TBC-CLO-025; TBC-APR-003; TBC-APR-005; TBC-EXT-015; TBC-EXT-028; PERF-TBC-030; TBC-NTF-004; TBC-NTF-005; TBC-NTF-006; TBC-NTF-007; TBC-NTF-010; TBC-NTF-011; TBC-NTF-016; TBC-NTF-018; TBC-NTF-020; TBC-NTF-021 | 101 | BPK-012 | W2 | TASK-035; TASK-036; TASK-037; TASK-038; TASK-039; TASK-040; TASK-041; TASK-042; TASK-044; TASK-045; TASK-046; TASK-047; TASK-048; TASK-049; TASK-050; TASK-051; TASK-052; TASK-053; TASK-054; TASK-055; TASK-056; TASK-057; TASK-058; TASK-059; TASK-060; TASK-061; TASK-062; TASK-063; TASK-064; TASK-065; TASK-066; TASK-067; TASK-068
PTBC-021 | Configuration | Dashboard catalogue/defaults/personalization scope | FG-01 | FG-01 | Before dashboard UAT | BEFORE UAT | Before dashboard UAT | A — Configurable value | Final dashboard composition by audience and allowed personalization. | Exact approved authority/value/provider; no production default inferred. | OPEN | 12 DSH definitions, 11 MVP (14B v1.1 §6, awaiting AHDA signature) — composition/personalization none |  |  |  | PMO Engagement Lead / AHDA Business Sponsor (OQ-002) | 15 | TBC-DSH-001; TBC-DSH-002; TBC-DSH-003; TBC-DSH-005; TBC-DSH-006; TBC-DSH-009; TBC-DSH-012; TBC-DSH-014; TBC-DSH-015; TBC-DSH-017; TBC-DSH-022; TBC-DSH-024; TBC-DSH-025; TBC-DSH-029; TBC-DSH-030 | 16 | BPK-026 | W5 | TASK-069; TASK-070; TASK-071; TASK-072 | OQ-002 | ADR-006 | Step 14B RTM QA Closed
PTBC-022 | Configuration | Report catalogue/default access/saved-view sharing | FG-02 | FG-02 | Before report UAT | BEFORE UAT | Before report UAT | A — Configurable value | Final standard report list and sharing policy. | Exact approved authority/value/provider; no production default inferred. | OPEN | 26 RPT definitions, 23 MVP (14B v1.1 §6, awaiting AHDA signature) — final list/sharing policy none |  |  |  | PMO Engagement Lead / AHDA Business Sponsor (OQ-002) | 15 | TBC-DSH-013; TBC-RPT-01; TBC-RPT-03; TBC-RPT-05; TBC-RPT-08; TBC-RPT-09; TBC-RPT-13; TBC-RPT-15; TBC-RPT-16; TBC-RPT-18; TBC-RPT-20; TBC-RPT-21; TBC-RPT-22; TBC-RPT-30; TBC-INT-28 | 14 | BPK-027 | W5 | TASK-069; TASK-070; TASK-071; TASK-072 | OQ-002 | ADR-006 | Step 14B RTM QA Closed
PTBC-023 | Configuration | Overall Project Health rule/presentation policy | WF-02, FG-04, FG-01/02 | WF-02; FG-04; FG-01; FG-02 | Before executive UAT | BEFORE UAT | Before executive UAT | A — Configurable value | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor (domain owner) via FG-04 publication | 13 | TBC-DSH-007; TBC-PRG-001; TBC-PRG-006; TBC-PRG-007; TBC-PRG-009; TBC-PRG-010; TBC-PRG-011; TBC-PRG-013; TBC-PRG-014; TBC-PRG-015; TBC-PRG-018; TBC-PRG-022; TBC-PRG-023 | 12 | BPK-022 | W4 | TASK-034; TASK-044; TASK-045; TASK-054; TASK-069; TASK-070; TASK-071; TASK-072
PTBC-024 | Configuration | KPI catalogue/formulas/targets/condition thresholds | WF-14, FG-04 | WF-14; FG-04 | Before KPI UAT | BEFORE UAT | Before KPI UAT | A — Configurable value | Final KPI definitions, formulas/evidence/condition rules. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Risk & Portfolio Office (OQ-006) | 24 | TBC-DSH-021; TBC-RPT-24; TBC-CFG-023; TBC-INT-06; TBC-PCR-10; TBC-PRG-022; TBC-CHG-019; TBC-SUS-016; TBC-CLO-014; TBC-EXT-022; PERF-TBC-006; PERF-TBC-012; PERF-TBC-013; PERF-TBC-014; PERF-TBC-015; PERF-TBC-016; PERF-TBC-017; PERF-TBC-018; PERF-TBC-019; PERF-TBC-020; PERF-TBC-022; PERF-TBC-023; PERF-TBC-026; PERF-TBC-028 | 21 | BPK-021 | W3 | TASK-034; TASK-052; TASK-053; TASK-054; TASK-055 | OQ-006
PTBC-025 | Configuration | Financial condition/variance/forecast terminology and thresholds | WF-14, FG-04 | WF-14; FG-04 | Before financial UAT | BEFORE UAT | Before financial UAT | A — Configurable value | Final AHDA terms and attention/critical rules. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor / Risk & Portfolio Office (OQ-006) | 33 | TBC-DSH-018; TBC-DSH-019; TBC-DSH-020; TBC-DSH-027; TBC-RPT-11; TBC-RPT-23; TBC-RPT-25; TBC-CFG-023; TBC-INT-06; TBC-AUD-12; TBC-PCR-12; TBC-PRG-021; TBC-CHG-003; TBC-CHG-015; TBC-CHG-019; TBC-SUS-016; TBC-CLO-013; TBC-APR-002; TBC-EXT-022; PERF-TBC-001; PERF-TBC-002; PERF-TBC-003; PERF-TBC-004; PERF-TBC-005; PERF-TBC-008; PERF-TBC-009; PERF-TBC-010; PERF-TBC-011; PERF-TBC-020; PERF-TBC-022; PERF-TBC-023; PERF-TBC-024; PERF-TBC-025 | 22 | BPK-021 | W3 | TASK-034; TASK-052; TASK-053; TASK-054; TASK-055 | OQ-006
PTBC-026 | Cybersecurity | Platform criticality and data classification | PM Cyber Guide, FG-03/12/14/06 | CSB-CYBER-GUIDE; FG-03; WF-12; WF-14; FG-06 | Before production security sign-off | BEFORE PRODUCTION | Before irreversible design/provider commitment; retain source gate for final approval | B — Authority / policy decision | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT / Cybersecurity | 9 | TBC-DSH-028; TBC-IAM-009; TBC-CFG-001; TBC-CFG-020; TBC-INT-34; TBC-AUD-11; TBC-APR-002; TBC-APR-014; TBC-DOC-030 | 3 | BPK-005; BPK-006; BPK-008; BPK-030 | W1; W6 | TASK-007; TASK-010; TASK-011; TASK-012; TASK-013; TASK-014; TASK-015; TASK-016; TASK-017; TASK-018; TASK-019; TASK-020; TASK-021; TASK-022; TASK-023; TASK-024; TASK-025; TASK-026; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-037; TASK-038; TASK-052; TASK-053; TASK-054; TASK-073; TASK-074; TASK-077; TASK-078; TASK-079; TASK-080; TASK-081; TASK-082; TASK-083; TASK-084; TASK-085; TASK-086; TASK-087; TASK-088; TASK-090; TASK-091; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101 |  |  | Security Review & Threat Modeling Signed Off; External Penetration Test Passed | Source-family shorthand "FG-12/14" expanded to WF-12/WF-14 per 14B v1.1 §7 (14B-F-007).
PTBC-027 | Cybersecurity | MFA/PAM/privileged administration policy | FG-03, Cyber Guide | CSB-CYBER-GUIDE; FG-03 | Before production | BEFORE PRODUCTION | Before production | B — Authority / policy decision | Exact privileged authentication/PAM requirements and admin account model. | Exact approved authority/value/provider; no production default inferred. | OPEN | MFA enforced for R01 as minimum viable scope (TASK-029 AC) — exact MFA/PAM policy none |  |  |  | AHDA IT / Cybersecurity | 25 | TBC-IAM-001; TBC-IAM-002; TBC-IAM-005; TBC-IAM-007; TBC-IAM-008; TBC-IAM-010; TBC-IAM-011; TBC-IAM-012; TBC-IAM-013; TBC-IAM-014; TBC-IAM-015; TBC-IAM-016; TBC-IAM-018; TBC-IAM-020; TBC-IAM-021; TBC-IAM-022; TBC-IAM-023; TBC-IAM-024; TBC-CFG-020; TBC-AUD-08; TBC-APR-009; TBC-DOC-012; TBC-EXT-004; TBC-EXT-005; PERF-TBC-024 | 23 | BPK-006; BPK-030 | W1; W6 | TASK-010; TASK-020; TASK-023; TASK-025; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-079; TASK-081; TASK-082; TASK-083; TASK-085; TASK-086; TASK-087; TASK-088; TASK-090; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101 |  |  | Security Review & Threat Modeling Signed Off
PTBC-028 | Cybersecurity | Sensitive payload/change-set visibility and redaction rules | FG-05, FG-06 | FG-05; FG-06 | Before security UAT | BEFORE UAT | Before security UAT | B — Authority / policy decision | Which operational/audit fields may be viewed and by whom. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT / Cybersecurity | 7 | TBC-DSH-019; TBC-RPT-25; TBC-INT-21; TBC-INT-22; TBC-AUD-11; TBC-DOC-025; PERF-TBC-024 | 3 | BPK-006; BPK-009; BPK-010; BPK-020; BPK-023; BPK-028 | W1; W2; W4; W5 | TASK-009; TASK-025; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-037; TASK-038; TASK-060; TASK-061; TASK-065; TASK-066; TASK-067; TASK-068; TASK-073; TASK-074; TASK-075; TASK-076; TASK-079; TASK-081; TASK-092
PTBC-029 | Cybersecurity | Audit/SIEM forwarding catalogue and integration | FG-06, FG-05, Cyber Guide | CSB-CYBER-GUIDE; FG-06; FG-05 | Before production | BEFORE PRODUCTION | Before production | D — Architecture / integration contract | Event catalogue, endpoint/process and SOC ownership. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT / Cybersecurity | 4 | TBC-IAM-017; TBC-INT-24; TBC-AUD-22; TBC-AUD-23 | 5 | BPK-008; BPK-009; BPK-030 | W1; W6 | TASK-009; TASK-010; TASK-020; TASK-023; TASK-033; TASK-073; TASK-074; TASK-075; TASK-076; TASK-081; TASK-082; TASK-083; TASK-085; TASK-086; TASK-087; TASK-088; TASK-090; TASK-092; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101
PTBC-030 | Cybersecurity | Export watermark/classification/attachment policy | FG-02, FG-06, WF-15 | FG-02; FG-06; WF-15 | Before production | BEFORE PRODUCTION | Before production | B — Authority / policy decision | Output marking and whether sensitive attachments may ever be emailed. | Exact approved authority/value/provider; no production default inferred. | OPEN | PDF/XLSX/CSV export baseline (ADR-005 ratifies ICD-17) — watermark/classification/attachment policy none |  |  |  | AHDA IT / Cybersecurity | 5 | TBC-RPT-06; TBC-RPT-14; TBC-INT-34; TBC-AUD-25; TBC-DOC-025 | 0 | BPK-027; BPK-010 | W2; W5 | TASK-010; TASK-033; TASK-037; TASK-038; TASK-039; TASK-040; TASK-071; TASK-072; TASK-073; TASK-074 |  | ADR-005 |  | Zero affected RTM rows (14B v1.1 §8 analytical gap; does not block the gate).
PTBC-031 | Cybersecurity | External identity proofing / Nafath applicability | WF-13, FG-03, FG-05 | WF-13; FG-03; FG-05 | Before External integration UAT | BEFORE UAT | Before irreversible design/provider commitment; retain source gate for final approval | D — Architecture / integration contract | Provider/use cases and data-minimization policy. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT (Identity) / Business Sponsor (OQ-007) | 2 | TBC-INT-03; TBC-EXT-004 | 1 | BPK-006; BPK-023 | W1; W5 | TASK-025; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-066; TASK-067; TASK-068; TASK-075; TASK-076; TASK-079; TASK-081; TASK-092 | OQ-007 |  | Security Review & Threat Modeling Signed Off
PTBC-032 | Integration | Production Integration catalogue and system owners | FG-05, Cyber Guide | CSB-CYBER-GUIDE; FG-05 | Before integration build/SIT | BEFORE BUILD / SIT | Before irreversible design/provider commitment; retain source gate for final approval | D — Architecture / integration contract | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT (system owners) | 22 | TBC-IAM-016; TBC-INT-01; TBC-INT-03; TBC-INT-04; TBC-INT-05; TBC-INT-07; TBC-INT-09; TBC-INT-10; TBC-INT-11; TBC-INT-13; TBC-INT-16; TBC-INT-28; TBC-INT-30; TBC-INT-31; TBC-INT-32; TBC-CLO-023; TBC-DOC-015; TBC-EXT-004; TBC-NTF-002; TBC-NTF-003; TBC-NTF-014; TBC-NTF-022 | 13 | BPK-009; BPK-030 | W1; W6 | TASK-009; TASK-010; TASK-020; TASK-023; TASK-075; TASK-076; TASK-081; TASK-082; TASK-083; TASK-085; TASK-086; TASK-087; TASK-088; TASK-090; TASK-092; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101
PTBC-033 | Integration | Financial/KPI authoritative source systems and field authority | WF-14, FG-05 | WF-14; FG-05 | Before financial integration SIT | BEFORE BUILD / SIT | Before irreversible design/provider commitment; retain source gate for final approval | D — Architecture / integration contract | Source-of-truth fields, cadence, reconciliation and fallback policy. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT (system owners) | 8 | TBC-INT-06; TBC-SUS-016; TBC-CLO-013; TBC-EXT-022; PERF-TBC-001; PERF-TBC-002; PERF-TBC-009; PERF-TBC-020 | 8 | BPK-021; BPK-009 | W1; W3 | TASK-009; TASK-052; TASK-053; TASK-054; TASK-075; TASK-076; TASK-092
PTBC-034 | Integration | Email/SMS provider topology and callbacks | WF-15, FG-05 | WF-15; FG-05 | Before notification SIT | BEFORE BUILD / SIT | Before irreversible design/provider commitment; retain source gate for final approval | D — Architecture / integration contract | Provider/gateway capabilities, callback semantics and throttling. | Exact approved authority/value/provider; no production default inferred. | OPEN | In-App + Email MVP channels; SMS Conditional/TBC (ADR-004 ratifies CSB-BP2 §15) — provider/topology none |  |  |  | AHDA IT (system owners) | 29 | TBC-RPT-19; TBC-CFG-024; TBC-INT-04; TBC-INT-05; TBC-INT-13; TBC-PCR-15; TBC-PRG-024; TBC-SCH-016; TBC-TSK-017; TBC-MIL-016; TBC-RSK-020; TBC-ISS-014; TBC-CHG-020; TBC-SUS-017; TBC-CLO-024; TBC-APR-017; TBC-EXT-023; PERF-TBC-027; TBC-NTF-001; TBC-NTF-002; TBC-NTF-003; TBC-NTF-009; TBC-NTF-012; TBC-NTF-013; TBC-NTF-014; TBC-NTF-017; TBC-NTF-022; TBC-NTF-023; TBC-NTF-025 | 341 | BPK-012; BPK-009 | W1; W2 | TASK-009; TASK-039; TASK-040; TASK-075; TASK-076; TASK-092 |  | ADR-004
PTBC-035 | Integration | Document storage/malware-scan provider and quarantine operations | WF-12, FG-05 | WF-12; FG-05 | Before document SIT | BEFORE BUILD / SIT | Before irreversible design/provider commitment; retain source gate for final approval | D — Architecture / integration contract | Technology, retry/quarantine operating procedure. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT (system owners) | 2 | TBC-INT-07; TBC-DOC-003 | 1 | BPK-010; BPK-009 | W1; W2 | TASK-009; TASK-037; TASK-038; TASK-075; TASK-076; TASK-092
PTBC-036 | Integration | SSO/directory topology and group/claim mappings | FG-03, FG-05 | FG-03; FG-05 | Before IAM SIT | BEFORE BUILD / SIT | Before irreversible design/provider commitment; retain source gate for final approval | D — Architecture / integration contract | Authoritative directory, sync model, role-group mappings if any. | Exact approved authority/value/provider; no production default inferred. | OPEN | AD/LDAP + SSO per ADM-041 (TASK-028) — authoritative directory/sync model none |  |  |  | AHDA IT (system owners) | 4 | TBC-IAM-003; TBC-IAM-004; TBC-INT-02; TBC-CLO-016 | 13 | BPK-006; BPK-009 | W1 | TASK-009; TASK-025; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-075; TASK-076; TASK-079; TASK-092
PTBC-037 | Integration | Integration health/freshness/reconciliation thresholds | FG-05 | FG-05 | Before operations UAT | BEFORE UAT | Before operations UAT | A — Configurable value | Exact latency/failure/backlog/stale/tolerance thresholds. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT (system owners) | 14 | TBC-DSH-010; TBC-DSH-011; TBC-CFG-027; TBC-INT-08; TBC-INT-12; TBC-INT-15; TBC-INT-27; TBC-PRG-012; TBC-PRG-013; TBC-PRG-017; TBC-SCH-003; TBC-TSK-014; TBC-RSK-016; PERF-TBC-020 | 7 | BPK-009; BPK-013 | W1; W2 | TASK-009; TASK-069; TASK-075; TASK-076; TASK-092 |  |  | Operational Runbooks & On-Call Ready
PTBC-038 | Integration | Retry/backoff/dead-letter policies | FG-05 and integration adapters | FG-05; INTEGRATION-ADAPTERS | Before SIT | BEFORE BUILD / SIT | Before SIT | A — Configurable value | Counts/backoff/final-failure rules; architecture already requires idempotency. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT (system owners) | 6 | TBC-INT-13; TBC-INT-14; TBC-INT-20; TBC-APR-018; TBC-DOC-003; TBC-NTF-014 | 4 | BPK-009; BPK-012 | W1; W2 | TASK-009; TASK-039; TASK-040; TASK-075; TASK-076; TASK-092
PTBC-039 | UX/Presentation | Arabic/English completeness and historical label policy | All; FG-01/02/06 | ALL; FG-01; FG-02; FG-06 | Before UAT | BEFORE UAT | Before UAT | A — Configurable value | Combined vs single-language reports, historical labels and translation governance. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor | 6 | TBC-RPT-07; TBC-INT-33; TBC-AUD-30; TBC-PRG-025; TBC-EXT-027; TBC-NTF-008 | 7 | BPK-007; BPK-013; BPK-026; BPK-027 | W1; W2; W5 | TASK-008; TASK-025; TASK-027; TASK-032; TASK-033; TASK-034; TASK-036; TASK-038; TASK-040; TASK-042; TASK-045; TASK-047; TASK-049; TASK-051; TASK-053; TASK-056; TASK-058; TASK-061; TASK-064; TASK-067; TASK-069; TASK-070; TASK-071; TASK-072; TASK-073; TASK-074; TASK-076; TASK-096
PTBC-040 | UX/Presentation | Accessibility conformance target | FG-01/02 and common UI | FG-01; FG-02; COMMON-UI | Before UAT | BEFORE UAT | Before UAT | A — Configurable value | Exact standard/target remains governance TBC; functional accessibility already required. | Exact approved authority/value/provider; no production default inferred. | OPEN | WCAG 2.1 AA (OQ-010, TASK-087, Release Checklist) — working baseline, not approved |  |  |  | AHDA Business Sponsor / AHDA IT (OQ-010) | 2 | TBC-DSH-026; TBC-RPT-27 | 1 | BPK-005; BPK-026; BPK-027 | W1; W5 | TASK-007; TASK-011; TASK-012; TASK-013; TASK-014; TASK-015; TASK-016; TASK-017; TASK-018; TASK-019; TASK-020; TASK-021; TASK-022; TASK-023; TASK-024; TASK-026; TASK-032; TASK-036; TASK-038; TASK-040; TASK-042; TASK-045; TASK-047; TASK-049; TASK-051; TASK-053; TASK-056; TASK-058; TASK-061; TASK-064; TASK-067; TASK-069; TASK-070; TASK-071; TASK-072; TASK-074; TASK-076; TASK-077; TASK-078; TASK-080; TASK-084; TASK-086; TASK-087; TASK-090; TASK-091 | OQ-010 |  | Accessibility Audit Findings Closed
PTBC-041 | UX/Presentation | Executive dashboard/report content and R07 scope | FG-01/02/03 | FG-01; FG-02; FG-03 | Before executive UAT | BEFORE UAT | Before executive UAT | A — Configurable value | Final metrics/composition and authorized enterprise/portfolio scope. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA Business Sponsor | 11 | TBC-DSH-004; TBC-DSH-016; TBC-PCR-03; TBC-PCR-04; TBC-PRG-008; TBC-SCH-008; TBC-MIL-010; TBC-RSK-020; TBC-CHG-014; TBC-SUS-013; TBC-CLO-021 | 12 | BPK-006; BPK-026; BPK-027 | W1; W5 | TASK-025; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-069; TASK-070; TASK-071; TASK-072; TASK-079
PTBC-042 | UX/Presentation | Geospatial/map and advanced visualization requirement | FG-01 | FG-01 | Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | Can remain configurable/deferred | B — Authority / policy decision | Only implement if AHDA confirms business value/data quality. | Exact approved authority/value/provider; no production default inferred. | OPEN | SCR-035 map view DEFERRED unless AHDA confirms (14B v1.1 §5.3 row 32; 15-D-006) |  |  |  | AHDA Business Sponsor (14B v1.1 §9 F-003 row 32) | 17 | TBC-DSH-008; TBC-RPT-02; TBC-IAM-003; TBC-IAM-019; TBC-CFG-005; TBC-PCR-16; TBC-PCR-17; TBC-RSK-004; TBC-ISS-003; TBC-ISS-016; TBC-CHG-001; TBC-CHG-009; TBC-DOC-018; TBC-EXT-011; TBC-EXT-026; PERF-TBC-029; TBC-NTF-024 | 15 | BPK-026; BPK-031 | Deferred; W5 | TASK-002; TASK-069; TASK-070 | OQ-004 |  |  | 16 of 17 associated source TBCs are not geospatial — see 06_Findings 004-F-001; only TBC-DSH-008 is a map requirement. SCR-035 deferred unless confirmed (14B v1.1 §5.3).
PTBC-043 | Technical Architecture | Performance/scale thresholds and cache/materialization TTLs | FG-01/02/05/06 + Cyber Guide | CSB-CYBER-GUIDE; FG-01; FG-02; FG-05; FG-06 | Before performance test | BEFORE BUILD / SIT | Before performance test | A — Configurable value | Exact NFRs, concurrency and refresh targets. | Exact approved authority/value/provider; no production default inferred. | OPEN | 150 named users / 10–25 active / 50 peak (brief; OQ-010, TASK-026, TASK-086) — working baseline, not approved |  |  |  | AHDA Business Sponsor / AHDA IT (OQ-010) | 13 | TBC-DSH-011; TBC-DSH-027; TBC-RPT-11; TBC-RPT-24; TBC-RPT-28; TBC-CFG-027; TBC-INT-13; TBC-AUD-27; TBC-SCH-003; TBC-ISS-004; TBC-ISS-015; PERF-TBC-030; TBC-NTF-014 | 14 | BPK-005; BPK-009; BPK-013; BPK-030 | W1; W2; W6 | TASK-007; TASK-009; TASK-010; TASK-011; TASK-012; TASK-013; TASK-014; TASK-015; TASK-016; TASK-017; TASK-018; TASK-019; TASK-020; TASK-021; TASK-022; TASK-023; TASK-024; TASK-026; TASK-033; TASK-069; TASK-070; TASK-071; TASK-072; TASK-073; TASK-074; TASK-075; TASK-076; TASK-077; TASK-078; TASK-080; TASK-081; TASK-082; TASK-083; TASK-084; TASK-085; TASK-086; TASK-087; TASK-088; TASK-090; TASK-091; TASK-092; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101 | OQ-010 |  | Performance/Load Test Within Target
PTBC-044 | Technical Architecture | Observability/logging/APM technology stack | FG-05/06, Cyber Guide | CSB-CYBER-GUIDE; FG-05; FG-06 | Before production | BEFORE PRODUCTION | Before production | D — Architecture / integration contract | Functional contracts fixed; products/platform selection by architecture/AHDA IT. | Exact approved authority/value/provider; no production default inferred. | OPEN | Stack ADR-002 proposed React/ASP.NET Core/PostgreSQL — APM/logging products none |  |  |  | AHDA IT + Engagement Architect | 1 | TBC-INT-25 | 0 | BPK-005; BPK-009; BPK-030 | W1; W6 | TASK-006; TASK-007; TASK-009; TASK-010; TASK-011; TASK-012; TASK-013; TASK-014; TASK-015; TASK-016; TASK-017; TASK-018; TASK-019; TASK-020; TASK-021; TASK-022; TASK-023; TASK-024; TASK-026; TASK-033; TASK-073; TASK-074; TASK-075; TASK-076; TASK-077; TASK-078; TASK-080; TASK-081; TASK-082; TASK-083; TASK-084; TASK-085; TASK-086; TASK-087; TASK-088; TASK-090; TASK-091; TASK-092; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101 |  | ADR-002 |  | Zero affected RTM rows (14B v1.1 §8 analytical gap; does not block the gate).
PTBC-045 | Technical Architecture | Immutable audit/tamper-evidence/archive implementation | FG-06 | FG-06 | Before production | BEFORE PRODUCTION | Before irreversible design/provider commitment; retain source gate for final approval | D — Architecture / integration contract | Technology choice for protected store/integrity/archive. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT + Engagement Architect | 1 | TBC-AUD-20 | 0 | BPK-008; BPK-028; BPK-030 | W1; W5; W6 | TASK-023; TASK-033; TASK-073; TASK-074; TASK-081; TASK-082; TASK-083; TASK-085; TASK-086; TASK-087; TASK-088; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101 |  |  |  | Zero affected RTM rows (14B v1.1 §8 analytical gap; does not block the gate).
PTBC-046 | Operations | Operational alert recipients, maintenance governance and production retry authority | FG-05 | FG-05 | Before operations UAT | BEFORE UAT | Before operations UAT | A — Configurable value | Who can acknowledge/retry/reprocess in PROD and maintenance handling. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT / Operations | 6 | TBC-INT-17; TBC-INT-18; TBC-INT-19; TBC-INT-20; TBC-INT-34; TBC-MIL-006 | 3 | BPK-009; BPK-012 | W1; W2 | TASK-009; TASK-039; TASK-040; TASK-075; TASK-076; TASK-092 |  |  | Operational Runbooks & On-Call Ready
PTBC-047 | Records/Retention | Document/report/audit/log retention and legal-hold policy | WF-12, FG-02, FG-05, FG-06 | WF-12; FG-02; FG-05; FG-06 | Before production | BEFORE PRODUCTION | Before production | A — Configurable value | Exact retention, archive, disposal, hold rules and owners. | Exact approved authority/value/provider; no production default inferred. | OPEN |  |  |  |  | AHDA IT / Cybersecurity + Records owner | 25 | TBC-DSH-028; TBC-RPT-12; TBC-RPT-29; TBC-IAM-017; TBC-IAM-025; TBC-CFG-026; TBC-INT-22; TBC-INT-23; TBC-INT-29; TBC-AUD-09; TBC-AUD-15; TBC-AUD-16; TBC-AUD-19; TBC-TSK-006; TBC-ISS-009; TBC-CHG-021; TBC-CLO-019; TBC-DOC-003; TBC-DOC-007; TBC-DOC-008; TBC-DOC-027; TBC-EXT-024; PERF-TBC-030; TBC-NTF-015; TBC-NTF-019 | 18 | BPK-008; BPK-010; BPK-027; BPK-028; BPK-030 | W1; W2; W5; W6 | TASK-023; TASK-033; TASK-037; TASK-038; TASK-071; TASK-072; TASK-073; TASK-074; TASK-075; TASK-076; TASK-081; TASK-082; TASK-083; TASK-085; TASK-086; TASK-087; TASK-088; TASK-092; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101
PTBC-048 | Records/Retention | Backup/DR RPO/RTO, backup retention and residency/hosting | Cyber Guide, FG-05/06 | CSB-CYBER-GUIDE; FG-05; FG-06 | Before production | BEFORE PRODUCTION | Before irreversible design/provider commitment; retain source gate for final approval | A — Configurable value | AHDA-approved KSA/hosting architecture and recovery targets. | Exact approved authority/value/provider; no production default inferred. | OPEN | GCP architecture proposed (ADR-001 Option B) — not selected; RPO/RTO/retention values none |  |  |  | AHDA IT / Cybersecurity (OQ-001, OQ-003, 14B v1.1 §9) | 3 | TBC-AUD-28; TBC-AUD-29; TBC-DOC-027 | 220 | BPK-005; BPK-030 | W1; W6 | TASK-005; TASK-007; TASK-010; TASK-011; TASK-012; TASK-013; TASK-014; TASK-015; TASK-016; TASK-017; TASK-018; TASK-019; TASK-020; TASK-021; TASK-022; TASK-023; TASK-024; TASK-026; TASK-033; TASK-073; TASK-074; TASK-075; TASK-076; TASK-077; TASK-078; TASK-080; TASK-081; TASK-082; TASK-083; TASK-084; TASK-085; TASK-086; TASK-087; TASK-088; TASK-090; TASK-091; TASK-092; TASK-093; TASK-098; TASK-099; TASK-100; TASK-101 | OQ-001; OQ-003 | ADR-001 | Backup & DR Restore Drill Passed; Architecture Decisions Approved

## 02_Source_TBC_Register
Source TBC ID | Owner spec | Original governance item (as recorded) | Source location | PTBC themes (14B crosswalk — controlling) | PTBC gates (as recorded) | Earliest gate class (14B v1.1 §8) | Step 15 packages | Explicit RTM references | Analytical RTM rows (count) | RTM coverage | Status | Association review (TASK-004) | Proposed PTBC (TASK-004, for confirmation) | Proposed gate class | Review note | Resolution reference | Resolved by | Resolution date
TBC-DSH-001 | FG-01 | Final dashboard catalogue/content composition. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 2 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-002 | FG-01 | Canonical Dashboard screen-ID reconciliation and whether any missing experiences require design-derived IDs. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 3 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-003 | FG-01 | Default dashboard resolution for users with multiple roles/audiences. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 4 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-004 | FG-01 | R07 Executive Management business/data scope. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 5 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-005 | FG-01 | Portfolio assignment, scope and hierarchy semantics. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 6 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-006 | FG-01 | Department hierarchy roll-up behavior for DEPT scope. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 7 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-007 | FG-01 | Official Project Health presentation and authoritative projection confirmation. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 8 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-026 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DSH-008 | FG-01 | Final MVP widget catalogue and whether map/location visualization is required. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 9 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-026 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DSH-009 | FG-01 | Allowed dashboard-level aggregations beyond the safe baseline defined here. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 10 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-010 | FG-01 | Source-projection refresh expectations and freshness presentation policy by domain. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 11 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-026 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DSH-011 | FG-01 | Cache/materialized-projection TTL and invalidation tolerances. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 12 | PTBC-037; PTBC-043 | PTBC-037 Before operations UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-026 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DSH-012 | FG-01 | Final user personalization scope, including widget reorder/hide. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 13 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-013 | FG-01 | Saved dashboard views and whether sharing is permitted. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 14 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-026 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DSH-014 | FG-01 | Cross-filtering interaction scope. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 15 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-015 | FG-01 | Historical/as-of dashboard capability beyond source-provided trends/snapshots. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 16 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-016 | FG-01 | Executive commentary requirement and ownership if included. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 17 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-017 | FG-01 | Final External Contributor dashboard content. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 18 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-018 | FG-01 | Sensitive financial widget classifications and additional permissions. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 19 | PTBC-012; PTBC-025 | PTBC-012 Before production; PTBC-025 Before financial UAT | BEFORE UAT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-019 | FG-01 | Project-level financial masking rules. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 20 | PTBC-025; PTBC-028 | PTBC-025 Before financial UAT; PTBC-028 Before security UAT | BEFORE UAT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-020 | FG-01 | Portfolio currency aggregation/conversion policy if multi-currency becomes applicable. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 21 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-021 | FG-01 | Approved cross-Project KPI aggregation methods, if any. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 22 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-026 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-022 | FG-01 | Dashboard print/snapshot requirement. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 23 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-023 | FG-01 | Dashboard publication authority by dashboard type/audience. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 24 | PTBC-010 | PTBC-010 Before admin UAT | BEFORE UAT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-024 | FG-01 | Dashboard configuration author/validator/publisher separation-of-duties requirements. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 25 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-025 | FG-01 | Bilingual completeness requirements for Dashboard Definitions/widgets. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 26 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-026 | FG-01 | Applicable accessibility standard/target conformance level. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 27 | PTBC-040 | PTBC-040 Before UAT | BEFORE UAT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-027 | FG-01 | Technical performance and concurrency targets. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 28 | PTBC-025; PTBC-043 | PTBC-025 Before financial UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-026 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-028 | FG-01 | Usage telemetry retention/privacy policy. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 29 | PTBC-026; PTBC-047 | PTBC-026 Before production security sign-off; PTBC-047 Before production | BEFORE PRODUCTION | BPK-026 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DSH-029 | FG-01 | Data-quality/coverage warning thresholds and display conventions. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 30 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DSH-030 | FG-01 | Exact FG-02 dashboard-to-report handoff contract and export/print ownership. Mechanism development-ready; value/policy TBC | Project_Management_Platform_FG-01_Dashboards_Functional_Specification_v1.0.docx :: 31. Controlled TBC Register :: table 56, row 31 | PTBC-021 | PTBC-021 Before dashboard UAT | BEFORE UAT | BPK-026 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-01 | FG-02 | Final AHDA standard Report Catalogue, names and mandatory/optional reports. Governance/Configuration | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 2 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-02 | FG-02 | Final detailed mapping within canonical SCR-130–140 where Blueprint names overlap specific report experiences. Platform reconciliation | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 3 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-022 | BEFORE UAT | Report screen mapping within SCR-130–140 is report-catalogue governance, not geospatial
TBC-RPT-03 | FG-02 | Default Report access by role/persona beyond FG-03 action/scope mechanics. Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 4 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-04 | FG-02 | Report publication authority by report family/sensitivity. Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 5 | PTBC-010 | PTBC-010 Before admin UAT | BEFORE UAT | BPK-027 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-05 | FG-02 | Report Definition author/validator/publisher separation-of-duties requirements. Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 6 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-06 | FG-02 | Official PDF branding, templates, classification/footer/watermark presentation. Branding/Security | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 7 | PTBC-030 | PTBC-030 Before production | BEFORE PRODUCTION | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-07 | FG-02 | Supported output language policy: Arabic, English, combined bilingual by report/output type. Localization | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 8 | PTBC-039 | PTBC-039 Before UAT | BEFORE UAT | BPK-027 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-08 | FG-02 | Final XLSX/CSV encoding, worksheet, delimiter and technical conventions. Technical | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 9 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-09 | FG-02 | Maximum dataset suitable for synchronous on-screen execution. Technical | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 10 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-10 | FG-02 | Maximum export row/file size and permitted exceptions. Technical/Security | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 11 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-11 | FG-02 | Job concurrency, rate limiting and resource-abuse thresholds. Technical/Security | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 12 | PTBC-025; PTBC-043 | PTBC-025 Before financial UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-027 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-12 | FG-02 | Temporary Generated Output retention/expiry periods. Records/Technical | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 13 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-13 | FG-02 | Which report executions/exports/downloads require enhanced audit logging. Security/Audit | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 14 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-14 | FG-02 | Exact watermark/classification-marking rules for generated outputs. Security | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 15 | PTBC-030 | PTBC-030 Before production | BEFORE PRODUCTION | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-15 | FG-02 | Which Report families are eligible to create formal Report Snapshots. Records/Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 16 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-16 | FG-02 | Whether limited Scheduled Reports are mandatory MVP or enabled conditionally after launch. Product/Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 17 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-17 | FG-02 | Permitted schedule frequencies, calendars and blackout/quiet-period behavior. Governance/Configuration | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 18 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-18 | FG-02 | Scheduled Report owner reassignment authority/process. Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 19 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-19 | FG-02 | Whether any Report outputs may be attached directly to email and under what classification. Security | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 20 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-20 | FG-02 | Shared/team Saved View policy and sharing authority. Product/Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 21 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-21 | FG-02 | Advanced grouping/pivot capability beyond baseline sort/group. Product | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 22 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-22 | FG-02 | Source domains/Reports supporting arbitrary As-Of versus fixed historical snapshots only. Data Architecture | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 23 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-23 | FG-02 | Portfolio financial aggregation/conversion policy where multiple currencies exist. Finance/Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 24 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-027 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-24 | FG-02 | Approved KPI aggregation methods by KPI family, if any. Performance/Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 25 | PTBC-024; PTBC-043 | PTBC-024 Before KPI UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-027 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-25 | FG-02 | Sensitive financial fields, masking and export restrictions by audience. Finance/Security | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 26 | PTBC-025; PTBC-028 | PTBC-025 Before financial UAT; PTBC-028 Before security UAT | BEFORE UAT | BPK-027 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-26 | FG-02 | External Entity Report and export eligibility/field rules. External Access Governance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 27 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-27 | FG-02 | Accessibility conformance target for on-screen and generated outputs. UX/Compliance | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 28 | PTBC-040 | PTBC-040 Before UAT | BEFORE UAT | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-28 | FG-02 | Report query/render/job technical performance SLAs. Technical | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 29 | PTBC-020; PTBC-043 | PTBC-020 Before notification UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-027 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RPT-29 | FG-02 | Final FG-06 audit retention/search/export contract for Report/Export events. Cross-Feature | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 30 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-027 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RPT-30 | FG-02 | Final FG-05 operational monitoring/alerting contract for Report infrastructure. Cross-Feature | Project_Management_Platform_FG-02_Reports_Filters_Export_Functional_Specification_v1.0.docx :: 28. Controlled TBC Register :: table 41, row 31 | PTBC-022 | PTBC-022 Before report UAT | BEFORE UAT | BPK-027 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-001 | FG-03 | Exact AHDA role-assignment authority by role/scope. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 2 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-002 | FG-03 | Whether custom roles beyond R01–R08 are enabled in MVP. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 3 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-003 | FG-03 | Exact mappings, if any, from directory groups to platform roles. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 4 | PTBC-036; PTBC-042 | PTBC-036 Before IAM SIT; PTBC-042 Can remain configurable/deferred | BEFORE BUILD / SIT | BPK-006 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-036 | BEFORE BUILD / SIT | Directory group→role mapping is already PTBC-036; drop PTBC-042
TBC-IAM-004 | FG-03 | Authoritative HR/directory source for department, manager and job-title attributes. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 5 | PTBC-036 | PTBC-036 Before IAM SIT | BEFORE BUILD / SIT | BPK-006 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-005 | FG-03 | Department hierarchy semantics for DEPT scope, including child units. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 6 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-006 | FG-03 | External Entity enablement and onboarding/sponsor policy. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 7 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-006 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-007 | FG-03 | External Entity authentication method and MFA requirements. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 8 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-008 | FG-03 | Exact external permitted modules/actions by business process. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 9 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-009 | FG-03 | Sensitive data classification taxonomy and field-level restrictions. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 10 | PTBC-026 | PTBC-026 Before production security sign-off | BEFORE PRODUCTION | BPK-006 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-IAM-010 | FG-03 | Step-up authentication triggers for privileged/sensitive actions. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 11 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-011 | FG-03 | Privileged R01 assignment approval/governance process. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 12 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-012 | FG-03 | Temporary elevated-access approval process and maximum duration. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 13 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-013 | FG-03 | Whether time-bound direct user permission exceptions are enabled. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 14 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-014 | FG-03 | Access-review frequency and reviewer responsibility. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 15 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-015 | FG-03 | Full access-recertification campaign scope for MVP versus later phase. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 16 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-016 | FG-03 | Session invalidation behavior available from the chosen identity provider. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 17 | PTBC-027; PTBC-032 | PTBC-027 Before production; PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-017 | FG-03 | Authorization-denied event retention/monitoring thresholds for SIEM. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 18 | PTBC-029; PTBC-047 | PTBC-029 Before production; PTBC-047 Before production | BEFORE PRODUCTION | BPK-006 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-018 | FG-03 | Service/integration identity credential platform and ownership. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 19 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-019 | FG-03 | Whether canonical role permission mappings are administered in FG-03 UI or published through FG-04 governance. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 20 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-006 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-027 | BEFORE PRODUCTION | Where role-permission mappings are administered is an admin-model decision (PTBC-027) or an FG-03/FG-04 boundary ICD; not geospatial
TBC-IAM-020 | FG-03 | Custom role/permission profile versioning strategy in FG-04 if enabled. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 21 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-021 | FG-03 | Project access assignment authorities for PM/Liaison/Contributor/Viewer relationships. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 22 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-022 | FG-03 | Exact “last required owner/PM” Project policy. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 23 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-023 | FG-03 | Mobile administration actions permitted by security policy. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 24 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-024 | FG-03 | Export permission model for user/access reports. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 25 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-006 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-IAM-025 | FG-03 | Retention period for IAM access-history records, governed with FG-06/cybersecurity policy. | Project_Management_Platform_FG-03_Users_Roles_Permissions_Functional_Specification_v1.0.docx :: 27. Configuration / TBC Register :: table 45, row 26 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-006 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-001 | FG-04 | Exact AHDA configuration publication authorities by family/criticality. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 2 | PTBC-026 | PTBC-026 Before production security sign-off | BEFORE PRODUCTION | BPK-007 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-002 | FG-04 | Which policy families mandate author/publisher separation versus configurable SoD. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 3 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-003 | FG-04 | Which sensitive configuration changes require WF-11 approval. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 4 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-004 | FG-04 | Exact Risk Probability labels/descriptions and Impact levels/dimensions. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 5 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-007 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-005 | FG-04 | Exact 5×5 Risk Matrix cell mappings, rating labels and display tokens. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 6 | PTBC-017; PTBC-042 | PTBC-017 Before risk UAT; PTBC-042 Can remain configurable/deferred | BEFORE UAT | BPK-007 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-017 | BEFORE UAT | 5×5 risk matrix cell mapping is already PTBC-017; drop PTBC-042
TBC-CFG-006 | FG-04 | Exact Risk review/escalation policy values. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 7 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-007 | FG-04 | Exact Issue Severity/Priority levels and governance. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 8 | PTBC-018 | PTBC-018 Before concern UAT | BEFORE UAT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-008 | FG-04 | Exact Change Materiality thresholds and classification values. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 9 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-007 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-009 | FG-04 | Controlled Commitment catalogue values and ownership sources. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 10 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-010 | FG-04 | Exact Approval authority thresholds/limits and routing policies. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 11 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-011 | FG-04 | Approval SLA durations, Due Soon windows, calendars and escalation timing. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 12 | PTBC-014; PTBC-020 | PTBC-014 Before SLA/schedule UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-007 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-012 | FG-04 | Exact Suspension categories/review cadence and readiness criteria. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 13 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-013 | FG-04 | Exact Completion/Closure readiness criteria and blocking/conditional policy. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 14 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-014 | FG-04 | Evidence requirement policies and any approved minimum-count rules. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 15 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-007 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-015 | FG-04 | Exact AHDA business calendar(s), weekends and holiday authoritative source. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 16 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-007 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-016 | FG-04 | Bilingual completeness policy by configuration family. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 17 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-017 | FG-04 | Whether Department/Portfolio-scoped overrides are required in MVP. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 18 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-018 | FG-04 | Any individual-Project override families permitted by governance. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 19 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-019 | FG-04 | Custom role/permission-profile template configuration scope versus FG-03. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 20 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-020 | FG-04 | Sensitive data classification taxonomy and step-up MFA triggers. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 21 | PTBC-026; PTBC-027 | PTBC-026 Before production security sign-off; PTBC-027 Before production | BEFORE PRODUCTION | BPK-007 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-021 | FG-04 | Document categories/evidence integration final contract with WF-12. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 22 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-007 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-022 | FG-04 | External Entity configuration policy finalization with WF-13. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 23 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-023 | FG-04 | KPI/Financial master/policy configuration finalization with WF-14. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 24 | PTBC-024; PTBC-025 | PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT | BEFORE UAT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-024 | FG-04 | Notification template/channel/preference configuration boundary with WF-15. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 25 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-007 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-025 | FG-04 | Exact import/export formats, size limits and approver requirements for bulk changes. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 26 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-026 | FG-04 | Configuration retention duration and archival policy with FG-06/records governance. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 27 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-027 | FG-04 | Operational cache refresh tolerances and alert thresholds with FG-05/Operations. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 28 | PTBC-037; PTBC-043 | PTBC-037 Before operations UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-028 | FG-04 | Exact emergency deactivation authority/process for defective critical policy. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 29 | PTBC-002 | PTBC-002 Before UAT | BEFORE UAT | BPK-007 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CFG-029 | FG-04 | Whether label-only changes require full policy approval for sensitive families. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 30 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CFG-030 | FG-04 | Exact Application Configuration items permitted under ADM-055 versus technical operations. Configuration/TBC | Project_Management_Platform_FG-04_Master_Data_Configuration_Functional_Specification_v1.0.docx :: 23.3 Configuration / TBC Register :: table 41, row 31 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-007 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-01 | FG-05 | Final Integration catalogue and which integrations are enabled in the production platform. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 2 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-02 | FG-05 | SSO/directory topology, authoritative directory/source and synchronization model. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 3 | PTBC-036 | PTBC-036 Before IAM SIT | BEFORE BUILD / SIT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-03 | FG-05 | Nafath scope, identity-proofing use cases and provider contract. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 4 | PTBC-031; PTBC-032 | PTBC-031 Before External integration UAT; PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-04 | FG-05 | Email/Exchange provider/topology and available delivery/health callbacks. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 5 | PTBC-032; PTBC-034 | PTBC-032 Before integration build/SIT; PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-05 | FG-05 | Whether SMS is enabled and, if enabled, provider/topology. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 6 | PTBC-032; PTBC-034 | PTBC-032 Before integration build/SIT; PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-06 | FG-05 | Authoritative Financial and KPI source systems and integration patterns. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 7 | PTBC-024; PTBC-025; PTBC-033 | PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT | BEFORE BUILD / SIT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-07 | FG-05 | Document storage and malware-scanning providers/architecture. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 8 | PTBC-032; PTBC-035 | PTBC-032 Before integration build/SIT; PTBC-035 Before document SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-08 | FG-05 | Exact Integration Health thresholds and combination policy. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 9 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-009 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-09 | FG-05 | Latency thresholds by integration/operation. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 10 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-10 | FG-05 | Failure-rate thresholds and evaluation windows. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 11 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-11 | FG-05 | Queue/backlog and oldest-item thresholds. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 12 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-12 | FG-05 | Expected data-refresh frequencies and source-domain freshness thresholds. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 13 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-009 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-13 | FG-05 | Automatic/manual retry counts, backoff and provider throttling profiles. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 14 | PTBC-032; PTBC-034; PTBC-038; PTBC-043 | PTBC-032 Before integration build/SIT; PTBC-034 Before notification SIT; PTBC-038 Before SIT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-009 |  | 14 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-14 | FG-05 | Dead-Letter creation, escalation, resolution and any permissible cancellation/discard rules. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 15 | PTBC-038 | PTBC-038 Before SIT | BEFORE BUILD / SIT | BPK-009 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-15 | FG-05 | Reconciliation schedules, comparison methods and tolerances by integration. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 16 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-009 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-16 | FG-05 | Credential/certificate expiration warning lead times. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 17 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-17 | FG-05 | Operational alert recipients, escalation routes and deduplication windows. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 18 | PTBC-046 | PTBC-046 Before operations UAT | BEFORE UAT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-18 | FG-05 | Maintenance-window authorization, publication and suppression policy. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 19 | PTBC-046 | PTBC-046 Before operations UAT | BEFORE UAT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-19 | FG-05 | Who receives Integration Operator permissions/assignments and by what authority. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 20 | PTBC-046 | PTBC-046 Before operations UAT | BEFORE UAT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-20 | FG-05 | Production retry/reprocess/rerun authority and any step-up/dual-control requirement. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 21 | PTBC-010; PTBC-038; PTBC-046 | PTBC-010 Before admin UAT; PTBC-038 Before SIT; PTBC-046 Before operations UAT | BEFORE BUILD / SIT | BPK-009 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-21 | FG-05 | Who may view sensitive diagnostic/payload excerpts and for which integrations/environments. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 22 | PTBC-028 | PTBC-028 Before security UAT | BEFORE UAT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-22 | FG-05 | Operational log, payload-metadata and detailed-diagnostic retention periods. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 23 | PTBC-028; PTBC-047 | PTBC-028 Before security UAT; PTBC-047 Before production | BEFORE UAT | BPK-009 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-23 | FG-05 | Integration-health snapshot, alert and reconciliation retention periods. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 24 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-009 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-24 | FG-05 | SIEM platform, event categories, transport and correlation requirements. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 25 | PTBC-029 | PTBC-029 Before production | BEFORE PRODUCTION | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-25 | FG-05 | Observability/APM/log platform and exact telemetry interfaces. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 26 | PTBC-044 | PTBC-044 Before production | BEFORE PRODUCTION | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-26 | FG-05 | Operational SLA/SLO expectations for integration availability, support and recovery. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 27 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-27 | FG-05 | Exact business-safe high-level FG-01 Integration Health/Freshness projection. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 28 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-009 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-28 | FG-05 | FG-02 Integration Health report catalogue and operational-export permissions/classifications. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 29 | PTBC-022; PTBC-032 | PTBC-022 Before report UAT; PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-29 | FG-05 | Final FG-06 audit retention/search/export handoff for FG-05 events. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 30 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-009 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-30 | FG-05 | Whether an external ITSM platform is integrated and the incident-creation/update scope. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 31 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-31 | FG-05 | Environment/deployment topology and which non-production environments are exposed to platform operations. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 32 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-32 | FG-05 | Whether internal Operational Notes are included in MVP and their edit/correction policy. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 33 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-009 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-INT-33 | FG-05 | Approved business-safe user-facing status language for source unavailable, stale and delivery pending conditions. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 34 | PTBC-039 | PTBC-039 Before UAT | BEFORE UAT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-INT-34 | FG-05 | Formal operational data export restrictions, classification/watermarking and recipient rules. Configuration / AHDA Governance / Technical TBC | FG-05_Integration_Monitoring_Functional_Specification_v1.0_QA_Closed.docx :: 29. Controlled TBC Register :: table 44, row 35 | PTBC-026; PTBC-030; PTBC-046 | PTBC-026 Before production security sign-off; PTBC-030 Before production; PTBC-046 Before operations UAT | BEFORE UAT | BPK-009 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-AUD-01 | FG-06 | Final auditable-action catalogue Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 2 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-02 | FG-06 | Final Audit category catalogue Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 3 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-03 | FG-06 | Mandatory fail-closed audit action classes Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 4 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-04 | FG-06 | Read/view audit policy Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 5 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-05 | FG-06 | Sensitive Audit access roles/assignments Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 6 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-06 | FG-06 | Audit Reviewer authority model Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 7 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-07 | FG-06 | Security Audit access model Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 8 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-08 | FG-06 | Request/session context fields captured Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 9 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-008 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-09 | FG-06 | IP/device metadata collection and retention policy Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 10 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-008 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-10 | FG-06 | Before/after value capture policy Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 11 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-11 | FG-06 | Personal-data redaction/masking rules Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 12 | PTBC-026; PTBC-028 | PTBC-026 Before production security sign-off; PTBC-028 Before security UAT | BEFORE UAT | BPK-008 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-AUD-12 | FG-06 | Financial Audit sensitivity and value-display policy Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 13 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-008 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-AUD-13 | FG-06 | Document access/download auditing policy Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 14 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-14 | FG-06 | External Entity Activity/Audit visibility detail Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 15 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-15 | FG-06 | Audit retention periods by class Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 16 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-008 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-16 | FG-06 | Activity/index retention periods Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 17 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-008 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-17 | FG-06 | Archive policy and tiers Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 18 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-18 | FG-06 | Legal/investigation/cyber hold authority Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 19 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-19 | FG-06 | Audit disposal authority and approval/SoD Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 20 | PTBC-011; PTBC-047 | PTBC-011 Before audit/records UAT; PTBC-047 Before production | BEFORE UAT | BPK-008 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-20 | FG-06 | Tamper-evidence implementation technology Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 21 | PTBC-045 | PTBC-045 Before production | BEFORE PRODUCTION | BPK-008 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-AUD-21 | FG-06 | Integrity-check frequency/sampling policy Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 22 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-22 | FG-06 | SIEM forwarding event catalogue Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 23 | PTBC-029 | PTBC-029 Before production | BEFORE PRODUCTION | BPK-008 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-23 | FG-06 | SIEM integration details Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 24 | PTBC-029 | PTBC-029 Before production | BEFORE PRODUCTION | BPK-008 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-24 | FG-06 | Audit export policy/catalogue Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 25 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-25 | FG-06 | Audit export watermark/classification rules Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 26 | PTBC-030 | PTBC-030 Before production | BEFORE PRODUCTION | BPK-008 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-AUD-26 | FG-06 | Archived Audit retrieval SLA Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 27 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-008 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-27 | FG-06 | Audit search performance targets Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 28 | PTBC-043 | PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-008 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-28 | FG-06 | Backup/DR RPO/RTO Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 29 | PTBC-048 | PTBC-048 Before production | BEFORE PRODUCTION | BPK-008 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-29 | FG-06 | Data residency/hosting architecture Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 30 | PTBC-048 | PTBC-048 Before production | BEFORE PRODUCTION | BPK-008 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-AUD-30 | FG-06 | Historical label/display policy Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 31 | PTBC-039 | PTBC-039 Before UAT | BEFORE UAT | BPK-008 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-AUD-31 | FG-06 | Final ADM-052 / ADM-053 ownership and navigation reconciliation Configuration/TBC Does not block functional architecture; confirm during governance/technical design and Platform Integration Review. | Project_Management_Platform_FG-06_Audit_Activity_Functional_Specification_v1.0.docx :: 27. Controlled TBC Register :: table 32, row 32 | PTBC-011 | PTBC-011 Before audit/records UAT | BEFORE UAT | BPK-008 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-01 | WF-01 | Can Liaison Officers originate new projects or only contribute to assigned requests? Default to contribution only; keep Create/Submit configurable. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 2 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-014 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-02 | WF-01 | Can External Entity Users originate projects or only update existing/assigned projects? Default to no creation; retain entity-scoped capability behind permission. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 3 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-014 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-PCR-03 | WF-01 | Exact Department / Portfolio / Executive approval authorities and rejection rights. Use configurable workflow steps and permissions. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 4 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-014 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-04 | WF-01 | Budget/priority/classification thresholds that trigger Executive approval. Use configurable decision rules; do not hard-code values. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 5 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-014 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-05 | WF-01 | Approval SLA duration and working calendar for each level. Configurable SLA/calendar; no fixed code constant. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 6 | PTBC-014; PTBC-020 | PTBC-014 Before SLA/schedule UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-014 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-06 | WF-01 | Reminder, first escalation and second escalation timing/hierarchy. Configurable escalation policy. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 7 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-014 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-07 | WF-01 | Whether delegation preserves remaining SLA or restarts the clock. Configurable per workflow. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 8 | PTBC-001; PTBC-020 | PTBC-001 Before UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-014 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-08 | WF-01 | Whether Returned for Correction has its own correction SLA. Support optional correction SLA. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 9 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-014 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-09 | WF-01 | Mandatory documents by project type/classification. Configuration-driven document requirements. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 10 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-014 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-10 | WF-01 | Mandatory KPI count/types and target rules at creation. Configuration-driven; validate only when rule exists. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 11 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-014 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-11 | WF-01 | Whether Project Description and Project Objective are formally mandatory. Recommended mandatory in baseline; configurable pending confirmation. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 12 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-014 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-12 | WF-01 | Funding Source and detailed financial field model. Keep optional/TBC until finance model confirmed. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 13 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-014 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-13 | WF-01 | Strategic Alignment hierarchy/source system. Keep conditional lookup until strategy structure is confirmed. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 14 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-014 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-14 | WF-01 | Exact Draft / Request / Project numbering format. Backend-generated configurable prefix/sequence. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 15 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-014 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-15 | WF-01 | Whether SMS will be enabled and for which events. Keep optional; default in-app + email. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 16 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-014 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PCR-16 | WF-01 | Which final-approval stakeholders receive project-registration notifications. Recipient rules configurable. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 17 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-014 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-020 | BEFORE UAT | Registration notification recipients are notification configuration (PTBC-020)
TBC-PCR-17 | WF-01 | Exact GCP architecture/services/region for implementation. Treat GCP mapping as architecture decision subject to AHDA IT/cyber approval. | Project_Management_Platform_WF-01_Project_Creation_Registration_Functional_Specification_v1.0.docx :: 13. Open Decisions / TBC Register :: table 52, row 18 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-014 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-048 | BEFORE BUILD / SIT | GCP architecture/services/region is the hosting decision (PTBC-048, ADR-001, OQ-001); must resolve before environment provisioning, not "configurable"
TBC-PRG-001 | WF-02 | Reporting frequency / cadence AHDA governance Before production cycle configuration | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 2 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-002 | WF-02 | Reporting cut-off, business timezone and working-calendar convention Platform governance / IT Before formal snapshot/UAT | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 3 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-022 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-PRG-003 | WF-02 | PM submission SLA AHDA governance Before production | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 4 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-022 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-004 | WF-02 | Reviewer SLA AHDA governance Before production | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 5 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-022 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-005 | WF-02 | Returned-correction SLA AHDA governance Before production if enabled | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 6 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-022 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-006 | WF-02 | Department Manager as mandatory reviewer AHDA governance Before production workflow publication | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 7 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-007 | WF-02 | Portfolio review on every update vs exception-based AHDA governance Before Portfolio approval feature activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 8 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-008 | WF-02 | Executive routine approval involvement AHDA governance Before any Executive approval stage | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 9 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-022 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-009 | WF-02 | Physical-progress calculation formula WF-03 / WF-04 design Before official calculated-progress acceptance | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 10 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-010 | WF-02 | Activity/task weighting methodology WF-03 / WF-04 design Before official calculated-progress acceptance | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 11 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-011 | WF-02 | Manual / Hybrid progress eligibility AHDA governance Before feature activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 12 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-012 | WF-02 | Progress override authority/tolerance AHDA governance Before override feature activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 13 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-022 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-013 | WF-02 | Overall-health composite formula and thresholds Cross-platform health design Before formal health acceptance | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 14 | PTBC-023; PTBC-037 | PTBC-023 Before executive UAT; PTBC-037 Before operations UAT | BEFORE UAT | BPK-022 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-014 | WF-02 | Health-override authority AHDA governance Before override feature activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 15 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-015 | WF-02 | Mandatory narrative fields AHDA governance Before UAT configuration freeze | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 16 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-016 | WF-02 | Mandatory supporting evidence rules AHDA governance Before UAT configuration freeze | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 17 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-022 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-017 | WF-02 | Source-freshness thresholds by module AHDA/source owners Before UAT / production | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 18 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-022 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-018 | WF-02 | Suspended-project reporting policy WF-10 / AHDA governance Before Suspended projects go live | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 19 | PTBC-023 | PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-019 | WF-02 | Open-cycle treatment when project completes/closes WF-11 / AHDA governance Before closure integration | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 20 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-022 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-PRG-020 | WF-02 | Published correction authority/process AHDA governance Before correction feature activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 21 | PTBC-010 | PTBC-010 Before admin UAT | BEFORE UAT | BPK-022 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-PRG-021 | WF-02 | Financial-progress formula WF-15 Before formal financial progress acceptance | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 22 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-022 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-022 | WF-02 | KPI achievement/health formula WF-15 Before formal KPI acceptance | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 23 | PTBC-023; PTBC-024 | PTBC-023 Before executive UAT; PTBC-024 Before KPI UAT | BEFORE UAT | BPK-022 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-023 | WF-02 | Risk-health formula/contribution WF-07 / cross-platform health Before formal risk-health acceptance | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 24 | PTBC-007; PTBC-023 | PTBC-007 Before risk UAT; PTBC-023 Before executive UAT | BEFORE UAT | BPK-022 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-024 | WF-02 | SMS channel use and critical recipients AHDA governance / IT Before SMS activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 25 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-022 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-PRG-025 | WF-02 | Separate Arabic/English narrative fields vs single entered-language narrative AHDA UX/business governance Before bilingual content-entry feature activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 26 | PTBC-039 | PTBC-039 Before UAT | BEFORE UAT | BPK-022 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-PRG-026 | WF-02 | Ad-hoc update approval/SLA/publication rules AHDA governance Before ad-hoc feature activation | Project_Management_Platform_WF-02_Project_Progress_Update_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 102, row 27 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-022 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-001 | WF-03 | Actual Project Calendar working weekdays/holidays Configuration before UAT Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 2 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-015 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SCH-002 | WF-03 | Scope of Activity calendar override Configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 3 | PTBC-014; PTBC-015 | PTBC-014 Before SLA/schedule UAT; PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-003 | WF-03 | Schedule Health warning/critical thresholds Configuration before performance UAT Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 4 | PTBC-015; PTBC-037; PTBC-043 | PTBC-015 Before schedule UAT; PTBC-037 Before operations UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-015 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-004 | WF-03 | Initial baseline preparation SLA Configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 5 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-005 | WF-03 | Baseline reviewer SLA Configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 6 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-006 | WF-03 | Returned-correction SLA Configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 7 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-007 | WF-03 | Portfolio review trigger rules Governance configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 8 | PTBC-015 | PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-008 | WF-03 | Executive review requirement, if any Governance configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 9 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-015 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SCH-009 | WF-03 | Whether initial Active Baseline is mandatory before Project Activation Validate during Activation design Cross-workflow | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 10 | PTBC-015 | PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-010 | WF-03 | WF-04 actual-progress aggregation formula Resolve in WF-04 Cross-workflow | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 11 | PTBC-015 | PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-011 | WF-03 | WF-05 milestone achievement/acceptance process Resolve in WF-05 Cross-workflow | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 12 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-015 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SCH-012 | WF-03 | Additional non-material schedule changes that may bypass WF-08 Resolve in WF-08; MVP remains conservative Cross-workflow | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 13 | PTBC-015 | PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-013 | WF-03 | Critical-milestone materiality thresholds WF-08 governance/configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 14 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-015 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SCH-014 | WF-03 | Suspended-project exception permissions Resolve in WF-09 Cross-workflow | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 15 | PTBC-015 | PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-015 | WF-03 | Final schedule/actual completion reconciliation Resolve in WF-10 Cross-workflow | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 16 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-015 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-016 | WF-03 | SMS use for WF-03 alerts Shared notification configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 17 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-015 |  | 28 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-017 | WF-03 | Exact maximum supported hierarchy depth Technical capacity/configuration Non-blocking | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 18 | PTBC-015 | PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SCH-018 | WF-03 | Advanced Critical Path / float requirement Enhancement decision Deferred | Project_Management_Platform_WF-03_Schedule_Baseline_Management_Functional_Specification_v1.0.docx :: 14. Open Decisions / TBC Register :: table 86, row 19 | PTBC-015 | PTBC-015 Before schedule UAT | BEFORE UAT | BPK-015 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-001 | WF-04 | Task due-soon reminder lead time. Configuration before UAT | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 2 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-016 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-002 | WF-04 | Overdue escalation intervals and recipient levels. Governance configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 3 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-003 | WF-04 | Prolonged Blocked reminder/escalation threshold. Governance configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 4 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-016 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-004 | WF-04 | Exact Task priority/category master-data values. Master-data configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 5 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-005 | WF-04 | Task categories that require completion evidence. Governance configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 6 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-016 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-006 | WF-04 | Allowed evidence attachment file types/sizes and retention specifics. Shared Documents/Cyber configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 7 | PTBC-019; PTBC-047 | PTBC-019 Before workflow UAT; PTBC-047 Before production | BEFORE UAT | BPK-016 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-TSK-007 | WF-04 | Default DM/PFM Task create/edit/reassignment rights. Governance/RBAC configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 8 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-008 | WF-04 | Which Project types/entities may use External Task contribution. Governance configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 9 | PTBC-013 | PTBC-013 Before UAT data load | BEFORE UAT | BPK-016 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-TSK-009 | WF-04 | Task/Activity execution progress display precision. Configuration/technical standard | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 10 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-010 | WF-04 | Days Overdue basis: working days or calendar days. Governance/calendar configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 11 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-016 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-TSK-011 | WF-04 | Detailed WF-05 milestone-to-Task generation/link behavior. Resolve in WF-05 | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 12 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-012 | WF-04 | Detailed WF-06 risk-treatment-to-Task behavior. Resolve in WF-06 | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 13 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-013 | WF-04 | Detailed WF-07 issue/challenge-action-to-Task behavior. Resolve in WF-07 | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 14 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-014 | WF-04 | Detailed WF-08 material Task-change tolerance beyond obvious formal commitments. Resolve in WF-08 | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 15 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-016 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-TSK-015 | WF-04 | Permitted Task execution exceptions while Project is Suspended. Resolve in WF-09 | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 16 | PTBC-016 | PTBC-016 Before task UAT | BEFORE UAT | BPK-016 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-016 | WF-04 | Final Task reconciliation requirements during Project Completion/Closure. Resolve in WF-10 | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 17 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-016 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-017 | WF-04 | SMS channel enablement. Shared notification configuration | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 18 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-016 |  | 17 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-TSK-018 | WF-04 | Task cloning/templates/recurrence release priority. Enhancement decision | Project_Management_Platform_WF-04_Task_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 80, row 19 | PTBC-016; PTBC-020 | PTBC-016 Before task UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-016 |  | 11 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-001 | WF-05 | Which milestone types/criticalities require which evidence categories. Configuration before UAT | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 2 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-017 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-002 | WF-05 | Exact standard achievement-review routing by Project/milestone class. Governance configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 3 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-017 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-003 | WF-05 | Whether Rejection is enabled in addition to Return. Governance configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 4 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-017 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-004 | WF-05 | Whether submitter may Withdraw after review has started. Governance configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 5 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-017 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-005 | WF-05 | Due Soon reminder window(s). Configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 6 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-017 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-006 | WF-05 | Operational overdue escalation timings/recipients. Configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 7 | PTBC-020; PTBC-046 | PTBC-020 Before notification UAT; PTBC-046 Before operations UAT | BEFORE UAT | BPK-017 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-007 | WF-05 | Achievement-review SLA and escalation timing. Configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 8 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-017 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-008 | WF-05 | Exact business-day versus calendar-day convention for “days to/from target” display. Configuration/technical standard | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 9 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-017 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-MIL-009 | WF-05 | External Entity contribution enablement and permitted evidence/comment fields. Governance configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 10 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-017 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-010 | WF-05 | Executive critical-milestone alert policy. Governance configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 11 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-017 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-011 | WF-05 | Detailed milestone materiality thresholds requiring WF-08. Resolve in WF-08 | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 12 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-017 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-MIL-012 | WF-05 | Risk-to-milestone linkage and risk-driven follow-up automation. Resolve in WF-06 | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 13 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-017 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-013 | WF-05 | Issue/Challenge-to-milestone blocker linkage. Resolve in WF-07 | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 14 | PTBC-006 | PTBC-006 Before milestone UAT | BEFORE UAT | BPK-017 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-014 | WF-05 | Milestone behavior/reminder pause during Suspension. Resolve in WF-09 | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 15 | PTBC-005; PTBC-020 | PTBC-005 Before suspension UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-017 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-MIL-015 | WF-05 | Required milestone reconciliation at Completion/Closure. Resolve in WF-10 | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 16 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-017 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-MIL-016 | WF-05 | SMS channel enablement. Shared notification configuration | Project_Management_Platform_WF-05_Milestone_Management_Functional_Specification_v1.0.docx :: 16.3 Remaining TBCs :: table 70, row 17 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-017 |  | 14 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-001 | WF-06 | Exact Probability level labels/descriptions and quantitative thresholds Configuration before Risk UAT | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 2 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-002 | WF-06 | Exact Impact dimensions used by AHDA projects Configuration before Risk UAT | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 3 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-003 | WF-06 | Impact level descriptions/quantitative thresholds per dimension Configuration before Risk UAT | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 4 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-004 | WF-06 | Exact 5×5 Risk Matrix cell → Rating mapping Configuration before Risk UAT | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 5 | PTBC-017; PTBC-042 | PTBC-017 Before risk UAT; PTBC-042 Can remain configurable/deferred | BEFORE UAT | BPK-018 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-017 | BEFORE UAT | 5×5 risk matrix cell→rating mapping is already PTBC-017; drop PTBC-042
TBC-RSK-005 | WF-06 | Rating labels/colors and high/critical threshold Configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 6 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-006 | WF-06 | Risk categories and sources Master data configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 7 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-007 | WF-06 | Default/maximum review intervals by rating/category Configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 8 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-008 | WF-06 | Risk review reminder/escalation timing Configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 9 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-009 | WF-06 | Treatment action reminder/escalation timing Configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 10 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-010 | WF-06 | Risk Acceptance authority/routing by exposure/project class Governance configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 11 | PTBC-007 | PTBC-007 Before risk UAT | BEFORE UAT | BPK-018 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-011 | WF-06 | Acceptance expiry/review rules Governance configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 12 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-012 | WF-06 | Escalation routes/thresholds Governance configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 13 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-013 | WF-06 | Evidence requirements for acceptance/closure/materialization Configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 14 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-018 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-014 | WF-06 | External Entity contribution enablement and fields Governance configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 15 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-015 | WF-06 | Exact WF-07 Issue creation fields/status on materialization Validate in WF-07 | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 16 | PTBC-017 | PTBC-017 Before risk UAT | BEFORE UAT | BPK-018 |  | 6 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-016 | WF-06 | Material change tolerances requiring WF-08 Validate in WF-08 | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 17 | PTBC-037 | PTBC-037 Before operations UAT | BEFORE UAT | BPK-018 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RSK-017 | WF-06 | Risk/treatment behavior during Project Suspension Validate in WF-09 | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 18 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-018 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RSK-018 | WF-06 | Open/high/accepted Risk disposition required before Completion/Closure Validate in WF-10 | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 19 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-018 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-RSK-019 | WF-06 | Calendar-day versus business-day treatment for review/treatment due conditions Configuration / platform convention | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 20 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-018 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-RSK-020 | WF-06 | SMS / executive alert channels Shared notification configuration | Project_Management_Platform_WF-06_Risk_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 54, row 21 | PTBC-034; PTBC-041 | PTBC-034 Before notification SIT; PTBC-041 Before executive UAT | BEFORE BUILD / SIT | BPK-018 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-001 | WF-07 | Exact Issue/Challenge category/source master values. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 2 | PTBC-018 | PTBC-018 Before concern UAT | BEFORE UAT | BPK-019 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-002 | WF-07 | Exact enabled impact dimensions and five-level descriptions/quantitative thresholds. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 3 | PTBC-018 | PTBC-018 Before concern UAT | BEFORE UAT | BPK-019 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-003 | WF-07 | Severity labels/colors mapped to impact levels. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 4 | PTBC-018; PTBC-042 | PTBC-018 Before concern UAT; PTBC-042 Can remain configurable/deferred | BEFORE UAT | BPK-019 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001, 004-F-002) | PTBC-008 | BEFORE UAT | Severity labels/colours are PTBC-008 (severity-priority governance) with PTBC-018; not geospatial
TBC-ISS-004 | WF-07 | Priority scale labels and severity-to-minimum/recommended priority rules. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 5 | PTBC-018; PTBC-043 | PTBC-018 Before concern UAT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-019 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001, 004-F-002) | PTBC-008 | BEFORE UAT | Priority scale labels/severity→priority rules are PTBC-008 with PTBC-018; the PTBC-043 link is the word "scale", not performance
TBC-ISS-005 | WF-07 | Due Soon windows and business-day/calendar-day conventions. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 6 | PTBC-014; PTBC-020 | PTBC-014 Before SLA/schedule UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-019 |  | 29 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-006 | WF-07 | Review frequency and target-resolution SLA rules by severity/category/project class. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 7 | PTBC-018; PTBC-020 | PTBC-018 Before concern UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-019 |  | 36 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-007 | WF-07 | Escalation thresholds, levels, acknowledgement SLAs and routing authorities. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 8 | PTBC-011; PTBC-020 | PTBC-011 Before audit/records UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-019 |  | 29 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-008 | WF-07 | Resolution verifier eligibility/authority rules and any higher-level verification triggers. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 9 | PTBC-018 | PTBC-018 Before concern UAT | BEFORE UAT | BPK-019 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-009 | WF-07 | Evidence requirements by type/category/severity and document-retention specifics. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 10 | PTBC-018; PTBC-047 | PTBC-018 Before concern UAT; PTBC-047 Before production | BEFORE UAT | BPK-019 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-010 | WF-07 | External Entity participation, field visibility and permitted mutations. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 11 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-019 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-ISS-011 | WF-07 | Exact Change materiality thresholds and WF-08 implementation-permitting states. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 12 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-019 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-012 | WF-07 | Suspended Project mutation/action/reminder exceptions under WF-09. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 13 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-019 |  | 29 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-013 | WF-07 | Open concern disposition requirements before Completion/Closure under WF-10. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 14 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-019 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-ISS-014 | WF-07 | SMS/other notification channels. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 15 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-019 |  | 28 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-ISS-015 | WF-07 | Maximum allowed linked relations/actions per concern for performance governance. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 16 | PTBC-043 | PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-019 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-ISS-016 | WF-07 | Whether selected low-governance Challenge categories may later waive independent verification; MVP requires verification for all registered records. | Project_Management_Platform_WF-07_Issue_Challenge_Management_Functional_Specification_v1.0.docx :: 16.3 TBC / configuration register :: table 52, row 17 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-019 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001, 004-F-002) | PTBC-008 | BEFORE UAT | Waiving independent verification for low-governance categories is WF-07 governance (PTBC-008)
TBC-CHG-001 | WF-08 | Exact AHDA materiality thresholds/rule mappings. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 2 | PTBC-009; PTBC-042 | PTBC-009 Before change UAT; PTBC-042 Can remain configurable/deferred | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-009 | BEFORE UAT | Materiality thresholds are already PTBC-009; drop PTBC-042
TBC-CHG-002 | WF-08 | Approval authority matrix/limits by type/materiality/Project classification. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 3 | PTBC-001; PTBC-009 | PTBC-001 Before UAT; PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 47 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-003 | WF-08 | Financial monetary thresholds and currency aggregation policy. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 4 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-020 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-004 | WF-08 | Approval SLA/reminder/escalation timings. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 5 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-020 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-005 | WF-08 | Returned-correction SLA/policy. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 6 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-020 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-006 | WF-08 | Implementation target/SLA defaults. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 7 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-020 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-007 | WF-08 | Evidence/document requirements by type/materiality. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 8 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-008 | WF-08 | Final active Change Type taxonomy/reason codes. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 9 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-009 | WF-08 | Final Controlled Commitment catalogue/source mappings. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 10 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-020 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-009 | BEFORE UAT | Controlled Commitment catalogue is change-control governance (PTBC-009)
TBC-CHG-010 | WF-08 | AUTO_GOVERNED enablement/rule classes. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 11 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-011 | WF-08 | Authorization expiry policy. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 12 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-012 | WF-08 | Parallel approval/quorum rules if needed. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 13 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-020 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-013 | WF-08 | External Entity participation permissions. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 14 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-020 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CHG-014 | WF-08 | Executive approval triggers. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 15 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-020 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CHG-015 | WF-08 | Sensitive field access for financial/contract/compliance impacts. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 16 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-020 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-016 | WF-08 | Implementation exception/cancellation authority. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 17 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-017 | WF-08 | Suspended-Project Change exceptions (WF-09). | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 18 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-018 | WF-08 | Completion/Closure gate for open Changes (WF-10). | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 19 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-020 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CHG-019 | WF-08 | Financial/KPI APIs/record IDs (WF-14). | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 20 | PTBC-024; PTBC-025 | PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT | BEFORE UAT | BPK-020 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-020 | WF-08 | SMS/channel policy. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 21 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-020 |  | 45 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-021 | WF-08 | Draft physical deletion/retention policy. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 22 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-020 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CHG-022 | WF-08 | Cumulative schedule/budget metric definitions. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 23 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-023 | WF-08 | Contract/procurement integration specifics. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 24 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CHG-024 | WF-08 | Whether formal CR Number is allocated at first submit or Draft creation; first submit recommended. | Project_Management_Platform_WF-08_Project_Change_Request_Functional_Specification_v1.0.docx :: 22.1 Configuration / TBC register :: table 50, row 25 | PTBC-009 | PTBC-009 Before change UAT | BEFORE UAT | BPK-020 |  | 46 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-001 | WF-09 | Exact Suspension categories and reason master data. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 2 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-002 | WF-09 | Suspension and Resumption approval authority/routing matrix. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 3 | PTBC-001; PTBC-005 | PTBC-001 Before UAT; PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 57 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-003 | WF-09 | Self-approval restrictions beyond platform default separation-of-duties. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 4 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-024 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-004 | WF-09 | Submission/review/approval SLA durations. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 5 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-024 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-005 | WF-09 | Suspension Review cadence. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 6 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-006 | WF-09 | Prolonged Suspension thresholds and recipients. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 7 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-007 | WF-09 | Evidence/document requirements by category. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 8 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-024 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SUS-008 | WF-09 | Maximum future effective-date lead time / cancellation policy before activation. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 9 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-009 | WF-09 | Exact Task capability exception authority and policy. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 10 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-010 | WF-09 | Task/Milestone reminder suppression/modification rules. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 11 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-024 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-011 | WF-09 | READY_WITH_CONDITIONS criteria and authority. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 12 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-012 | WF-09 | External Entity contribution permissions. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 13 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-024 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SUS-013 | WF-09 | Executive approval triggers, if any. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 14 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-024 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SUS-014 | WF-09 | WF-08 implementation exception authority during Suspension. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 15 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-015 | WF-09 | WF-10 disposition of permanent/prolonged Suspensions and pending requests. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 16 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-016 | WF-09 | Financial/KPI source behavior and readiness criteria. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 17 | PTBC-024; PTBC-025; PTBC-033 | PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT | BEFORE BUILD / SIT | BPK-024 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-SUS-017 | WF-09 | Notification channels including SMS. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 18 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-024 |  | 49 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-018 | WF-09 | Calendar/business-day basis for configurable governance SLAs. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 19 | PTBC-014; PTBC-020 | PTBC-014 Before SLA/schedule UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-024 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-019 | WF-09 | Whether expected Resumption date is informational or governed target for specific categories. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 20 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-SUS-020 | WF-09 | Exact criteria/policy versions for Resumption readiness. | Project_Management_Platform_WF-09_Project_Suspension_Resumption_Functional_Specification_v1.0.docx :: 24.3 TBC register :: table 42, row 21 | PTBC-005 | PTBC-005 Before suspension UAT | BEFORE UAT | BPK-024 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-001 | WF-10 | Completion approval authority/routing matrix. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 2 | PTBC-001; PTBC-004 | PTBC-001 Before UAT; PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 65 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-002 | WF-10 | Closure approval authority/routing matrix. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 3 | PTBC-001; PTBC-004 | PTBC-001 Before UAT; PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 65 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-003 | WF-10 | Completion/Closure review and approval SLA durations. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 4 | PTBC-004; PTBC-020 | PTBC-004 Before closeout UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-025 |  | 66 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-004 | WF-10 | Exact readiness criteria by Project classification. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 5 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-005 | WF-10 | READY_WITH_CONDITIONS accepting authority and limits. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 6 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-006 | WF-10 | Mandatory deliverable acceptance/evidence rules. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 7 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-025 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CLO-007 | WF-10 | Official Completion date backdating policy/limits. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 8 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-008 | WF-10 | Residual Risk acceptance/transfer authorities and thresholds. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 9 | PTBC-007 | PTBC-007 Before risk UAT | BEFORE UAT | BPK-025 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CLO-009 | WF-10 | Residual Issue/Challenge acceptance/transfer authorities. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 10 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-010 | WF-10 | Which Task states/dispositions block Completion by Project type. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 11 | PTBC-004; PTBC-013 | PTBC-004 Before closeout UAT; PTBC-013 Before UAT data load | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-011 | WF-10 | Critical Milestone exception authority. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 12 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-012 | WF-10 | Change Request states that block Completion vs Closure by Change type. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 13 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-013 | WF-10 | Financial closeout thresholds and authoritative source API. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 14 | PTBC-004; PTBC-011; PTBC-025; PTBC-033 | PTBC-004 Before closeout UAT; PTBC-011 Before audit/records UAT; PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT | BEFORE BUILD / SIT | BPK-025 |  | 65 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-014 | WF-10 | KPI/benefit finalization and post-Project owner requirements. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 15 | PTBC-004; PTBC-024 | PTBC-004 Before closeout UAT; PTBC-024 Before KPI UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-015 | WF-10 | Contract/procurement closeout projection/source. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 16 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-016 | WF-10 | Lessons learned mandatory policy by Project classification. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 17 | PTBC-004; PTBC-036 | PTBC-004 Before closeout UAT; PTBC-036 Before IAM SIT | BEFORE BUILD / SIT | BPK-025 |  | 65 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-017 | WF-10 | Final Project Summary template/required fields. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 18 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-018 | WF-10 | Final document/Closure pack checklist by Project type. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 19 | PTBC-004; PTBC-013 | PTBC-004 Before closeout UAT; PTBC-013 Before UAT data load | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-019 | WF-10 | Records retention/archive classification rules. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 20 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-025 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CLO-020 | WF-10 | External Entity closeout contribution permissions. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 21 | PTBC-003; PTBC-004 | PTBC-003 Before External UAT; PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-021 | WF-10 | Executive approval triggers, if any. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 22 | PTBC-041 | PTBC-041 Before executive UAT | BEFORE UAT | BPK-025 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CLO-022 | WF-10 | Terminal Suspended Closure authority and evidence requirements. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 23 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-025 |  | 64 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-023 | WF-10 | PostProjectObligation follow-up system/integration ownership. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 24 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-025 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-CLO-024 | WF-10 | Notification channels including SMS. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 25 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-025 |  | 56 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-CLO-025 | WF-10 | Calendar/business-day basis for configurable governance SLAs. | Project_Management_Platform_WF-10_Project_Completion_Closure_Functional_Specification_v1.0.docx :: 25.3 TBC register :: table 42, row 26 | PTBC-014; PTBC-020 | PTBC-014 Before SLA/schedule UAT; PTBC-020 Before notification UAT | BEFORE UAT | BPK-025 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-001 | WF-11 | Exact AHDA approval authority matrix by domain/action/project classification. Configuration/TBC FG-04 / Governance | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 2 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-002 | WF-11 | Monetary/materiality/schedule/criticality thresholds used by authority rules. Configuration/TBC FG-04 / WF-08 / Financial | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 3 | PTBC-009; PTBC-011; PTBC-025; PTBC-026 | PTBC-009 Before change UAT; PTBC-011 Before audit/records UAT; PTBC-025 Before financial UAT; PTBC-026 Before production security sign-off | BEFORE UAT | BPK-011 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-APR-003 | WF-11 | Approval SLA durations and Due Soon windows. Configuration/TBC FG-04 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 4 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-011 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-APR-004 | WF-11 | Working-day versus calendar-day policy and holiday calendar source. Configuration/TBC FG-04 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 5 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-011 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-APR-005 | WF-11 | Escalation levels, recipients and timings by approval action. Configuration/TBC FG-04 / Governance | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 6 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-011 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-APR-006 | WF-11 | Standing/time-bound out-of-office delegation enablement and approval. Deferred/Conditional FG-03 / FG-04 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 7 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-007 | WF-11 | Whether delegates may redelegate in any domain. Configuration/TBC Governance | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 8 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-008 | WF-11 | Parallel quorum policies beyond ANY_ONE and ALL_REQUIRED. Deferred/Enhancement Governance | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 9 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-009 | WF-11 | Exact business actions requiring step-up authentication/MFA. Configuration/TBC Cybersecurity / FG-04 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 10 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-011 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-010 | WF-11 | External Entity approval actions and eligible authority relationships. Configuration/TBC WF-13 / FG-03 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 11 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-011 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-APR-011 | WF-11 | Whether selected workflows permit resume-from-returning-step rather than full route restart. Deferred/Conditional Governance / FG-04 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 12 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-012 | WF-11 | Approval reason/evidence requirements by decision/action. Configuration/TBC Source workflow / FG-04 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 13 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-013 | WF-11 | Approver unavailability/calendar integration policy. Configuration/TBC FG-03 / Integration | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 14 | PTBC-001; PTBC-014 | PTBC-001 Before UAT; PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-014 | WF-11 | Privacy policy for approver workload analytics. Configuration/TBC Governance / Privacy | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 15 | PTBC-001; PTBC-026 | PTBC-001 Before UAT; PTBC-026 Before production security sign-off | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-015 | WF-11 | Exact runtime cancellation authority/support roles. Configuration/TBC FG-03 / Governance | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 16 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-016 | WF-11 | Approval-definition migration policy for exceptional in-flight governance change. Configuration/TBC FG-04 / Governance | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 17 | PTBC-001 | PTBC-001 Before UAT | BEFORE UAT | BPK-011 |  | 10 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-017 | WF-11 | Notification channels/templates for approval mechanics. Configuration/TBC WF-15 | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 18 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-011 |  | 3 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-APR-018 | WF-11 | Callback retry limits and operational escalation thresholds. Technical Configuration FG-05 / Operations | Project_Management_Platform_WF-11_Shared_Approval_Framework_Functional_Specification_v1.0.docx :: 26. Configuration / TBC Register :: table 46, row 19 | PTBC-038 | PTBC-038 Before SIT | BEFORE BUILD / SIT | BPK-011 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DOC-001 | WF-12 | Final permitted file extension/MIME allowlist and prohibited formats. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 2 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-002 | WF-12 | Maximum file size by file/document category and any large-file handling policy. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 3 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-003 | WF-12 | Malware scanning technology, retry policy, quarantine retention and security operating procedure. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 4 | PTBC-035; PTBC-038; PTBC-047 | PTBC-035 Before document SIT; PTBC-038 Before SIT; PTBC-047 Before production | BEFORE BUILD / SIT | BPK-010 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-004 | WF-12 | Final Document Category/Type catalogue. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 5 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-005 | WF-12 | AHDA Document classification/sensitivity scheme and additional-permission rules. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 6 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-006 | WF-12 | Exact External Entity upload/download/version-history permissions by document/source type. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 7 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-010 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-007 | WF-12 | Retention classifications, periods, triggers and disposal authorities. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 8 | PTBC-011; PTBC-047 | PTBC-011 Before audit/records UAT; PTBC-047 Before production | BEFORE UAT | BPK-010 |  | 5 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-008 | WF-12 | Records/legal hold governance and authorized custodian roles. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 9 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-010 |  | 4 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-009 | WF-12 | Records-management exceptions allowed after Project Closed. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 10 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-010 | WF-12 | Exact evidence categories and any approved minimum evidence counts by workflow/action. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 11 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-011 | WF-12 | Classification downgrade authority and whether WF-11 approval is required. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 12 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-012 | WF-12 | Step-up authentication requirements for sensitive documents/download/export. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 13 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-010 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DOC-013 | WF-12 | Whether full-text content search is enabled in MVP and which classifications are indexable. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 14 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-014 | WF-12 | Whether OCR is required for scanned/image documents. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 15 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-015 | WF-12 | Digital-signature/cryptographic signature requirements and provider, if any. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 16 | PTBC-032 | PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-010 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DOC-016 | WF-12 | Which generated documents are retained as managed records and template-version governance. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 17 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-017 | WF-12 | Bulk upload/download feature limits and sensitive bulk-extraction controls. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 18 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-018 | WF-12 | Legacy document migration scope, source systems, mappings and migration tooling. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 19 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-010 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | (none — OQ-008) | BEFORE PRODUCTION | Legacy document migration scope has no PTBC theme; tracked by OQ-008 / TASK-089 / TASK-102 (finding 004-F-003)
TBC-DOC-019 | WF-12 | Export package format for Closure/records requests. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 20 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-010 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DOC-020 | WF-12 | Download/view audit-event threshold by classification/action. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 21 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-021 | WF-12 | Exact Document Owner reassignment authority and custodian model. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 22 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-022 | WF-12 | Whether exceptional explicit DocumentAccessGrant is enabled beyond inherited access. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 23 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-023 | WF-12 | Document/reference numbering policy, if business-visible numbering is required. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 24 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-024 | WF-12 | Document expiry semantics/categories, if any. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 25 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-025 | WF-12 | Supported preview formats/viewer technology and redaction/watermarking requirements if later needed. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 26 | PTBC-028; PTBC-030 | PTBC-028 Before security UAT; PTBC-030 Before production | BEFORE UAT | BPK-010 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-DOC-026 | WF-12 | Exact storage technology, cloud region/location and lifecycle settings in technical design. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 27 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-027 | WF-12 | Backup/restore RTO/RPO/retention and integrity-verification schedule. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 28 | PTBC-047; PTBC-048 | PTBC-047 Before production; PTBC-048 Before production | BEFORE PRODUCTION | BPK-010 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-028 | WF-12 | Technical service-level targets for upload/scan/index/search/download. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 29 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-029 | WF-12 | Whether multi-file upload is core MVP or Conditional for first release. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 30 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-010 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-DOC-030 | WF-12 | Whether content deduplication is technical storage optimization and under what privacy/security constraints. Configuration/TBC | Project_Management_Platform_WF-12_Document_Management_Functional_Specification_v1.0.docx :: 24. Configuration/TBC Register and Cross-Feature Assumptions :: table 41, row 31 | PTBC-026 | PTBC-026 Before production security sign-off | BEFORE PRODUCTION | BPK-010 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-001 | WF-13 | External participation coverage Whether enabled for all or selected Projects/classifications. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 2 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-002 | WF-13 | Eligible Entity types Which External Entity categories may participate. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 3 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-003 | WF-13 | Onboarding/invitation authority Exact AHDA authority to request/approve External identity and Project access. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 4 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-004 | WF-13 | External authentication / identity proofing Exact provider/method including Nafath applicability. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 5 | PTBC-027; PTBC-031; PTBC-032 | PTBC-027 Before production; PTBC-031 Before External integration UAT; PTBC-032 Before integration build/SIT | BEFORE BUILD / SIT | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-005 | WF-13 | MFA / step-up Which External actions require additional authentication. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 6 | PTBC-027 | PTBC-027 Before production | BEFORE PRODUCTION | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-006 | WF-13 | Project access assignment authority Exact business/security authority to grant Entity/Project access. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 7 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-007 | WF-13 | Default access duration Effective period and expiry defaults. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 8 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-008 | WF-13 | Access review frequency How often External participation must be recertified. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 9 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-009 | WF-13 | Direct source-workflow actions Which workflows/actions may use Path A for R08. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 10 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-010 | WF-13 | Contribution types Final controlled catalogue. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 11 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-011 | WF-13 | Contribution field schemas Exact fields/questions/mappings per domain/type. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 12 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-003 | BEFORE UAT | Contribution field schemas per domain/type are external-participation configuration (PTBC-003)
TBC-EXT-012 | WF-13 | Unsolicited contribution policy Which observation/intake types are permitted without Request. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 13 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-013 | WF-13 | Responsible-user reassignment Exact initiating/authorizing actors and notifications. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 14 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-014 | WF-13 | Response due periods Default/maximum due periods and business-calendar basis. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 15 | PTBC-014 | PTBC-014 Before SLA/schedule UAT | BEFORE UAT | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-015 | WF-13 | Escalation Exact overdue timing, levels and recipients. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 16 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-023 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-016 | WF-13 | Reviewer routing Exact reviewer selection by domain/Project/type. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 17 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-017 | WF-13 | Formal approval triggers Which accepted contributions must proceed to WF-11 through source workflow. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 18 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-018 | WF-13 | Evidence requirements Exact categories/minimum requirements per type. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 19 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-019 | WF-13 | External Document classification Allowed classifications/categories and prior-version visibility. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 20 | PTBC-019 | PTBC-019 Before workflow UAT | BEFORE UAT | BPK-023 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-020 | WF-13 | Sensitive information Exact prohibited/limited fields and external disclosure rules. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 21 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-021 | WF-13 | Access-expiry behavior Whether Drafts may be reassigned/reactivated and under what authority. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 22 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-022 | WF-13 | WF-14 external contribution contract Financial/KPI fields, validations, application modes and source authority. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 23 | PTBC-024; PTBC-025; PTBC-033 | PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT | BEFORE BUILD / SIT | BPK-023 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-023 | WF-13 | Notification channels Email/In-App/SMS applicability for External users. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 24 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-024 | WF-13 | Audit/retention periods Exact retention periods for requests, submissions, notes, access and audit. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 25 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-025 | WF-13 | Export/download restrictions Exact permitted external/internal export and document-download rules. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 26 | PTBC-003 | PTBC-003 Before External UAT | BEFORE UAT | BPK-023 |  | 7 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-EXT-026 | WF-13 | Source-application mappings Final typed adapter/action mapping per contribution type. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 27 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-003 | BEFORE UAT | Source-application adapter mapping per contribution type is WF-13 governance (PTBC-003)
TBC-EXT-027 | WF-13 | Bilingual instructions Whether both Arabic/English content is mandatory for every request/schema. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 28 | PTBC-039 | PTBC-039 Before UAT | BEFORE UAT | BPK-023 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-EXT-028 | WF-13 | Internal review SLA Exact review due/SLA and escalation policy. | Project_Management_Platform_WF-13_External_Entity_Update_Review_Functional_Specification_v1.0.docx :: 25.2 Controlled TBC Register :: table 52, row 29 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-023 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-001 | WF-14 | Authoritative financial source system(s) Confirm systems and field-level authority for approved budget, actual expenditure and commitments. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 2 | PTBC-025; PTBC-033 | PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT | BEFORE BUILD / SIT | BPK-021 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-002 | WF-14 | Financial data refresh frequency Confirm integration cadence and acceptable source latency. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 3 | PTBC-025; PTBC-033 | PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT | BEFORE BUILD / SIT | BPK-021 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-003 | WF-14 | AHDA financial terminology Confirm preferred labels for commitments/encumbrances/forecast/final cost. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 4 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-004 | WF-14 | Reporting currency Confirm default/project reporting currency. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 5 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-005 | WF-14 | Multi-currency requirement Confirm whether conversion is required and approved rate source/method. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 6 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-006 | WF-14 | Commitment / encumbrance availability Confirm whether open commitments can be sourced reliably and their semantics. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 7 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-007 | WF-14 | Forecast at Completion ownership Confirm whether FAC is PM/manual, Finance/integrated, calculated or hybrid. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 8 | PTBC-004 | PTBC-004 Before closeout UAT | BEFORE UAT | BPK-021 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-008 | WF-14 | Financial category/breakdown Confirm Project total only vs configured cost/funding/phase categories. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 9 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-009 | WF-14 | Financial review routing Confirm routine reviewer assignment rules by Project/type/source mode. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 10 | PTBC-025; PTBC-033 | PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT | BEFORE BUILD / SIT | BPK-021 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-010 | WF-14 | Financial reporting frequency Confirm monthly/other cycles and relationship to WF-02 periods. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 11 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-011 | WF-14 | Financial Condition thresholds Confirm versioned thresholds and labels in FG-04. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 12 | PTBC-025 | PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 12 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-012 | WF-14 | KPI catalogue governance details Confirm business ownership/publish authority and catalogue values in FG-04. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 13 | PTBC-010; PTBC-024 | PTBC-010 Before admin UAT; PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-013 | WF-14 | Project KPI catalogue / assignments Confirm which KPI Definitions are mandatory/optional by Project type/classification. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 14 | PTBC-013; PTBC-024 | PTBC-013 Before UAT data load; PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-014 | WF-14 | KPI target approval/materiality Confirm which target changes require WF-08/WF-11 governance. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 15 | PTBC-009; PTBC-024 | PTBC-009 Before change UAT; PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-015 | WF-14 | KPI measurement frequencies Confirm allowed/default frequencies by KPI. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 16 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-016 | WF-14 | KPI Condition thresholds Confirm versioned condition bands by KPI/direction. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 17 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-017 | WF-14 | Derived KPI formula catalogue Confirm supported allowlisted formulas/inputs and governance. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 18 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-018 | WF-14 | KPI evidence requirements Confirm evidence categories/conditions; no fixed count assumed. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 19 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-019 | WF-14 | Manual fallback / override policy Confirm if/when manual values may temporarily substitute unavailable integrated source. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 20 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-020 | WF-14 | Financial/KPI freshness thresholds Confirm stale/missing escalation thresholds by source/domain. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 21 | PTBC-024; PTBC-025; PTBC-033; PTBC-037 | PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT; PTBC-033 Before financial integration SIT; PTBC-037 Before operations UAT | BEFORE BUILD / SIT | BPK-021 |  | 24 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-021 | WF-14 | Published correction authority Confirm who may initiate/review/publish corrections. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 22 | PTBC-010 | PTBC-010 Before admin UAT | BEFORE UAT | BPK-021 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
PERF-TBC-022 | WF-14 | WF-08 financial/KPI materiality rules Confirm exact thresholds/commitment operations that require formal ChangeAuthorization. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 23 | PTBC-009; PTBC-024; PTBC-025 | PTBC-009 Before change UAT; PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-023 | WF-14 | External Entity Financial/KPI visibility Confirm which values/fields can be shown through WF-13 projections. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 24 | PTBC-024; PTBC-025 | PTBC-024 Before KPI UAT; PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 23 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-024 | WF-14 | Sensitive financial classifications Confirm restricted fields, masking/export rules and step-up authentication triggers. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 25 | PTBC-025; PTBC-027; PTBC-028 | PTBC-025 Before financial UAT; PTBC-027 Before production; PTBC-028 Before security UAT | BEFORE UAT | BPK-021 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-025 | WF-14 | Completion/Closure financial close requirements Confirm minimum close-status/disposition needed for Completed vs Closed. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 26 | PTBC-004; PTBC-025 | PTBC-004 Before closeout UAT; PTBC-025 Before financial UAT | BEFORE UAT | BPK-021 |  | 13 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-026 | WF-14 | Benefits/post-Project KPI policy Confirm which KPIs/benefits continue after Closure and receiving owner requirements. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 27 | PTBC-004; PTBC-024 | PTBC-004 Before closeout UAT; PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 16 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-027 | WF-14 | Notification timing/channels Confirm due/overdue/condition-alert timings and channels through WF-15. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 28 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-021 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
PERF-TBC-028 | WF-14 | Bulk import policy Confirm whether controlled XLSX/CSV import is needed in MVP. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 29 | PTBC-024 | PTBC-024 Before KPI UAT | BEFORE UAT | BPK-021 |  | 15 | ANALYTICAL | OPEN — deferred to PTBC gate
PERF-TBC-029 | WF-14 | Exact integration APIs/mappings Confirm endpoint/data contracts once source systems are selected. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 30 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-021 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-033 | BEFORE BUILD / SIT | Integration API/data contracts once source systems are selected is PTBC-033
PERF-TBC-030 | WF-14 | Retention / audit / performance SLAs Confirm retention periods, operational support expectations and technical SLAs. | Project_Management_Platform_WF-14_KPI_Financial_Progress_Functional_Specification_v1.0.docx :: 26.3 Controlled TBC Register :: table 54, row 31 | PTBC-020; PTBC-043; PTBC-047 | PTBC-020 Before notification UAT; PTBC-043 Before performance test; PTBC-047 Before production | BEFORE BUILD / SIT | BPK-021 |  | 1 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-001 | WF-15 | Enabled external channels beyond In-App/Email, including SMS. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 2 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-002 | WF-15 | Email provider/gateway and integration topology. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 3 | PTBC-032; PTBC-034 | PTBC-032 Before integration build/SIT; PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-003 | WF-15 | SMS provider/gateway if enabled. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 4 | PTBC-032; PTBC-034 | PTBC-032 Before integration build/SIT; PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-004 | WF-15 | Exact reminder offsets by domain/event. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 5 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-005 | WF-15 | Exact overdue recurrence frequencies. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 6 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-006 | WF-15 | Escalation timing and recipients by source domain. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 7 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-007 | WF-15 | Mandatory vs USER_CONFIGURABLE classification for each event family. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 8 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-008 | WF-15 | Final Arabic/English template content and mandatory bilingual completeness policy. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 9 | PTBC-039 | PTBC-039 Before UAT | BEFORE UAT | BPK-012 |  | 2 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-009 | WF-15 | User preference categories and which channels may be disabled. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 10 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-010 | WF-15 | Quiet-hours enablement/rules. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 11 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-011 | WF-15 | Digest enablement, cadence and eligible events. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 12 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-012 | WF-15 | Automatic channel fallback rules. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 13 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-013 | WF-15 | Sensitive-content rules by channel/classification. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 14 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-014 | WF-15 | Exact retry count/backoff and provider throttling settings. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 15 | PTBC-032; PTBC-034; PTBC-038; PTBC-043 | PTBC-032 Before integration build/SIT; PTBC-034 Before notification SIT; PTBC-038 Before SIT; PTBC-043 Before performance test | BEFORE BUILD / SIT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-015 | WF-15 | Notification history retention periods/classifications. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 16 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-012 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-NTF-016 | WF-15 | Broadcast/system-announcement authority and targeting. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 17 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-017 | WF-15 | External Entity channel/contact policy. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 18 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-018 | WF-15 | Acknowledgement-required events, if any. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 19 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-019 | WF-15 | Delivery/read audit event retention/thresholds. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 20 | PTBC-047 | PTBC-047 Before production | BEFORE PRODUCTION | BPK-012 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate
TBC-NTF-020 | WF-15 | Operational SLAs for event intake/delivery/queue health. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 21 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-021 | WF-15 | Exact anti-flood/rate limits. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 22 | PTBC-020 | PTBC-020 Before notification UAT | BEFORE UAT | BPK-012 |  | 9 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-022 | WF-15 | Whether provider “delivered” receipts are available/reliable per channel. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 23 | PTBC-032; PTBC-034 | PTBC-032 Before integration build/SIT; PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-023 | WF-15 | Email subject/body branding and sender identities. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 24 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate
TBC-NTF-024 | WF-15 | Exact event family deduplication mappings between WF-11 and source domains. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 25 | PTBC-042 | PTBC-042 Can remain configurable/deferred | MAY REMAIN CONFIGURABLE | BPK-012 |  | 0 | NONE (14B v1.1 §8 analytical gap) | OPEN — deferred to PTBC gate | ASSOCIATION UNDER REVIEW (004-F-001) | PTBC-020 | BEFORE UAT | Event-family deduplication between WF-11 and source domains is notification configuration (PTBC-020)
TBC-NTF-025 | WF-15 | Whether selected security/governance communications require multiple mandatory channels. | Project_Management_Platform_WF-15_Notifications_Reminders_Escalations_Functional_Specification_v1.0.docx :: 24.2 Controlled TBC Register :: table 46, row 26 | PTBC-034 | PTBC-034 Before notification SIT | BEFORE BUILD / SIT | BPK-012 |  | 8 | ANALYTICAL | OPEN — deferred to PTBC gate

## 03_Task_Links
Task ID | Task name | Phase | Task wave (TASK-003 App. A) | Step 15 package(s) | Priority | PTBC ID | PTBC theme | Gate class | Link strength | Link basis | Evidence | Constraint on the task (must not invent) | Workbook cites PTBC ID?
TASK-002 | Close Step 14B RTM Findings | P0 | W0 | BPK-001; BPK-002; BPK-004 (F-006 disposition) | P0 | PTBC-042 | Geospatial/map and advanced visualization requirement | MAY REMAIN CONFIGURABLE | DIRECT | OPEN QUESTION | OQ-004: Closed by 14B v1.1 §5.3; the one deferred component (SCR-035 map view) sits at PTBC-042 and is built, if confirmed, by TASK-070 (FG-01 frontend) | Only implement if AHDA confirms business value/data quality. Exact approved authority/value/provider; no production default inferred. | NO
TASK-005 | Resolve Hosting & Data Localisation Architecture Decision Record | P1 | W0 | 15-D-005 / ADR-001 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | OPEN QUESTION | OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-006 | Ratify Application Technology Stack ADR | P1 | W0 | 15-D-005 / ADR-002 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | DIRECT | ADR | TASK-006 produces ADR-002 (stack); PTBC-044 observability/APM products follow the stack decision and AHDA IT selection | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-007 | Define Three-Tier Solution Architecture & Module Boundaries | P1 | W0 | BPK-005 (design) / 15-D-002 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-007 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-007 | Define Three-Tier Solution Architecture & Module Boundaries | P1 | W0 | BPK-005 (design) / 15-D-002 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-007 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-007 | Define Three-Tier Solution Architecture & Module Boundaries | P1 | W0 | BPK-005 (design) / 15-D-002 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-007 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-007 | Define Three-Tier Solution Architecture & Module Boundaries | P1 | W0 | BPK-005 (design) / 15-D-002 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-007 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-007 | Define Three-Tier Solution Architecture & Module Boundaries | P1 | W0 | BPK-005 (design) / 15-D-002 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-007 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-007, BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-009 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-013 | Project type/classification/priority/sector/location catalogues | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-007, BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-013 | Final AHDA master values and labels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-008 | Produce Canonical Entity-Relationship Diagram | P1 | W0 | BPK-007, BPK-014 (data model) | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-008 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-033 | Financial/KPI authoritative source systems and field authority | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-033 | Source-of-truth fields, cadence, reconciliation and fallback policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-034 | Email/SMS provider topology and callbacks | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-034 | Provider/gateway capabilities, callback semantics and throttling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-035 | Document storage/malware-scan provider and quarantine operations | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-035 | Technology, retry/quarantine operating procedure. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-037 | Integration health/freshness/reconciliation thresholds | BEFORE UAT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-037 | Exact latency/failure/backlog/stale/tolerance thresholds. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-038 | Retry/backoff/dead-letter policies | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-038 | Counts/backoff/final-failure rules; architecture already requires idempotency. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-009 | Define Platform API & Event Contract Conventions | P1 | W0 | BPK-009 (ICD-06 contracts) / 15-D-002 | P0 | PTBC-046 | Operational alert recipients, maintenance governance and production retry authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-009 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-046 | Who can acknowledge/retry/reprocess in PROD and maintenance handling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | DIRECT | EXPLICIT; SOURCE FAMILY | TASK-010 text cites PTBC-026 ¦ TASK-010 builds CSB-CYBER-GUIDE, a source family of PTBC-026 (CSB-14A §19.2) | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | YES
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-010 builds CSB-CYBER-GUIDE, a source family of PTBC-027 (CSB-14A §19.2) | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-010 builds CSB-CYBER-GUIDE, a source family of PTBC-029 (CSB-14A §19.2) | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | DIRECT | EXPLICIT | TASK-010 text cites PTBC-030 | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | YES
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-010 builds CSB-CYBER-GUIDE, a source family of PTBC-032 (CSB-14A §19.2) | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-010 builds CSB-CYBER-GUIDE, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-010 builds CSB-CYBER-GUIDE, a source family of PTBC-044 (CSB-14A §19.2) | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | BPK-003 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-010 builds CSB-CYBER-GUIDE, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-011 | Initialize Monorepo & Solution Structure | P2 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-011 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-011 | Initialize Monorepo & Solution Structure | P2 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-011 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-011 | Initialize Monorepo & Solution Structure | P2 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-011 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-011 | Initialize Monorepo & Solution Structure | P2 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-011 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-011 | Initialize Monorepo & Solution Structure | P2 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-011 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-012 | Define Branching Strategy, PR Template & Code Owners | P2 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-012 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-012 | Define Branching Strategy, PR Template & Code Owners | P2 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-012 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-012 | Define Branching Strategy, PR Template & Code Owners | P2 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-012 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-012 | Define Branching Strategy, PR Template & Code Owners | P2 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-012 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-012 | Define Branching Strategy, PR Template & Code Owners | P2 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-012 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-013 | Author Environment Variable Templates per Environment | P2 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-013 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-013 | Author Environment Variable Templates per Environment | P2 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-013 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-013 | Author Environment Variable Templates per Environment | P2 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-013 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-013 | Author Environment Variable Templates per Environment | P2 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-013 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-013 | Author Environment Variable Templates per Environment | P2 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-013 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-014 | Build Local Development Environment (Docker Compose) | P2 | W1 | BPK-005-I1 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-014 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-014 | Build Local Development Environment (Docker Compose) | P2 | W1 | BPK-005-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-014 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-014 | Build Local Development Environment (Docker Compose) | P2 | W1 | BPK-005-I1 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-014 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-014 | Build Local Development Environment (Docker Compose) | P2 | W1 | BPK-005-I1 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-014 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-014 | Build Local Development Environment (Docker Compose) | P2 | W1 | BPK-005-I1 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | OPEN QUESTION; PACKAGE | OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook ¦ TASK-014 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-015 | Configure Quality Gates: Lint, Format, Type-Check, Test in CI | P2 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-015 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-015 | Configure Quality Gates: Lint, Format, Type-Check, Test in CI | P2 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-015 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-015 | Configure Quality Gates: Lint, Format, Type-Check, Test in CI | P2 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-015 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-015 | Configure Quality Gates: Lint, Format, Type-Check, Test in CI | P2 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-015 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-015 | Configure Quality Gates: Lint, Format, Type-Check, Test in CI | P2 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | OPEN QUESTION; PACKAGE | OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook ¦ TASK-015 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-016 | Provision DEV / SIT / UAT / PROD Environment Separation | P3 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-016 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-016 | Provision DEV / SIT / UAT / PROD Environment Separation | P3 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-016 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-016 | Provision DEV / SIT / UAT / PROD Environment Separation | P3 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-016 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-016 | Provision DEV / SIT / UAT / PROD Environment Separation | P3 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-016 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-016 | Provision DEV / SIT / UAT / PROD Environment Separation | P3 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | OPEN QUESTION; PACKAGE | OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook ¦ TASK-016 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-017 | Author Infrastructure as Code for Approved Hosting Target | P3 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-017 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-017 | Author Infrastructure as Code for Approved Hosting Target | P3 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-017 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-017 | Author Infrastructure as Code for Approved Hosting Target | P3 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-017 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-017 | Author Infrastructure as Code for Approved Hosting Target | P3 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-017 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-017 | Author Infrastructure as Code for Approved Hosting Target | P3 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | OPEN QUESTION; PACKAGE | OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook ¦ TASK-017 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-018 | Build CI/CD Pipeline with Controlled Promotion Gates | P3 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-018 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-018 | Build CI/CD Pipeline with Controlled Promotion Gates | P3 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-018 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-018 | Build CI/CD Pipeline with Controlled Promotion Gates | P3 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-018 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-018 | Build CI/CD Pipeline with Controlled Promotion Gates | P3 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-018 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-018 | Build CI/CD Pipeline with Controlled Promotion Gates | P3 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | OPEN QUESTION; PACKAGE | OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook ¦ TASK-018 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-019 | Integrate Approved Secret Management Store | P3 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-019 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-019 | Integrate Approved Secret Management Store | P3 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-019 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-019 | Integrate Approved Secret Management Store | P3 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-019 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-019 | Integrate Approved Secret Management Store | P3 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-019 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-019 | Integrate Approved Secret Management Store | P3 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | OPEN QUESTION; PACKAGE | OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook ¦ TASK-019 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-020 builds CSB-CYBER-GUIDE, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-020 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-020 builds CSB-CYBER-GUIDE, a source family of PTBC-027 (CSB-14A §19.2) | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-020 builds CSB-CYBER-GUIDE, a source family of PTBC-029 (CSB-14A §19.2) | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-020 builds CSB-CYBER-GUIDE, a source family of PTBC-032 (CSB-14A §19.2) | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-020 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-020 builds CSB-CYBER-GUIDE, a source family of PTBC-043 (CSB-14A §19.2) ¦ TASK-020 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-020 builds CSB-CYBER-GUIDE, a source family of PTBC-044 (CSB-14A §19.2) ¦ TASK-020 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-020 | Provision Managed PostgreSQL with Backup & Encryption | P3 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | EXPLICIT; OPEN QUESTION; SOURCE FAMILY; PACKAGE | TASK-020 text cites PTBC-048 ¦ OQ-001: OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook ¦ TASK-020 builds CSB-CYBER-GUIDE, a source family of PTBC-048 (CSB-14A §19.2) ¦ TASK-020 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | YES
TASK-021 | Configure Network Security: WAF, Load Balancer & Segmentation | P3 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-021 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-021 | Configure Network Security: WAF, Load Balancer & Segmentation | P3 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-021 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-021 | Configure Network Security: WAF, Load Balancer & Segmentation | P3 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-021 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-021 | Configure Network Security: WAF, Load Balancer & Segmentation | P3 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-021 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-021 | Configure Network Security: WAF, Load Balancer & Segmentation | P3 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-021 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-022 | Establish Container/Artifact Build & Dependency Scanning | P3 | W1 | BPK-005-I1 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-022 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-022 | Establish Container/Artifact Build & Dependency Scanning | P3 | W1 | BPK-005-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-022 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-022 | Establish Container/Artifact Build & Dependency Scanning | P3 | W1 | BPK-005-I1 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-022 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-022 | Establish Container/Artifact Build & Dependency Scanning | P3 | W1 | BPK-005-I1 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-022 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-022 | Establish Container/Artifact Build & Dependency Scanning | P3 | W1 | BPK-005-I1 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-022 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-023 builds CSB-CYBER-GUIDE, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-023 delivers BPK-005, BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-023 builds CSB-CYBER-GUIDE, a source family of PTBC-027 (CSB-14A §19.2) ¦ TASK-023 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-023 builds CSB-CYBER-GUIDE, a source family of PTBC-029 (CSB-14A §19.2) ¦ TASK-023 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-023 builds CSB-CYBER-GUIDE, a source family of PTBC-032 (CSB-14A §19.2) ¦ TASK-023 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-023 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-023 builds CSB-CYBER-GUIDE, a source family of PTBC-043 (CSB-14A §19.2) ¦ TASK-023 delivers BPK-005, BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-023 builds CSB-CYBER-GUIDE, a source family of PTBC-044 (CSB-14A §19.2) ¦ TASK-023 delivers BPK-005, BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-023 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-023 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | BPK-005-I1 (runbook); BPK-030 (drill evidence) | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | DIRECT | EXPLICIT; OPEN QUESTION; SOURCE FAMILY; PACKAGE | TASK-023 text cites PTBC-048 ¦ OQ-003: OQ-003 names PTBC-048; "TASK for backup/restore/DR runbook" = TASK-023 ¦ TASK-023 builds CSB-CYBER-GUIDE, a source family of PTBC-048 (CSB-14A §19.2) ¦ TASK-023 delivers BPK-005, BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | YES
TASK-024 | Establish Database Migration Framework & Conventions | P4 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-024 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-024 | Establish Database Migration Framework & Conventions | P4 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-024 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-024 | Establish Database Migration Framework & Conventions | P4 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-024 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-024 | Establish Database Migration Framework & Conventions | P4 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-024 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-024 | Establish Database Migration Framework & Conventions | P4 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-024 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-007, BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-006, BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-009 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-013 | Project type/classification/priority/sector/location catalogues | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-007, BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-013 | Final AHDA master values and labels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-025 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-025 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-025 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-025 | Implement Core Platform Schema (Project, User, Org, Master Data) | P4 | W1 | BPK-006-I1; BPK-007-I1; BPK-014 (Project identity) | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | PACKAGE | PACKAGE | TASK-025 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-026 | Define Indexing Strategy for Query, Filter, Sort & Pagination Paths | P4 | W1 | BPK-005-I1 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-026 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-026 | Define Indexing Strategy for Query, Filter, Sort & Pagination Paths | P4 | W1 | BPK-005-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-026 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-026 | Define Indexing Strategy for Query, Filter, Sort & Pagination Paths | P4 | W1 | BPK-005-I1 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-026 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-026 | Define Indexing Strategy for Query, Filter, Sort & Pagination Paths | P4 | W1 | BPK-005-I1 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-026 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-026 | Define Indexing Strategy for Query, Filter, Sort & Pagination Paths | P4 | W1 | BPK-005-I1 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-026 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | BPK-007-I1 | P1 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-027 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | BPK-007-I1 | P1 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | PACKAGE | PACKAGE | TASK-027 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-009 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | BPK-007-I1 | P1 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | PACKAGE | PACKAGE | TASK-027 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | BPK-007-I1 | P1 | PTBC-013 | Project type/classification/priority/sector/location catalogues | BEFORE UAT | PACKAGE | PACKAGE | TASK-027 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-013 | Final AHDA master values and labels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | BPK-007-I1 | P1 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-027 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | BPK-007-I1 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-027 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | BPK-006-I1 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-028 builds FG-03, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-028 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | BPK-006-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-028 builds FG-03, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-028 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | BPK-006-I1 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-028 builds FG-03, a source family of PTBC-027 (CSB-14A §19.2) ¦ TASK-028 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | BPK-006-I1 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-028 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | BPK-006-I1 | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-028 builds FG-03, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-028 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | BPK-006-I1 | P0 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-028 text cites PTBC-036 ¦ TASK-028 builds FG-03, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-028 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | YES
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | BPK-006-I1 | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-028 builds FG-03, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-028 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | BPK-006-I1 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-029 builds FG-03, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-029 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | BPK-006-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-029 builds FG-03, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-029 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | BPK-006-I1 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-029 text cites PTBC-027 ¦ TASK-029 builds FG-03, a source family of PTBC-027 (CSB-14A §19.2) ¦ TASK-029 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | YES
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | BPK-006-I1 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-029 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | BPK-006-I1 | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-029 builds FG-03, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-029 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | BPK-006-I1 | P0 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-029 builds FG-03, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-029 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | BPK-006-I1 | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-029 builds FG-03, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-029 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-030 | Implement Server-Side RBAC & Data-Scope Authorization Engine | P5 | W1 | BPK-006-I1 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-030 builds FG-03, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-030 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-030 | Implement Server-Side RBAC & Data-Scope Authorization Engine | P5 | W1 | BPK-006-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-030 builds FG-03, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-030 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-030 | Implement Server-Side RBAC & Data-Scope Authorization Engine | P5 | W1 | BPK-006-I1 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-030 builds FG-03, a source family of PTBC-027 (CSB-14A §19.2) ¦ TASK-030 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-030 | Implement Server-Side RBAC & Data-Scope Authorization Engine | P5 | W1 | BPK-006-I1 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-030 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-030 | Implement Server-Side RBAC & Data-Scope Authorization Engine | P5 | W1 | BPK-006-I1 | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-030 builds FG-03, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-030 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-030 | Implement Server-Side RBAC & Data-Scope Authorization Engine | P5 | W1 | BPK-006-I1 | P0 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-030 builds FG-03, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-030 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-030 | Implement Server-Side RBAC & Data-Scope Authorization Engine | P5 | W1 | BPK-006-I1 | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-030 builds FG-03, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-030 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-031 | Build Users, Roles & Permissions Administration (FG-03 Backend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-031 builds FG-03, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-031 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-031 | Build Users, Roles & Permissions Administration (FG-03 Backend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-031 builds FG-03, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-031 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-031 | Build Users, Roles & Permissions Administration (FG-03 Backend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-031 builds FG-03, a source family of PTBC-027 (CSB-14A §19.2) ¦ TASK-031 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-031 | Build Users, Roles & Permissions Administration (FG-03 Backend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-031 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-031 | Build Users, Roles & Permissions Administration (FG-03 Backend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-031 builds FG-03, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-031 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-031 | Build Users, Roles & Permissions Administration (FG-03 Backend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-031 builds FG-03, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-031 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-031 | Build Users, Roles & Permissions Administration (FG-03 Backend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-031 builds FG-03, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-031 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-032 builds FG-03, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-032 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-032 builds FG-03, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-032 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-032 builds FG-03, a source family of PTBC-027 (CSB-14A §19.2) ¦ TASK-032 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-032 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-032 builds FG-03, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-032 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-032 builds FG-03, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-032 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-032 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-032 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-032 | Build Users, Roles & Permissions Administration (FG-03 Frontend) | P5 | W3 | BPK-006-I2 | P1 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-032 builds FG-03, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-032 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-03, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-011 | Audit Reviewer, retention-hold and disposal authorities | BEFORE UAT | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-033 text cites PTBC-011 ¦ TASK-033 builds FG-06, a source family of PTBC-011 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-011 | Named permission/assignment authorities and SoD. Exact approved authority/value/provider; no production default inferred. | YES
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-012 | Sensitive read/export audit policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-033 builds FG-06, a source family of PTBC-012 (CSB-14A §19.2) | Which views/downloads require enhanced audit. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-03, FG-06, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-006, BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-03, a source family of PTBC-027 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-06, a source family of PTBC-028 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-033 text cites PTBC-029 ¦ TASK-033 builds FG-06, a source family of PTBC-029 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | YES
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-033 builds FG-06, a source family of PTBC-030 (CSB-14A §19.2) | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-03, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-03, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-033 builds FG-06, a source family of PTBC-039 (CSB-14A §19.2) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-03, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-033 builds FG-06, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-033 builds FG-06, a source family of PTBC-044 (CSB-14A §19.2) | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-06, a source family of PTBC-045 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-033 builds FG-06, a source family of PTBC-047 (CSB-14A §19.2) ¦ TASK-033 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | BPK-006-I1; BPK-008-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-033 builds FG-06, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-034 builds FG-04, a source family of PTBC-002 (CSB-14A §19.2) ¦ TASK-034 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-034 builds FG-04, a source family of PTBC-009 (CSB-14A §19.2) ¦ TASK-034 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-009 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-034 builds FG-04, a source family of PTBC-010 (CSB-14A §19.2) ¦ TASK-034 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-013 | Project type/classification/priority/sector/location catalogues | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-034 builds FG-04, a source family of PTBC-013 (CSB-14A §19.2) ¦ TASK-034 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-013 | Final AHDA master values and labels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-034 builds FG-04, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-034 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-017 | Risk scales/dimensions/matrix | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-034 builds FG-04, a source family of PTBC-017 (CSB-14A §19.2) | Probability/Impact labels, quantitative descriptions, 5x5 cell→rating mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-018 | Issue/Challenge categories/severity/priority master data | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-034 builds FG-04, a source family of PTBC-018 (CSB-14A §19.2) | Final categories, dimension labels and presentation. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-034 builds FG-04, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-034 builds FG-04, a source family of PTBC-023 (CSB-14A §19.2) | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-024 | KPI catalogue/formulas/targets/condition thresholds | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-034 builds FG-04, a source family of PTBC-024 (CSB-14A §19.2) | Final KPI definitions, formulas/evidence/condition rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-025 | Financial condition/variance/forecast terminology and thresholds | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-034 builds FG-04, a source family of PTBC-025 (CSB-14A §19.2) | Final AHDA terms and attention/critical rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | BPK-007-I1 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-034 delivers BPK-007, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-035 | Build Shared Approval Framework (WF-11 Backend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-005: OQ-005 names PTBC-001/009; "TASK for WF-11 backend" = TASK-035, "TASK for WF-08 backend" = TASK-060 ¦ TASK-035 builds WF-11, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-035 delivers BPK-011, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-035 | Build Shared Approval Framework (WF-11 Backend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-005: OQ-005 names PTBC-001/009; "TASK for WF-11 backend" = TASK-035, "TASK for WF-08 backend" = TASK-060 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-035 | Build Shared Approval Framework (WF-11 Backend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-035 builds WF-11, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-035 delivers BPK-011, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-035 | Build Shared Approval Framework (WF-11 Backend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-035 builds WF-11, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-036 | Build Approvals UI: Inbox, My Requests & History (WF-11 Frontend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-036 builds WF-11, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-036 delivers BPK-011, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-036 | Build Approvals UI: Inbox, My Requests & History (WF-11 Frontend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-036 builds WF-11, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-036 delivers BPK-011, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-036 | Build Approvals UI: Inbox, My Requests & History (WF-11 Frontend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-036 builds WF-11, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-036 | Build Approvals UI: Inbox, My Requests & History (WF-11 Frontend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-036 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-036 | Build Approvals UI: Inbox, My Requests & History (WF-11 Frontend) | P6 | W2 | BPK-011-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-036 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-037 | Build Document & Evidence Management (WF-12 Backend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-037 builds WF-12, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-037 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-037 | Build Document & Evidence Management (WF-12 Backend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-037 builds WF-12, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-037 | Build Document & Evidence Management (WF-12 Backend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-037 builds WF-12, a source family of PTBC-026 (CSB-14A §19.2) | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-037 | Build Document & Evidence Management (WF-12 Backend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-037 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-037 | Build Document & Evidence Management (WF-12 Backend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-037 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-030 | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-037 | Build Document & Evidence Management (WF-12 Backend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-035 | Document storage/malware-scan provider and quarantine operations | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-037 builds WF-12, a source family of PTBC-035 (CSB-14A §19.2) ¦ TASK-037 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-035 | Technology, retry/quarantine operating procedure. Exact approved authority/value/provider; no production default inferred. | NO
TASK-037 | Build Document & Evidence Management (WF-12 Backend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-037 builds WF-12, a source family of PTBC-047 (CSB-14A §19.2) ¦ TASK-037 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-038 builds WF-12, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-038 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-038 builds WF-12, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-038 builds WF-12, a source family of PTBC-026 (CSB-14A §19.2) | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-038 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-038 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-030 | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-035 | Document storage/malware-scan provider and quarantine operations | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-038 builds WF-12, a source family of PTBC-035 (CSB-14A §19.2) ¦ TASK-038 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-035 | Technology, retry/quarantine operating procedure. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-038 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-038 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-038 | Build Document Library & Upload UI (WF-12 Frontend) | P6 | W2 | BPK-010-I1 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-038 builds WF-12, a source family of PTBC-047 (CSB-14A §19.2) ¦ TASK-038 delivers BPK-010, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-039 | Build Notifications, Reminders & Escalations Runtime (WF-15 Backend) | P6 | W2 | BPK-012-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-039 builds WF-15, a source family of PTBC-020 (CSB-14A §19.2) ¦ TASK-039 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-020 | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-039 | Build Notifications, Reminders & Escalations Runtime (WF-15 Backend) | P6 | W2 | BPK-012-I1 | P0 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-039 builds WF-15, a source family of PTBC-030 (CSB-14A §19.2) | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-039 | Build Notifications, Reminders & Escalations Runtime (WF-15 Backend) | P6 | W2 | BPK-012-I1 | P0 | PTBC-034 | Email/SMS provider topology and callbacks | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-039 builds WF-15, a source family of PTBC-034 (CSB-14A §19.2) ¦ TASK-039 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-034 | Provider/gateway capabilities, callback semantics and throttling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-039 | Build Notifications, Reminders & Escalations Runtime (WF-15 Backend) | P6 | W2 | BPK-012-I1 | P0 | PTBC-038 | Retry/backoff/dead-letter policies | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-039 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-038 | Counts/backoff/final-failure rules; architecture already requires idempotency. Exact approved authority/value/provider; no production default inferred. | NO
TASK-039 | Build Notifications, Reminders & Escalations Runtime (WF-15 Backend) | P6 | W2 | BPK-012-I1 | P0 | PTBC-046 | Operational alert recipients, maintenance governance and production retry authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-039 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-046 | Who can acknowledge/retry/reprocess in PROD and maintenance handling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-040 | Build Notification Center UI (WF-15 Frontend) | P6 | W2 | BPK-012-I1 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-040 builds WF-15, a source family of PTBC-020 (CSB-14A §19.2) ¦ TASK-040 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-020 | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-040 | Build Notification Center UI (WF-15 Frontend) | P6 | W2 | BPK-012-I1 | P1 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-040 builds WF-15, a source family of PTBC-030 (CSB-14A §19.2) | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-040 | Build Notification Center UI (WF-15 Frontend) | P6 | W2 | BPK-012-I1 | P1 | PTBC-034 | Email/SMS provider topology and callbacks | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-040 builds WF-15, a source family of PTBC-034 (CSB-14A §19.2) ¦ TASK-040 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-034 | Provider/gateway capabilities, callback semantics and throttling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-040 | Build Notification Center UI (WF-15 Frontend) | P6 | W2 | BPK-012-I1 | P1 | PTBC-038 | Retry/backoff/dead-letter policies | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-040 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-038 | Counts/backoff/final-failure rules; architecture already requires idempotency. Exact approved authority/value/provider; no production default inferred. | NO
TASK-040 | Build Notification Center UI (WF-15 Frontend) | P6 | W2 | BPK-012-I1 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-040 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-040 | Build Notification Center UI (WF-15 Frontend) | P6 | W2 | BPK-012-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-040 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-040 | Build Notification Center UI (WF-15 Frontend) | P6 | W2 | BPK-012-I1 | P1 | PTBC-046 | Operational alert recipients, maintenance governance and production retry authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-040 delivers BPK-012, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-046 | Who can acknowledge/retry/reprocess in PROD and maintenance handling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-041 | Build Project Creation & Registration (WF-01 Backend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-041 builds WF-01, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-041 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-041 | Build Project Creation & Registration (WF-01 Backend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-041 text cites PTBC-002 ¦ TASK-041 builds WF-01, a source family of PTBC-002 (CSB-14A §19.2) ¦ TASK-041 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | YES
TASK-041 | Build Project Creation & Registration (WF-01 Backend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-041 builds WF-01, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-041 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-041 | Build Project Creation & Registration (WF-01 Backend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-013 | Project type/classification/priority/sector/location catalogues | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-041 builds WF-01, a source family of PTBC-013 (CSB-14A §19.2) ¦ TASK-041 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-013 | Final AHDA master values and labels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-041 | Build Project Creation & Registration (WF-01 Backend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-041 builds WF-01, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-041 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-041 | Build Project Creation & Registration (WF-01 Backend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-041 builds WF-01, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-042 builds WF-01, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-042 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-042 builds WF-01, a source family of PTBC-002 (CSB-14A §19.2) ¦ TASK-042 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-042 builds WF-01, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-042 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-013 | Project type/classification/priority/sector/location catalogues | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-042 builds WF-01, a source family of PTBC-013 (CSB-14A §19.2) ¦ TASK-042 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-013 | Final AHDA master values and labels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-042 builds WF-01, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-042 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-042 builds WF-01, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-042 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-042 | Build Project Register & Creation UI (WF-01 Frontend) | P7 | W2 | BPK-014-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-042 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-043 | Contract & Integration Tests for Project Lifecycle | P7 | W2 | BPK-014-I1 | P1 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | PACKAGE | PACKAGE | TASK-043 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-043 | Contract & Integration Tests for Project Lifecycle | P7 | W2 | BPK-014-I1 | P1 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | PACKAGE | PACKAGE | TASK-043 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-043 | Contract & Integration Tests for Project Lifecycle | P7 | W2 | BPK-014-I1 | P1 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-043 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-043 | Contract & Integration Tests for Project Lifecycle | P7 | W2 | BPK-014-I1 | P1 | PTBC-013 | Project type/classification/priority/sector/location catalogues | BEFORE UAT | PACKAGE | PACKAGE | TASK-043 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-013 | Final AHDA master values and labels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-043 | Contract & Integration Tests for Project Lifecycle | P7 | W2 | BPK-014-I1 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | PACKAGE | PACKAGE | TASK-043 delivers BPK-014, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-044 | Build Progress Update & Overall Health (WF-02 Backend) | P8 | W4 | BPK-022 | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-044 builds WF-02, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-044 delivers BPK-022, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-044 | Build Progress Update & Overall Health (WF-02 Backend) | P8 | W4 | BPK-022 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-044 builds WF-02, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-044 | Build Progress Update & Overall Health (WF-02 Backend) | P8 | W4 | BPK-022 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-044 builds WF-02, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-044 | Build Progress Update & Overall Health (WF-02 Backend) | P8 | W4 | BPK-022 | P0 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-044 builds WF-02, a source family of PTBC-023 (CSB-14A §19.2) ¦ TASK-044 delivers BPK-022, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-023 | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-045 builds WF-03, a source family of PTBC-001 (CSB-14A §19.2) | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-045 builds WF-03, a source family of PTBC-002 (CSB-14A §19.2) | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-045 builds WF-02, WF-03, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-045 delivers BPK-022, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-015 | Schedule Health thresholds and calendar override policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-045 builds WF-03, a source family of PTBC-015 (CSB-14A §19.2) | Warning/critical thresholds and allowed overrides. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-045 builds WF-02, WF-03, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-045 builds WF-02, WF-03, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-045 builds WF-02, a source family of PTBC-023 (CSB-14A §19.2) ¦ TASK-045 delivers BPK-022, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-023 | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-045 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-045 | Build Progress & Schedule UI (WF-02/WF-03 Frontend) | P8 | W4 | BPK-022 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-045 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-046 | Build Schedule & Baseline Management (WF-03 Backend) | P8 | W3 | BPK-015-I1 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-046 builds WF-03, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-046 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-046 | Build Schedule & Baseline Management (WF-03 Backend) | P8 | W3 | BPK-015-I1 | P0 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-046 builds WF-03, a source family of PTBC-002 (CSB-14A §19.2) ¦ TASK-046 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-046 | Build Schedule & Baseline Management (WF-03 Backend) | P8 | W3 | BPK-015-I1 | P0 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-046 builds WF-03, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-046 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-046 | Build Schedule & Baseline Management (WF-03 Backend) | P8 | W3 | BPK-015-I1 | P0 | PTBC-015 | Schedule Health thresholds and calendar override policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-046 builds WF-03, a source family of PTBC-015 (CSB-14A §19.2) ¦ TASK-046 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-015 | Warning/critical thresholds and allowed overrides. Exact approved authority/value/provider; no production default inferred. | NO
TASK-046 | Build Schedule & Baseline Management (WF-03 Backend) | P8 | W3 | BPK-015-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-046 builds WF-03, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-046 | Build Schedule & Baseline Management (WF-03 Backend) | P8 | W3 | BPK-015-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-046 builds WF-03, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-047 builds WF-03, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-047 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-047 builds WF-03, a source family of PTBC-002 (CSB-14A §19.2) ¦ TASK-047 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-047 builds WF-03, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-047 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-015 | Schedule Health thresholds and calendar override policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-047 builds WF-03, a source family of PTBC-015 (CSB-14A §19.2) ¦ TASK-047 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-015 | Warning/critical thresholds and allowed overrides. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-047 builds WF-03, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-047 builds WF-03, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-047 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-047 | Build Schedule, Gantt & Baseline UI (WF-03 Frontend) | P8 | W3 | BPK-015-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-047 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-048 | Build Task Management (WF-04 Backend) | P8 | W3 | BPK-016-I1 | P0 | PTBC-016 | Task priority/category/reminder/blocked thresholds | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-048 builds WF-04, a source family of PTBC-016 (CSB-14A §19.2) ¦ TASK-048 delivers BPK-016, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-016 | Operational values remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-048 | Build Task Management (WF-04 Backend) | P8 | W3 | BPK-016-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-048 builds WF-04, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-048 | Build Task Management (WF-04 Backend) | P8 | W3 | BPK-016-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-048 builds WF-04, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-049 | Build Task Boards & My Tasks UI (WF-04 Frontend) | P8 | W3 | BPK-016-I1 | P1 | PTBC-016 | Task priority/category/reminder/blocked thresholds | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-049 builds WF-04, a source family of PTBC-016 (CSB-14A §19.2) ¦ TASK-049 delivers BPK-016, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-016 | Operational values remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-049 | Build Task Boards & My Tasks UI (WF-04 Frontend) | P8 | W3 | BPK-016-I1 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-049 builds WF-04, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-049 | Build Task Boards & My Tasks UI (WF-04 Frontend) | P8 | W3 | BPK-016-I1 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-049 builds WF-04, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-049 | Build Task Boards & My Tasks UI (WF-04 Frontend) | P8 | W3 | BPK-016-I1 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-049 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-049 | Build Task Boards & My Tasks UI (WF-04 Frontend) | P8 | W3 | BPK-016-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-049 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-050 | Build Milestone Management (WF-05 Backend) | P8 | W4 | BPK-017 | P0 | PTBC-006 | Milestone achievement evidence/review governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-050 builds WF-05, a source family of PTBC-006 (CSB-14A §19.2) ¦ TASK-050 delivers BPK-017, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-006 | Which milestone classes require evidence/acceptance/rejection options. Exact approved authority/value/provider; no production default inferred. | NO
TASK-050 | Build Milestone Management (WF-05 Backend) | P8 | W4 | BPK-017 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-050 builds WF-05, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-050 delivers BPK-017, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-050 | Build Milestone Management (WF-05 Backend) | P8 | W4 | BPK-017 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-050 builds WF-05, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-051 | Build Milestone Register & Achievement UI (WF-05 Frontend) | P8 | W4 | BPK-017 | P1 | PTBC-006 | Milestone achievement evidence/review governance | BEFORE UAT | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-051 text cites PTBC-006 ¦ TASK-051 builds WF-05, a source family of PTBC-006 (CSB-14A §19.2) ¦ TASK-051 delivers BPK-017, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-006 | Which milestone classes require evidence/acceptance/rejection options. Exact approved authority/value/provider; no production default inferred. | YES
TASK-051 | Build Milestone Register & Achievement UI (WF-05 Frontend) | P8 | W4 | BPK-017 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-051 text cites PTBC-019 ¦ TASK-051 builds WF-05, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-051 delivers BPK-017, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | YES
TASK-051 | Build Milestone Register & Achievement UI (WF-05 Frontend) | P8 | W4 | BPK-017 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-051 builds WF-05, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-051 | Build Milestone Register & Achievement UI (WF-05 Frontend) | P8 | W4 | BPK-017 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-051 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-051 | Build Milestone Register & Achievement UI (WF-05 Frontend) | P8 | W4 | BPK-017 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-051 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | BPK-021-I1 | P0 | PTBC-017 | Risk scales/dimensions/matrix | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-006: OQ-006 names PTBC-017/024/025; "TASK for WF-06 backend" = TASK-055, "TASK for WF-14 backend" = TASK-052 | Probability/Impact labels, quantitative descriptions, 5x5 cell→rating mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | BPK-021-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-052 builds WF-14, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | BPK-021-I1 | P0 | PTBC-024 | KPI catalogue/formulas/targets/condition thresholds | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-006: OQ-006 names PTBC-017/024/025; "TASK for WF-06 backend" = TASK-055, "TASK for WF-14 backend" = TASK-052 ¦ TASK-052 builds WF-14, a source family of PTBC-024 (CSB-14A §19.2) ¦ TASK-052 delivers BPK-021, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-024 | Final KPI definitions, formulas/evidence/condition rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | BPK-021-I1 | P0 | PTBC-025 | Financial condition/variance/forecast terminology and thresholds | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-006: OQ-006 names PTBC-017/024/025; "TASK for WF-06 backend" = TASK-055, "TASK for WF-14 backend" = TASK-052 ¦ TASK-052 builds WF-14, a source family of PTBC-025 (CSB-14A §19.2) ¦ TASK-052 delivers BPK-021, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-025 | Final AHDA terms and attention/critical rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | BPK-021-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-052 builds WF-14, a source family of PTBC-026 (CSB-14A §19.2) | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | BPK-021-I1 | P0 | PTBC-033 | Financial/KPI authoritative source systems and field authority | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-052 builds WF-14, a source family of PTBC-033 (CSB-14A §19.2) ¦ TASK-052 delivers BPK-021, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-033 | Source-of-truth fields, cadence, reconciliation and fallback policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | BPK-021-I1 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-053 builds WF-14, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | BPK-021-I1 | P1 | PTBC-024 | KPI catalogue/formulas/targets/condition thresholds | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-053 builds WF-14, a source family of PTBC-024 (CSB-14A §19.2) ¦ TASK-053 delivers BPK-021, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-024 | Final KPI definitions, formulas/evidence/condition rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | BPK-021-I1 | P1 | PTBC-025 | Financial condition/variance/forecast terminology and thresholds | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-053 builds WF-14, a source family of PTBC-025 (CSB-14A §19.2) ¦ TASK-053 delivers BPK-021, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-025 | Final AHDA terms and attention/critical rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | BPK-021-I1 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-053 builds WF-14, a source family of PTBC-026 (CSB-14A §19.2) | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | BPK-021-I1 | P1 | PTBC-033 | Financial/KPI authoritative source systems and field authority | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-053 builds WF-14, a source family of PTBC-033 (CSB-14A §19.2) ¦ TASK-053 delivers BPK-021, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-033 | Source-of-truth fields, cadence, reconciliation and fallback policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | BPK-021-I1 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-053 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | BPK-021-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-053 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-054 builds WF-03, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-054 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-002 | Project Activation authority and readiness policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-054 builds WF-03, a source family of PTBC-002 (CSB-14A §19.2) ¦ TASK-054 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-002 | Integrated owner is Project master; exact required readiness checks and actor authority remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-006 | Milestone achievement evidence/review governance | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-054 builds WF-05, a source family of PTBC-006 (CSB-14A §19.2) | Which milestone classes require evidence/acceptance/rejection options. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-014 | Business calendar, timezone and working-day policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-054 builds WF-02, WF-03, a source family of PTBC-014 (CSB-14A §19.2) ¦ TASK-054 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-014 | Shared business calendar plus schedule-specific working-time mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-015 | Schedule Health thresholds and calendar override policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-054 builds WF-03, a source family of PTBC-015 (CSB-14A §19.2) ¦ TASK-054 delivers BPK-015, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-015 | Warning/critical thresholds and allowed overrides. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-016 | Task priority/category/reminder/blocked thresholds | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-054 builds WF-04, a source family of PTBC-016 (CSB-14A §19.2) | Operational values remain configurable. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-054 builds WF-02, WF-03, WF-04, WF-05, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-054 builds WF-02, WF-03, WF-04, WF-05, WF-14, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-054 builds WF-02, a source family of PTBC-023 (CSB-14A §19.2) | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-024 | KPI catalogue/formulas/targets/condition thresholds | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-054 builds WF-14, a source family of PTBC-024 (CSB-14A §19.2) | Final KPI definitions, formulas/evidence/condition rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-025 | Financial condition/variance/forecast terminology and thresholds | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-054 builds WF-14, a source family of PTBC-025 (CSB-14A §19.2) | Final AHDA terms and attention/critical rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-054 builds WF-14, a source family of PTBC-026 (CSB-14A §19.2) | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-054 | Contract & Integration Tests for Execution Domain (WF-02/03/04/05/14) | P8 | W4 | BPK-015/016/017/021/022 | P1 | PTBC-033 | Financial/KPI authoritative source systems and field authority | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-054 builds WF-14, a source family of PTBC-033 (CSB-14A §19.2) | Source-of-truth fields, cadence, reconciliation and fallback policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-055 | Build Risk Management (WF-06 Backend) | P9 | W3 | BPK-018-I1 | P0 | PTBC-007 | Risk acceptance/escalation authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-055 builds WF-06, a source family of PTBC-007 (CSB-14A §19.2) ¦ TASK-055 delivers BPK-018, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-007 | Who may accept residual risk/escalation by rating/context. Exact approved authority/value/provider; no production default inferred. | NO
TASK-055 | Build Risk Management (WF-06 Backend) | P9 | W3 | BPK-018-I1 | P0 | PTBC-017 | Risk scales/dimensions/matrix | BEFORE UAT | DIRECT | EXPLICIT; OPEN QUESTION; SOURCE FAMILY; PACKAGE | TASK-055 text cites PTBC-017 ¦ OQ-006: OQ-006 names PTBC-017/024/025; "TASK for WF-06 backend" = TASK-055, "TASK for WF-14 backend" = TASK-052 ¦ TASK-055 builds WF-06, a source family of PTBC-017 (CSB-14A §19.2) ¦ TASK-055 delivers BPK-018, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-017 | Probability/Impact labels, quantitative descriptions, 5x5 cell→rating mapping. Exact approved authority/value/provider; no production default inferred. | YES
TASK-055 | Build Risk Management (WF-06 Backend) | P9 | W3 | BPK-018-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-055 builds WF-06, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-055 | Build Risk Management (WF-06 Backend) | P9 | W3 | BPK-018-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-055 builds WF-06, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-055 | Build Risk Management (WF-06 Backend) | P9 | W3 | BPK-018-I1 | P0 | PTBC-024 | KPI catalogue/formulas/targets/condition thresholds | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-006: OQ-006 names PTBC-017/024/025; "TASK for WF-06 backend" = TASK-055, "TASK for WF-14 backend" = TASK-052 | Final KPI definitions, formulas/evidence/condition rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-055 | Build Risk Management (WF-06 Backend) | P9 | W3 | BPK-018-I1 | P0 | PTBC-025 | Financial condition/variance/forecast terminology and thresholds | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-006: OQ-006 names PTBC-017/024/025; "TASK for WF-06 backend" = TASK-055, "TASK for WF-14 backend" = TASK-052 | Final AHDA terms and attention/critical rules. Exact approved authority/value/provider; no production default inferred. | NO
TASK-056 | Build Risk Register & Detail UI (WF-06 Frontend) | P9 | W3 | BPK-018-I1 | P1 | PTBC-007 | Risk acceptance/escalation authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-056 builds WF-06, a source family of PTBC-007 (CSB-14A §19.2) ¦ TASK-056 delivers BPK-018, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-007 | Who may accept residual risk/escalation by rating/context. Exact approved authority/value/provider; no production default inferred. | NO
TASK-056 | Build Risk Register & Detail UI (WF-06 Frontend) | P9 | W3 | BPK-018-I1 | P1 | PTBC-017 | Risk scales/dimensions/matrix | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-056 builds WF-06, a source family of PTBC-017 (CSB-14A §19.2) ¦ TASK-056 delivers BPK-018, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-017 | Probability/Impact labels, quantitative descriptions, 5x5 cell→rating mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-056 | Build Risk Register & Detail UI (WF-06 Frontend) | P9 | W3 | BPK-018-I1 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-056 builds WF-06, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-056 | Build Risk Register & Detail UI (WF-06 Frontend) | P9 | W3 | BPK-018-I1 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-056 builds WF-06, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-056 | Build Risk Register & Detail UI (WF-06 Frontend) | P9 | W3 | BPK-018-I1 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-056 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-056 | Build Risk Register & Detail UI (WF-06 Frontend) | P9 | W3 | BPK-018-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-056 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-057 | Build Issue & Challenge Management (WF-07 Backend) | P9 | W3 | BPK-019-I1 | P0 | PTBC-008 | Issue/Challenge severity-priority/escalation governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-057 builds WF-07, a source family of PTBC-008 (CSB-14A §19.2) ¦ TASK-057 delivers BPK-019, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-008 | Final labels, minimum priority rules and escalation authorities. Exact approved authority/value/provider; no production default inferred. | NO
TASK-057 | Build Issue & Challenge Management (WF-07 Backend) | P9 | W3 | BPK-019-I1 | P0 | PTBC-018 | Issue/Challenge categories/severity/priority master data | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-057 builds WF-07, a source family of PTBC-018 (CSB-14A §19.2) ¦ TASK-057 delivers BPK-019, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-018 | Final categories, dimension labels and presentation. Exact approved authority/value/provider; no production default inferred. | NO
TASK-057 | Build Issue & Challenge Management (WF-07 Backend) | P9 | W3 | BPK-019-I1 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-057 builds WF-07, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-057 | Build Issue & Challenge Management (WF-07 Backend) | P9 | W3 | BPK-019-I1 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-057 builds WF-07, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-058 | Build Issue, Challenge & Escalation UI (WF-07 Frontend) | P9 | W3 | BPK-019-I1 | P1 | PTBC-008 | Issue/Challenge severity-priority/escalation governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-058 builds WF-07, a source family of PTBC-008 (CSB-14A §19.2) ¦ TASK-058 delivers BPK-019, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-008 | Final labels, minimum priority rules and escalation authorities. Exact approved authority/value/provider; no production default inferred. | NO
TASK-058 | Build Issue, Challenge & Escalation UI (WF-07 Frontend) | P9 | W3 | BPK-019-I1 | P1 | PTBC-018 | Issue/Challenge categories/severity/priority master data | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-058 builds WF-07, a source family of PTBC-018 (CSB-14A §19.2) ¦ TASK-058 delivers BPK-019, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-018 | Final categories, dimension labels and presentation. Exact approved authority/value/provider; no production default inferred. | NO
TASK-058 | Build Issue, Challenge & Escalation UI (WF-07 Frontend) | P9 | W3 | BPK-019-I1 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-058 builds WF-07, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-058 | Build Issue, Challenge & Escalation UI (WF-07 Frontend) | P9 | W3 | BPK-019-I1 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-058 builds WF-07, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-058 | Build Issue, Challenge & Escalation UI (WF-07 Frontend) | P9 | W3 | BPK-019-I1 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-058 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-058 | Build Issue, Challenge & Escalation UI (WF-07 Frontend) | P9 | W3 | BPK-019-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-058 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-059 | Contract & Regression Tests for Risk/Issue Domain (WF-06/07) | P9 | W3 | BPK-018; BPK-019 | P1 | PTBC-007 | Risk acceptance/escalation authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-059 builds WF-06, a source family of PTBC-007 (CSB-14A §19.2) ¦ TASK-059 delivers BPK-018, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-007 | Who may accept residual risk/escalation by rating/context. Exact approved authority/value/provider; no production default inferred. | NO
TASK-059 | Contract & Regression Tests for Risk/Issue Domain (WF-06/07) | P9 | W3 | BPK-018; BPK-019 | P1 | PTBC-008 | Issue/Challenge severity-priority/escalation governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-059 builds WF-07, a source family of PTBC-008 (CSB-14A §19.2) ¦ TASK-059 delivers BPK-019, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-008 | Final labels, minimum priority rules and escalation authorities. Exact approved authority/value/provider; no production default inferred. | NO
TASK-059 | Contract & Regression Tests for Risk/Issue Domain (WF-06/07) | P9 | W3 | BPK-018; BPK-019 | P1 | PTBC-017 | Risk scales/dimensions/matrix | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-059 builds WF-06, a source family of PTBC-017 (CSB-14A §19.2) ¦ TASK-059 delivers BPK-018, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-017 | Probability/Impact labels, quantitative descriptions, 5x5 cell→rating mapping. Exact approved authority/value/provider; no production default inferred. | NO
TASK-059 | Contract & Regression Tests for Risk/Issue Domain (WF-06/07) | P9 | W3 | BPK-018; BPK-019 | P1 | PTBC-018 | Issue/Challenge categories/severity/priority master data | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-059 builds WF-07, a source family of PTBC-018 (CSB-14A §19.2) ¦ TASK-059 delivers BPK-019, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-018 | Final categories, dimension labels and presentation. Exact approved authority/value/provider; no production default inferred. | NO
TASK-059 | Contract & Regression Tests for Risk/Issue Domain (WF-06/07) | P9 | W3 | BPK-018; BPK-019 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-059 builds WF-06, WF-07, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-059 | Contract & Regression Tests for Risk/Issue Domain (WF-06/07) | P9 | W3 | BPK-018; BPK-019 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-059 builds WF-06, WF-07, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-060 | Build Change Request & Authorization (WF-08 Backend) | P10 | W4 | BPK-020 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-005: OQ-005 names PTBC-001/009; "TASK for WF-11 backend" = TASK-035, "TASK for WF-08 backend" = TASK-060 ¦ TASK-060 builds WF-08, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-060 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-060 | Build Change Request & Authorization (WF-08 Backend) | P10 | W4 | BPK-020 | P0 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-005: OQ-005 names PTBC-001/009; "TASK for WF-11 backend" = TASK-035, "TASK for WF-08 backend" = TASK-060 ¦ TASK-060 builds WF-08, a source family of PTBC-009 (CSB-14A §19.2) ¦ TASK-060 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-009 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-060 | Build Change Request & Authorization (WF-08 Backend) | P10 | W4 | BPK-020 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-060 builds WF-08, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-060 | Build Change Request & Authorization (WF-08 Backend) | P10 | W4 | BPK-020 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-060 builds WF-08, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-060 | Build Change Request & Authorization (WF-08 Backend) | P10 | W4 | BPK-020 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-060 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | BPK-020 | P1 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-061 builds WF-08, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-061 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | BPK-020 | P1 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-061 builds WF-08, a source family of PTBC-009 (CSB-14A §19.2) ¦ TASK-061 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-009 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | BPK-020 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-061 builds WF-08, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | BPK-020 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-061 builds WF-08, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | BPK-020 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-061 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | BPK-020 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-061 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | BPK-020 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-061 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-062 | Build Suspension & Resumption (WF-09 Backend) | P10 | W5 | BPK-024 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-062 builds WF-09, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-062 delivers BPK-024, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-062 | Build Suspension & Resumption (WF-09 Backend) | P10 | W5 | BPK-024 | P0 | PTBC-005 | Suspension/Resumption reasons, readiness and review governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-062 builds WF-09, a source family of PTBC-005 (CSB-14A §19.2) ¦ TASK-062 delivers BPK-024, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-005 | Exact categories, review cadence and authority. Exact approved authority/value/provider; no production default inferred. | NO
TASK-062 | Build Suspension & Resumption (WF-09 Backend) | P10 | W5 | BPK-024 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-062 builds WF-09, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-062 | Build Suspension & Resumption (WF-09 Backend) | P10 | W5 | BPK-024 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-062 builds WF-09, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-063 | Build Completion & Closure (WF-10 Backend) | P10 | W6 | BPK-025 | P0 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-063 builds WF-10, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-063 delivers BPK-025, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-063 | Build Completion & Closure (WF-10 Backend) | P10 | W6 | BPK-025 | P0 | PTBC-004 | Completion/Closure readiness criteria and disposition policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-063 builds WF-10, a source family of PTBC-004 (CSB-14A §19.2) ¦ TASK-063 delivers BPK-025, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-004 | Exact criteria by Project classification and acceptable open obligations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-063 | Build Completion & Closure (WF-10 Backend) | P10 | W6 | BPK-025 | P0 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-063 builds WF-10, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-063 delivers BPK-025, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-063 | Build Completion & Closure (WF-10 Backend) | P10 | W6 | BPK-025 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-063 builds WF-10, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-064 | Build Suspension & Closure UI (WF-09/WF-10 Frontend) | P10 | W6 | BPK-024; BPK-025 | P1 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-064 builds WF-09, WF-10, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-064 delivers BPK-024, BPK-025, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-064 | Build Suspension & Closure UI (WF-09/WF-10 Frontend) | P10 | W6 | BPK-024; BPK-025 | P1 | PTBC-004 | Completion/Closure readiness criteria and disposition policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-064 builds WF-10, a source family of PTBC-004 (CSB-14A §19.2) ¦ TASK-064 delivers BPK-025, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-004 | Exact criteria by Project classification and acceptable open obligations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-064 | Build Suspension & Closure UI (WF-09/WF-10 Frontend) | P10 | W6 | BPK-024; BPK-025 | P1 | PTBC-005 | Suspension/Resumption reasons, readiness and review governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-064 builds WF-09, a source family of PTBC-005 (CSB-14A §19.2) ¦ TASK-064 delivers BPK-024, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-005 | Exact categories, review cadence and authority. Exact approved authority/value/provider; no production default inferred. | NO
TASK-064 | Build Suspension & Closure UI (WF-09/WF-10 Frontend) | P10 | W6 | BPK-024; BPK-025 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-064 builds WF-09, WF-10, a source family of PTBC-019 (CSB-14A §19.2) ¦ TASK-064 delivers BPK-025, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-019 | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-064 | Build Suspension & Closure UI (WF-09/WF-10 Frontend) | P10 | W6 | BPK-024; BPK-025 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-064 builds WF-09, WF-10, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-064 | Build Suspension & Closure UI (WF-09/WF-10 Frontend) | P10 | W6 | BPK-024; BPK-025 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-064 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-064 | Build Suspension & Closure UI (WF-09/WF-10 Frontend) | P10 | W6 | BPK-024; BPK-025 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-064 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-065 | Contract & Regression Tests for Governance Domain (WF-08/09/10) | P10 | W6 | BPK-020/024/025 | P1 | PTBC-001 | Approval authority matrices and decision limits | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-065 builds WF-08, WF-09, WF-10, a source family of PTBC-001 (CSB-14A §19.2) ¦ TASK-065 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-001 | Exact approver authorities/limits by action/materiality/classification; runtime mechanism is complete. Exact approved authority/value/provider; no production default inferred. | NO
TASK-065 | Contract & Regression Tests for Governance Domain (WF-08/09/10) | P10 | W6 | BPK-020/024/025 | P1 | PTBC-004 | Completion/Closure readiness criteria and disposition policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-065 builds WF-10, a source family of PTBC-004 (CSB-14A §19.2) | Exact criteria by Project classification and acceptable open obligations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-065 | Contract & Regression Tests for Governance Domain (WF-08/09/10) | P10 | W6 | BPK-020/024/025 | P1 | PTBC-005 | Suspension/Resumption reasons, readiness and review governance | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-065 builds WF-09, a source family of PTBC-005 (CSB-14A §19.2) | Exact categories, review cadence and authority. Exact approved authority/value/provider; no production default inferred. | NO
TASK-065 | Contract & Regression Tests for Governance Domain (WF-08/09/10) | P10 | W6 | BPK-020/024/025 | P1 | PTBC-009 | Change materiality/threshold governance | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-065 builds WF-08, a source family of PTBC-009 (CSB-14A §19.2) ¦ TASK-065 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-009 | Exact rule mappings/thresholds for formal/elevated/prohibited outcomes. Exact approved authority/value/provider; no production default inferred. | NO
TASK-065 | Contract & Regression Tests for Governance Domain (WF-08/09/10) | P10 | W6 | BPK-020/024/025 | P1 | PTBC-019 | Evidence/document categories and mandatory evidence policies | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-065 builds WF-08, WF-09, WF-10, a source family of PTBC-019 (CSB-14A §19.2) | Final categories and requirement rules by workflow/classification. Exact approved authority/value/provider; no production default inferred. | NO
TASK-065 | Contract & Regression Tests for Governance Domain (WF-08/09/10) | P10 | W6 | BPK-020/024/025 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-065 builds WF-08, WF-09, WF-10, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-065 | Contract & Regression Tests for Governance Domain (WF-08/09/10) | P10 | W6 | BPK-020/024/025 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-065 delivers BPK-020, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-066 | Build External Entity Update & Review (WF-13 Backend) | P11 | W5 | BPK-023 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-007: OQ-007 names PTBC-031/003; Nafath = TASK-068, WF-13 backend/frontend = TASK-066/067 ¦ TASK-066 builds WF-13, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-066 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-066 | Build External Entity Update & Review (WF-13 Backend) | P11 | W5 | BPK-023 | P0 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-066 builds WF-13, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-066 | Build External Entity Update & Review (WF-13 Backend) | P11 | W5 | BPK-023 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-066 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-066 | Build External Entity Update & Review (WF-13 Backend) | P11 | W5 | BPK-023 | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-007: OQ-007 names PTBC-031/003; Nafath = TASK-068, WF-13 backend/frontend = TASK-066/067 ¦ TASK-066 builds WF-13, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-066 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-067 | Build External Participation UI (WF-13 Frontend) | P11 | W5 | BPK-023 | P1 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-007: OQ-007 names PTBC-031/003; Nafath = TASK-068, WF-13 backend/frontend = TASK-066/067 ¦ TASK-067 builds WF-13, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-067 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-067 | Build External Participation UI (WF-13 Frontend) | P11 | W5 | BPK-023 | P1 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-067 builds WF-13, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-067 | Build External Participation UI (WF-13 Frontend) | P11 | W5 | BPK-023 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-067 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-067 | Build External Participation UI (WF-13 Frontend) | P11 | W5 | BPK-023 | P1 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-007: OQ-007 names PTBC-031/003; Nafath = TASK-068, WF-13 backend/frontend = TASK-066/067 ¦ TASK-067 builds WF-13, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-067 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-067 | Build External Participation UI (WF-13 Frontend) | P11 | W5 | BPK-023 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-067 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-067 | Build External Participation UI (WF-13 Frontend) | P11 | W5 | BPK-023 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-067 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-068 | Integrate Nafath Identity Verification (If Confirmed In Scope) | P11 | W5 | BPK-023 (real-provider integration; PTBC-031) | P2 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | DIRECT | EXPLICIT; OPEN QUESTION; SOURCE FAMILY; PACKAGE | TASK-068 text cites PTBC-003 ¦ OQ-007: OQ-007 names PTBC-031/003; Nafath = TASK-068, WF-13 backend/frontend = TASK-066/067 ¦ TASK-068 builds WF-13, a source family of PTBC-003 (CSB-14A §19.2) ¦ TASK-068 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | YES
TASK-068 | Integrate Nafath Identity Verification (If Confirmed In Scope) | P11 | W5 | BPK-023 (real-provider integration; PTBC-031) | P2 | PTBC-020 | Notification reminder offsets/escalation timing | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-068 builds WF-13, a source family of PTBC-020 (CSB-14A §19.2) | Exact offsets/recurrence/recipient escalation levels. Exact approved authority/value/provider; no production default inferred. | NO
TASK-068 | Integrate Nafath Identity Verification (If Confirmed In Scope) | P11 | W5 | BPK-023 (real-provider integration; PTBC-031) | P2 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-068 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-068 | Integrate Nafath Identity Verification (If Confirmed In Scope) | P11 | W5 | BPK-023 (real-provider integration; PTBC-031) | P2 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | DIRECT | EXPLICIT; OPEN QUESTION; SOURCE FAMILY; PACKAGE | TASK-068 text cites PTBC-031 ¦ OQ-007: OQ-007 names PTBC-031/003; Nafath = TASK-068, WF-13 backend/frontend = TASK-066/067 ¦ TASK-068 builds WF-13, a source family of PTBC-031 (CSB-14A §19.2) ¦ TASK-068 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | YES
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-069 builds FG-01, a source family of PTBC-010 (CSB-14A §19.2) ¦ TASK-069 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-021 | Dashboard catalogue/defaults/personalization scope | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 ¦ TASK-069 builds FG-01, a source family of PTBC-021 (CSB-14A §19.2) ¦ TASK-069 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-021 | Final dashboard composition by audience and allowed personalization. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-022 | Report catalogue/default access/saved-view sharing | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 | Final standard report list and sharing policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-069 builds FG-01, a source family of PTBC-023 (CSB-14A §19.2) | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-037 | Integration health/freshness/reconciliation thresholds | BEFORE UAT | PACKAGE | PACKAGE | TASK-069 delivers BPK-013, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-037 | Exact latency/failure/backlog/stale/tolerance thresholds. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-069 builds FG-01, a source family of PTBC-039 (CSB-14A §19.2) ¦ TASK-069 delivers BPK-013, BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-069 builds FG-01, a source family of PTBC-040 (CSB-14A §19.2) ¦ TASK-069 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-069 builds FG-01, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-069 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-042 | Geospatial/map and advanced visualization requirement | MAY REMAIN CONFIGURABLE | SPEC | SOURCE FAMILY; PACKAGE | TASK-069 builds FG-01, a source family of PTBC-042 (CSB-14A §19.2) ¦ TASK-069 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-042 | Only implement if AHDA confirms business value/data quality. Exact approved authority/value/provider; no production default inferred. | NO
TASK-069 | Build Dashboard Projection & Definition Service (FG-01 Backend) | P12 | W5 | BPK-026 (BPK-013-I1 contract not in workbook) | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-069 builds FG-01, a source family of PTBC-043 (CSB-14A §19.2) ¦ TASK-069 delivers BPK-013, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-070 builds FG-01, a source family of PTBC-010 (CSB-14A §19.2) ¦ TASK-070 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-021 | Dashboard catalogue/defaults/personalization scope | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 ¦ TASK-070 builds FG-01, a source family of PTBC-021 (CSB-14A §19.2) ¦ TASK-070 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-021 | Final dashboard composition by audience and allowed personalization. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-022 | Report catalogue/default access/saved-view sharing | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 | Final standard report list and sharing policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-070 builds FG-01, a source family of PTBC-023 (CSB-14A §19.2) | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-070 builds FG-01, a source family of PTBC-039 (CSB-14A §19.2) ¦ TASK-070 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-070 builds FG-01, a source family of PTBC-040 (CSB-14A §19.2) ¦ TASK-070 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-070 builds FG-01, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-070 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-042 | Geospatial/map and advanced visualization requirement | MAY REMAIN CONFIGURABLE | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-004: Closed by 14B v1.1 §5.3; the one deferred component (SCR-035 map view) sits at PTBC-042 and is built, if confirmed, by TASK-070 (FG-01 frontend) ¦ TASK-070 builds FG-01, a source family of PTBC-042 (CSB-14A §19.2) ¦ TASK-070 delivers BPK-026, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-042 | Only implement if AHDA confirms business value/data quality. Exact approved authority/value/provider; no production default inferred. | NO
TASK-070 | Build Dashboards UI (FG-01 Frontend) | P12 | W5 | BPK-026 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-070 builds FG-01, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-071 builds FG-02, a source family of PTBC-010 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-012 | Sensitive read/export audit policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-071 builds FG-02, a source family of PTBC-012 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-012 | Which views/downloads require enhanced audit. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-021 | Dashboard catalogue/defaults/personalization scope | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 | Final dashboard composition by audience and allowed personalization. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-022 | Report catalogue/default access/saved-view sharing | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 ¦ TASK-071 builds FG-02, a source family of PTBC-022 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-022 | Final standard report list and sharing policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-071 builds FG-02, a source family of PTBC-023 (CSB-14A §19.2) | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-071 builds FG-02, a source family of PTBC-030 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-030 | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-071 builds FG-02, a source family of PTBC-039 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-071 builds FG-02, a source family of PTBC-040 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-071 builds FG-02, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-071 builds FG-02, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-071 | Build Reports, Filters & Export Service (FG-02 Backend) | P12 | W5 | BPK-027 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-071 builds FG-02, a source family of PTBC-047 (CSB-14A §19.2) ¦ TASK-071 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-010 | Dashboard/Report publication authority and SoD | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-072 builds FG-02, a source family of PTBC-010 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-010 | Who validates/publishes official dashboards/reports and whether dual control required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-012 | Sensitive read/export audit policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-072 builds FG-02, a source family of PTBC-012 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-012 | Which views/downloads require enhanced audit. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-021 | Dashboard catalogue/defaults/personalization scope | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 | Final dashboard composition by audience and allowed personalization. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-022 | Report catalogue/default access/saved-view sharing | BEFORE UAT | DIRECT | OPEN QUESTION; SOURCE FAMILY; PACKAGE | OQ-002: Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072 ¦ TASK-072 builds FG-02, a source family of PTBC-022 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-022 | Final standard report list and sharing policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-023 | Overall Project Health rule/presentation policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-072 builds FG-02, a source family of PTBC-023 (CSB-14A §19.2) | WF-02 owns calculation/published health; exact rule/labels/override governance TBC. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-072 builds FG-02, a source family of PTBC-030 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-030 | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-072 builds FG-02, a source family of PTBC-039 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-039 | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-072 builds FG-02, a source family of PTBC-040 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-072 builds FG-02, a source family of PTBC-041 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-072 builds FG-02, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-072 | Build Reports Center UI (FG-02 Frontend) | P12 | W5 | BPK-027 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-072 builds FG-02, a source family of PTBC-047 (CSB-14A §19.2) ¦ TASK-072 delivers BPK-027, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-011 | Audit Reviewer, retention-hold and disposal authorities | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-073 builds FG-06, a source family of PTBC-011 (CSB-14A §19.2) ¦ TASK-073 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-011 | Named permission/assignment authorities and SoD. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-012 | Sensitive read/export audit policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-073 builds FG-06, a source family of PTBC-012 (CSB-14A §19.2) | Which views/downloads require enhanced audit. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-073 builds FG-06, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-073 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-073 builds FG-06, a source family of PTBC-028 (CSB-14A §19.2) | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-073 builds FG-06, a source family of PTBC-029 (CSB-14A §19.2) ¦ TASK-073 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-073 builds FG-06, a source family of PTBC-030 (CSB-14A §19.2) | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-073 builds FG-06, a source family of PTBC-039 (CSB-14A §19.2) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-073 builds FG-06, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-073 builds FG-06, a source family of PTBC-044 (CSB-14A §19.2) | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-073 builds FG-06, a source family of PTBC-045 (CSB-14A §19.2) ¦ TASK-073 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-073 builds FG-06, a source family of PTBC-047 (CSB-14A §19.2) ¦ TASK-073 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | BPK-008-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-073 builds FG-06, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-011 | Audit Reviewer, retention-hold and disposal authorities | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-074 builds FG-06, a source family of PTBC-011 (CSB-14A §19.2) ¦ TASK-074 delivers BPK-028, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-011 | Named permission/assignment authorities and SoD. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-012 | Sensitive read/export audit policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-074 builds FG-06, a source family of PTBC-012 (CSB-14A §19.2) ¦ TASK-074 delivers BPK-028, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-012 | Which views/downloads require enhanced audit. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-074 builds FG-06, a source family of PTBC-026 (CSB-14A §19.2) | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-074 builds FG-06, a source family of PTBC-028 (CSB-14A §19.2) ¦ TASK-074 delivers BPK-028, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-074 builds FG-06, a source family of PTBC-029 (CSB-14A §19.2) | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-030 | Export watermark/classification/attachment policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-074 builds FG-06, a source family of PTBC-030 (CSB-14A §19.2) | Output marking and whether sensitive attachments may ever be emailed. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-074 builds FG-06, a source family of PTBC-039 (CSB-14A §19.2) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-074 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-074 builds FG-06, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-074 builds FG-06, a source family of PTBC-044 (CSB-14A §19.2) | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-074 builds FG-06, a source family of PTBC-045 (CSB-14A §19.2) ¦ TASK-074 delivers BPK-028, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-074 builds FG-06, a source family of PTBC-047 (CSB-14A §19.2) ¦ TASK-074 delivers BPK-028, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-074 | Build Audit & Activity UI (FG-06 Frontend) | P13 | W5 | BPK-028 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-074 builds FG-06, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-028 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-029 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-075 builds FG-05, a source family of PTBC-031 (CSB-14A §19.2) | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-032 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-033 | Financial/KPI authoritative source systems and field authority | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-033 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-033 | Source-of-truth fields, cadence, reconciliation and fallback policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-034 | Email/SMS provider topology and callbacks | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-034 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-034 | Provider/gateway capabilities, callback semantics and throttling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-035 | Document storage/malware-scan provider and quarantine operations | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-035 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-035 | Technology, retry/quarantine operating procedure. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-037 | Integration health/freshness/reconciliation thresholds | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-037 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-037 | Exact latency/failure/backlog/stale/tolerance thresholds. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-038 | Retry/backoff/dead-letter policies | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-038 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-038 | Counts/backoff/final-failure rules; architecture already requires idempotency. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-043 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-044 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-046 | Operational alert recipients, maintenance governance and production retry authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-075 builds FG-05, a source family of PTBC-046 (CSB-14A §19.2) ¦ TASK-075 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-046 | Who can acknowledge/retry/reprocess in PROD and maintenance handling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-075 builds FG-05, a source family of PTBC-047 (CSB-14A §19.2) | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W1 | BPK-009-I1 (typed runtime); BPK-009-I2 (monitoring/reconciliation, W5) | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-075 builds FG-05, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-028 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-029 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-076 builds FG-05, a source family of PTBC-031 (CSB-14A §19.2) | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-032 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-033 | Financial/KPI authoritative source systems and field authority | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-033 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-033 | Source-of-truth fields, cadence, reconciliation and fallback policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-034 | Email/SMS provider topology and callbacks | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-034 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-034 | Provider/gateway capabilities, callback semantics and throttling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-035 | Document storage/malware-scan provider and quarantine operations | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-035 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-035 | Technology, retry/quarantine operating procedure. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-037 | Integration health/freshness/reconciliation thresholds | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-037 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-037 | Exact latency/failure/backlog/stale/tolerance thresholds. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-038 | Retry/backoff/dead-letter policies | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-038 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-038 | Counts/backoff/final-failure rules; architecture already requires idempotency. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-076 is a frontend task; PTBC-039 source family is "All" (CSB-14A §19.2; CSB-16 09_Accessibility_Localization) | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-076 is a frontend task; PTBC-040 source family includes "common UI" (CSB-14A §19.2) | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-043 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-044 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-046 | Operational alert recipients, maintenance governance and production retry authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-076 builds FG-05, a source family of PTBC-046 (CSB-14A §19.2) ¦ TASK-076 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-046 | Who can acknowledge/retry/reprocess in PROD and maintenance handling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-076 builds FG-05, a source family of PTBC-047 (CSB-14A §19.2) | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-076 | Build Integration Administration UI (FG-05 Frontend) | P13 | W5 | BPK-009-I2 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-076 builds FG-05, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-077 | Implement Platform-Wide Input Validation & Output Encoding | P14 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-077 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-077 | Implement Platform-Wide Input Validation & Output Encoding | P14 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-077 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-077 | Implement Platform-Wide Input Validation & Output Encoding | P14 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-077 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-077 | Implement Platform-Wide Input Validation & Output Encoding | P14 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-077 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-077 | Implement Platform-Wide Input Validation & Output Encoding | P14 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-077 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-078 | Implement Rate Limiting, CORS & Secure HTTP Headers | P14 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-078 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-078 | Implement Rate Limiting, CORS & Secure HTTP Headers | P14 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-078 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-078 | Implement Rate Limiting, CORS & Secure HTTP Headers | P14 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-078 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-078 | Implement Rate Limiting, CORS & Secure HTTP Headers | P14 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-078 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-078 | Implement Rate Limiting, CORS & Secure HTTP Headers | P14 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-078 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-079 | Implement CSRF Protection for Session-Based Flows | P14 | W1 | BPK-006-I1 | P1 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-079 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-079 | Implement CSRF Protection for Session-Based Flows | P14 | W1 | BPK-006-I1 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-079 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-079 | Implement CSRF Protection for Session-Based Flows | P14 | W1 | BPK-006-I1 | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-079 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-079 | Implement CSRF Protection for Session-Based Flows | P14 | W1 | BPK-006-I1 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-079 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-079 | Implement CSRF Protection for Session-Based Flows | P14 | W1 | BPK-006-I1 | P1 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | PACKAGE | PACKAGE | TASK-079 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-079 | Implement CSRF Protection for Session-Based Flows | P14 | W1 | BPK-006-I1 | P1 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-079 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-079 | Implement CSRF Protection for Session-Based Flows | P14 | W1 | BPK-006-I1 | P1 | PTBC-041 | Executive dashboard/report content and R07 scope | BEFORE UAT | PACKAGE | PACKAGE | TASK-079 delivers BPK-006, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-041 | Final metrics/composition and authorized enterprise/portfolio scope. Exact approved authority/value/provider; no production default inferred. | NO
TASK-080 | Add Secret Scanning & Dependency Vulnerability Gate to CI | P14 | W1 | BPK-005-I1 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-080 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-080 | Add Secret Scanning & Dependency Vulnerability Gate to CI | P14 | W1 | BPK-005-I1 | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-080 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-080 | Add Secret Scanning & Dependency Vulnerability Gate to CI | P14 | W1 | BPK-005-I1 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-080 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-080 | Add Secret Scanning & Dependency Vulnerability Gate to CI | P14 | W1 | BPK-005-I1 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-080 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-080 | Add Secret Scanning & Dependency Vulnerability Gate to CI | P14 | W1 | BPK-005-I1 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-080 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-003 | External Entity participation eligibility and onboarding authority | BEFORE UAT | PACKAGE | PACKAGE | TASK-081 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-003 | Which Projects/Entity types/users may participate and who may grant access. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | PACKAGE | PACKAGE | TASK-081 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | PACKAGE | PACKAGE | TASK-081 delivers BPK-023, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-031 | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-081 | Conduct Threat Modeling & Security Review for Sensitive Features | P14 | W5 | BPK-023 inputs; evidence BPK-030 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-081 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-082 | Commission External Penetration Test Before Production | P14 | W6 | BPK-030 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-082 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-011 | Audit Reviewer, retention-hold and disposal authorities | BEFORE UAT | PACKAGE | PACKAGE | TASK-083 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-011 | Named permission/assignment authorities and SoD. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-083 builds CSB-CYBER-GUIDE, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-083 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-083 builds CSB-CYBER-GUIDE, a source family of PTBC-027 (CSB-14A §19.2) | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-083 builds CSB-CYBER-GUIDE, a source family of PTBC-029 (CSB-14A §19.2) ¦ TASK-083 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-083 builds CSB-CYBER-GUIDE, a source family of PTBC-032 (CSB-14A §19.2) | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-083 builds CSB-CYBER-GUIDE, a source family of PTBC-043 (CSB-14A §19.2) | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-083 builds CSB-CYBER-GUIDE, a source family of PTBC-044 (CSB-14A §19.2) | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-083 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-083 delivers BPK-008, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | BPK-008-I1 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-083 builds CSB-CYBER-GUIDE, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-084 | Author Platform Test Strategy & Coverage Policy | P15 | W1 | BPK-005-I1 (test harness) | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-084 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-084 | Author Platform Test Strategy & Coverage Policy | P15 | W1 | BPK-005-I1 (test harness) | P0 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-084 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-084 | Author Platform Test Strategy & Coverage Policy | P15 | W1 | BPK-005-I1 (test harness) | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-084 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-084 | Author Platform Test Strategy & Coverage Policy | P15 | W1 | BPK-005-I1 (test harness) | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-084 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-084 | Author Platform Test Strategy & Coverage Policy | P15 | W1 | BPK-005-I1 (test harness) | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-084 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-085 | Implement Cross-Domain End-to-End Test Suite | P15 | W6 | BPK-030 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-085 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | DIRECT | OPEN QUESTION | OQ-010: OQ-010 names PTBC-040/043; accessibility audit = TASK-087, performance/load = TASK-086 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | DIRECT | EXPLICIT; OPEN QUESTION; PACKAGE | TASK-086 text cites PTBC-043 ¦ OQ-010: OQ-010 names PTBC-040/043; accessibility audit = TASK-087, performance/load = TASK-086 ¦ TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | YES
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | BPK-030 (PTBC-043) | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-086 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | DIRECT | EXPLICIT; OPEN QUESTION | TASK-087 text cites PTBC-040 ¦ OQ-010: OQ-010 names PTBC-040/043; accessibility audit = TASK-087, performance/load = TASK-086 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | YES
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | DIRECT | OPEN QUESTION; PACKAGE | OQ-010: OQ-010 names PTBC-040/043; accessibility audit = TASK-087, performance/load = TASK-086 ¦ TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | BPK-030 (PTBC-040) | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-087 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-088 | Prepare & Execute UAT Catalogue Scenarios | P15 | W6 | BPK-030 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-088 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-090 builds CSB-CYBER-GUIDE, a source family of PTBC-026 (CSB-14A §19.2) ¦ TASK-090 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-090 builds CSB-CYBER-GUIDE, a source family of PTBC-027 (CSB-14A §19.2) | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-090 builds CSB-CYBER-GUIDE, a source family of PTBC-029 (CSB-14A §19.2) | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY | TASK-090 builds CSB-CYBER-GUIDE, a source family of PTBC-032 (CSB-14A §19.2) | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-090 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-090 builds CSB-CYBER-GUIDE, a source family of PTBC-043 (CSB-14A §19.2) ¦ TASK-090 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-090 builds CSB-CYBER-GUIDE, a source family of PTBC-044 (CSB-14A §19.2) ¦ TASK-090 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-090 | Integrate Application Performance Monitoring & Error Tracking | P16 | W1 | BPK-005-I1 (diagnostic logging) | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-090 builds CSB-CYBER-GUIDE, a source family of PTBC-048 (CSB-14A §19.2) ¦ TASK-090 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-091 | Implement Health Checks & Uptime Monitoring | P16 | W1 | BPK-005-I1 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-091 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-091 | Implement Health Checks & Uptime Monitoring | P16 | W1 | BPK-005-I1 | P1 | PTBC-040 | Accessibility conformance target | BEFORE UAT | PACKAGE | PACKAGE | TASK-091 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-040 | Exact standard/target remains governance TBC; functional accessibility already required. Exact approved authority/value/provider; no production default inferred. | NO
TASK-091 | Implement Health Checks & Uptime Monitoring | P16 | W1 | BPK-005-I1 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-091 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-091 | Implement Health Checks & Uptime Monitoring | P16 | W1 | BPK-005-I1 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-091 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-091 | Implement Health Checks & Uptime Monitoring | P16 | W1 | BPK-005-I1 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-091 delivers BPK-005, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-028 | Sensitive payload/change-set visibility and redaction rules | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-028 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-028 | Which operational/audit fields may be viewed and by whom. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-029 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-031 | External identity proofing / Nafath applicability | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-092 builds FG-05, a source family of PTBC-031 (CSB-14A §19.2) | Provider/use cases and data-minimization policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-032 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-033 | Financial/KPI authoritative source systems and field authority | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-033 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-033 | Source-of-truth fields, cadence, reconciliation and fallback policy. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-034 | Email/SMS provider topology and callbacks | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-034 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-034 | Provider/gateway capabilities, callback semantics and throttling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-035 | Document storage/malware-scan provider and quarantine operations | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-035 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-035 | Technology, retry/quarantine operating procedure. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-036 | SSO/directory topology and group/claim mappings | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-036 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-036 | Authoritative directory, sync model, role-group mappings if any. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-037 | Integration health/freshness/reconciliation thresholds | BEFORE UAT | DIRECT | EXPLICIT; SOURCE FAMILY; PACKAGE | TASK-092 text cites PTBC-037 ¦ TASK-092 builds FG-05, a source family of PTBC-037 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-037 | Exact latency/failure/backlog/stale/tolerance thresholds. Exact approved authority/value/provider; no production default inferred. | YES
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-038 | Retry/backoff/dead-letter policies | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-038 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-038 | Counts/backoff/final-failure rules; architecture already requires idempotency. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-043 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-044 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-046 | Operational alert recipients, maintenance governance and production retry authority | BEFORE UAT | SPEC | SOURCE FAMILY; PACKAGE | TASK-092 builds FG-05, a source family of PTBC-046 (CSB-14A §19.2) ¦ TASK-092 delivers BPK-009, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-046 | Who can acknowledge/retry/reprocess in PROD and maintenance handling. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-092 builds FG-05, a source family of PTBC-047 (CSB-14A §19.2) | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W5 | BPK-009-I2 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | SPEC | SOURCE FAMILY | TASK-092 builds FG-05, a source family of PTBC-048 (CSB-14A §19.2) | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | BPK-029; BPK-030 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-093 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-096 | Author End-User Guide & FAQ (Arabic + English) | P17 | W6 | BPK-029 | P2 | PTBC-039 | Arabic/English completeness and historical label policy | BEFORE UAT | SPEC | SOURCE FAMILY | TASK-096 Arabic/English end-user guide is governed by the PTBC-039 language policy | Combined vs single-language reports, historical labels and translation governance. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-098 | Define Release & Rollback Strategy | P18 | W6 | BPK-030 (authored from W1) | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-098 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-099 | Execute Staging/Pre-Production Soak Test | P18 | W6 | BPK-030 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-099 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-100 | Execute Production Go-Live | P18 | W6 | BPK-030 | P0 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-100 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-026 | Platform criticality and data classification | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-026 | Formal AHDA classification drives privileged access, logging, PT/DR and masking depth. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-027 | MFA/PAM/privileged administration policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-027 | Exact privileged authentication/PAM requirements and admin account model. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-029 | Audit/SIEM forwarding catalogue and integration | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-029 | Event catalogue, endpoint/process and SOC ownership. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-032 | Production Integration catalogue and system owners | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-032 | Exact SSO, email, Nafath, internal, financial/KPI, storage/scan integrations. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-043 | Performance/scale thresholds and cache/materialization TTLs | BEFORE BUILD / SIT | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-043 | Exact NFRs, concurrency and refresh targets. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-044 | Observability/logging/APM technology stack | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-044 | Functional contracts fixed; products/platform selection by architecture/AHDA IT. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-045 | Immutable audit/tamper-evidence/archive implementation | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-045 | Technology choice for protected store/integrity/archive. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-047 | Document/report/audit/log retention and legal-hold policy | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-047 | Exact retention, archive, disposal, hold rules and owners. Exact approved authority/value/provider; no production default inferred. | NO
TASK-101 | Run Post-Launch Hypercare & Stabilization Period | P18 | W6 | BPK-030 | P1 | PTBC-048 | Backup/DR RPO/RTO, backup retention and residency/hosting | BEFORE PRODUCTION | PACKAGE | PACKAGE | TASK-101 delivers BPK-030, which CSB-15 11_TBC_PTBC_Gates lists under PTBC-048 | AHDA-approved KSA/hosting architecture and recovery targets. Exact approved authority/value/provider; no production default inferred. | NO

## 04_Open_Questions
Question ID | Missing information (workbook) | PTBC IDs | Blocking tasks (resolved to IDs) | Blocking tasks (as written in the workbook) | Decision owner | Workbook status | Resolution basis / note
OQ-001 | Hosting target: internal/KSA on-premise vs. the proposed Google Cloud architecture — the RFP requires internal hosting and data localisation; only a cloud architecture has been detailed to date. | PTBC-048 | TASK-005; TASK-014; TASK-015; TASK-016; TASK-017; TASK-018; TASK-019; TASK-020 | TASK-005, TASK-014 through TASK-020 (all Phase P3) | AHDA IT / Cybersecurity | Blocked | OQ-001 names PTBC-048 hosting/residency (14B v1.1 §3); blocking tasks listed by ID in the workbook
OQ-002 | Exact dashboard and report count/catalogue: RFP states "3 dashboards + 10 reports", the BoQ states "24 outputs", and Blueprint Appendix B independently lists 12 DSH- dashboards and 11 SCR-13x report/related screens. | PTBC-021; PTBC-022 | TASK-069; TASK-070; TASK-071; TASK-072 | TASK for FG-01 backend, TASK for FG-01 frontend, TASK for FG-02 backend, TASK for FG-02 frontend | PMO Engagement Lead / AHDA Business Sponsor | Open | Count fixed by 14B v1.1 §6 (38/34); composition and naming stay at PTBC-021/022; "TASK for FG-01/FG-02 backend/frontend" = TASK-069–072
OQ-003 | Backup retention period and DR RPO/RTO targets are not yet specified by AHDA (PTBC-048). | PTBC-048 | TASK-023 | TASK for backup/restore/DR runbook, Release Checklist row "Backup & DR Restore Drill Passed" | AHDA IT / Cybersecurity | Open | OQ-003 names PTBC-048; "TASK for backup/restore/DR runbook" = TASK-023
OQ-004 | 32 Step 14B RTM inventory-only components have no confirmed disposition (build, defer, or drop). | PTBC-042 | TASK-002; TASK-070 | TASK for RTM findings closure; indirectly all WF/FG frontend tasks | PMO Engagement Lead | Open | Closed by 14B v1.1 §5.3; the one deferred component (SCR-035 map view) sits at PTBC-042 and is built, if confirmed, by TASK-070 (FG-01 frontend)
OQ-005 | Approval authority matrices and materiality/monetary thresholds (who can approve what, at what value) are not yet defined by AHDA (PTBC-001, PTBC-009). | PTBC-001; PTBC-009 | TASK-035; TASK-060 | TASK for WF-11 backend, TASK for WF-08 backend | AHDA Business Sponsor / Portfolio Office | Open | OQ-005 names PTBC-001/009; "TASK for WF-11 backend" = TASK-035, "TASK for WF-08 backend" = TASK-060
OQ-006 | Risk probability/impact matrix values, KPI formulas/targets, and financial condition/variance thresholds are not yet defined by AHDA (PTBC-017, PTBC-024, PTBC-025). | PTBC-017; PTBC-024; PTBC-025 | TASK-055; TASK-052 | TASK for WF-06 backend, TASK for WF-14 backend | AHDA Business Sponsor / Risk & Portfolio Office | Open | OQ-006 names PTBC-017/024/025; "TASK for WF-06 backend" = TASK-055, "TASK for WF-14 backend" = TASK-052
OQ-007 | Nafath integration's exact use case(s) and data-minimization scope are not confirmed (PTBC-031), nor is external-entity onboarding/eligibility authority (PTBC-003). | PTBC-031; PTBC-003 | TASK-068; TASK-066; TASK-067 | TASK for Nafath integration, TASK for WF-13 backend/frontend | AHDA IT (Identity) / Business Sponsor | Open | OQ-007 names PTBC-031/003; Nafath = TASK-068, WF-13 backend/frontend = TASK-066/067
OQ-008 | Legacy project-records source system, format, volume and field mapping for data migration/cutover are not yet documented. | (none — see 06_Findings) | TASK-089; TASK-102 | TASK for migration/rollback validation, TASK for data migration cutover | AHDA IT / Data Owner | Blocked | No PTBC theme covers legacy migration (see finding 004-F-003); nearest source TBC is TBC-DOC-018
OQ-009 | Exact SLA table for the ~22-month operations/maintenance/support period (response times, severity definitions, service credits) is not yet contractually confirmed to the delivery team. | (none — see 06_Findings) | TASK-093 | TASK for operational SLA/on-call runbook | AHDA Contracts / PMO Engagement Lead | Open | Contractual SLA table has no PTBC theme (see finding 004-F-004); operational thresholds are PTBC-037/046
OQ-010 | Target accessibility conformance level (PTBC-040) and platform performance/NFR thresholds (PTBC-043) are not yet confirmed by AHDA; this workbook uses WCAG 2.1 AA and the brief's 150-user capacity figure as working baselines. | PTBC-040; PTBC-043 | TASK-087; TASK-086 | TASK for accessibility audit, TASK for performance/load testing | AHDA Business Sponsor / AHDA IT | Open | OQ-010 names PTBC-040/043; accessibility audit = TASK-087, performance/load = TASK-086

## 05_Gate_Summary
Gate class | PTBC themes | PTBC IDs | Source TBCs (earliest gate, as recorded) | Source TBCs if 004-F-001 re-associations are confirmed | PTBC status: OPEN | PTBC status: APPROVED | Rule
BEFORE BUILD / SIT | 7 | PTBC-032; PTBC-033; PTBC-034; PTBC-035; PTBC-036; PTBC-038; PTBC-043 | 71 | 72 | 7 | 0 | Resolve only what is needed to connect to real enterprise systems or to fix mandatory security architecture; generic adapters and configuration mechanisms may be built earlier (CSB-14A §19.3). SIT and performance-test gates are classed here (14B v1.1 §8).
BEFORE UAT | 31 | PTBC-001; PTBC-002; PTBC-003; PTBC-004; PTBC-005; PTBC-006; PTBC-007; PTBC-008; PTBC-009; PTBC-010; PTBC-011; PTBC-013; PTBC-014; PTBC-015; PTBC-016; PTBC-017; PTBC-018; PTBC-019; PTBC-020; PTBC-021; PTBC-022; PTBC-023; PTBC-024; PTBC-025; PTBC-028; PTBC-031; PTBC-037; PTBC-039; PTBC-040; PTBC-041; PTBC-046 | 375 | 383 | 31 | 0 | Populate workflow authorities, master data, matrices, thresholds, evidence rules and the dashboard/report catalogue before the affected UAT scenarios run (CSB-14A §19.3).
BEFORE PRODUCTION | 9 | PTBC-012; PTBC-026; PTBC-027; PTBC-029; PTBC-030; PTBC-044; PTBC-045; PTBC-047; PTBC-048 | 53 | 55 | 9 | 0 | Finalise security classification, privileged access, SIEM/logging, retention, backup/DR, production operators, providers and operational SLAs before go-live (CSB-14A §19.3).
MAY REMAIN CONFIGURABLE | 1 | PTBC-042 | 12 | 1 | 1 | 0 | Business labels, reminder offsets, display preferences and similar values may change after go-live if their configuration lifecycle is governed (CSB-14A §19.3).
TOTAL | 48 |  | 511 | 511 | 48 | 0
By category | PTBC themes | PTBC IDs | Source TBCs (distinct)
Business Governance | 12 | PTBC-001; PTBC-002; PTBC-003; PTBC-004; PTBC-005; PTBC-006; PTBC-007; PTBC-008; PTBC-009; PTBC-010; PTBC-011; PTBC-012 | 140
Configuration | 13 | PTBC-013; PTBC-014; PTBC-015; PTBC-016; PTBC-017; PTBC-018; PTBC-019; PTBC-020; PTBC-021; PTBC-022; PTBC-023; PTBC-024; PTBC-025 | 235
Cybersecurity | 6 | PTBC-026; PTBC-027; PTBC-028; PTBC-029; PTBC-030; PTBC-031 | 46
Integration | 7 | PTBC-032; PTBC-033; PTBC-034; PTBC-035; PTBC-036; PTBC-037; PTBC-038 | 73
UX/Presentation | 4 | PTBC-039; PTBC-040; PTBC-041; PTBC-042 | 36
Technical Architecture | 3 | PTBC-043; PTBC-044; PTBC-045 | 15
Operations | 1 | PTBC-046 | 6
Records/Retention | 2 | PTBC-047; PTBC-048 | 27
By owner spec | Source TBCs | ID range (CSB-14A §19.1) | Before Build / SIT | Before UAT | Before Production | May Remain Configurable
FG-01 | 30 | TBC-DSH-001 … TBC-DSH-030 | 2 | 26 | 1 | 1
FG-02 | 30 | TBC-RPT-01 … TBC-RPT-30 | 4 | 21 | 4 | 1
FG-03 | 25 | TBC-IAM-001 … TBC-IAM-025 | 3 | 1 | 20 | 1
FG-04 | 30 | TBC-CFG-001 … TBC-CFG-030 | 2 | 25 | 3 | 0
FG-05 | 34 | TBC-INT-01 … TBC-INT-34 | 18 | 12 | 4 | 0
FG-06 | 31 | TBC-AUD-01 … TBC-AUD-31 | 1 | 20 | 10 | 0
WF-01 | 17 | TBC-PCR-01 … TBC-PCR-17 | 1 | 14 | 0 | 2
WF-02 | 26 | TBC-PRG-001 … TBC-PRG-026 | 1 | 25 | 0 | 0
WF-03 | 18 | TBC-SCH-001 … TBC-SCH-018 | 2 | 16 | 0 | 0
WF-04 | 18 | TBC-TSK-001 … TBC-TSK-018 | 1 | 17 | 0 | 0
WF-05 | 16 | TBC-MIL-001 … TBC-MIL-016 | 1 | 15 | 0 | 0
WF-06 | 20 | TBC-RSK-001 … TBC-RSK-020 | 1 | 19 | 0 | 0
WF-07 | 16 | TBC-ISS-001 … TBC-ISS-016 | 3 | 12 | 0 | 1
WF-08 | 24 | TBC-CHG-001 … TBC-CHG-024 | 1 | 21 | 1 | 1
WF-09 | 20 | TBC-SUS-001 … TBC-SUS-020 | 2 | 18 | 0 | 0
WF-10 | 25 | TBC-CLO-001 … TBC-CLO-025 | 4 | 20 | 1 | 0
WF-11 | 18 | TBC-APR-001 … TBC-APR-018 | 2 | 15 | 1 | 0
WF-12 | 30 | TBC-DOC-001 … TBC-DOC-030 | 2 | 23 | 4 | 1
WF-13 | 28 | TBC-EXT-001 … TBC-EXT-028 | 3 | 21 | 2 | 2
WF-14 | 30 | PERF-TBC-001 … PERF-TBC-030 | 6 | 23 | 0 | 1
WF-15 | 25 | TBC-NTF-001 … TBC-NTF-025 | 11 | 11 | 2 | 1

## 06_Findings
Finding | Severity | Class | Observation | Risk | Disposition in this tracker | Owner | Due gate | Status | Linked IDs
004-F-001 | IMPORTANT | Crosswalk association | PTBC-042 (Geospatial/map and advanced visualization) carries 17 source TBCs in the 14B crosswalk; 16 of them are not geospatial — the association follows the word "mapping" (e.g. TBC-PCR-17 GCP architecture/region, TBC-CHG-001 materiality thresholds, TBC-DOC-018 legacy document migration, TBC-NTF-024 event deduplication). 12 of these TBCs have PTBC-042 as their only theme and therefore inherit "May Remain Configurable" as their gate class; only TBC-DSH-008 is genuinely a map requirement. TBC-ISS-004 → PTBC-043 is the same pattern on the word "scale". | A task could treat a hosting, materiality or migration question as post-go-live configurable because its only recorded gate is PTBC-042. | Proposed re-association and gate class recorded per TBC in 02_Source_TBC_Register (columns N–P); recorded 14B association stays controlling until confirmed. If confirmed: BEFORE BUILD / SIT 71 → 72; BEFORE UAT 375 → 383; BEFORE PRODUCTION 53 → 55; MAY REMAIN CONFIGURABLE 12 → 1 (05_Gate_Summary). | Requirements governance lead (14B-F-008 owner) | Before the 14B v1.1 §9 F-008 signature | OPEN | TBC-RPT-02; TBC-IAM-003; TBC-IAM-019; TBC-CFG-005; TBC-PCR-16; TBC-PCR-17; TBC-RSK-004; TBC-ISS-003; TBC-ISS-016; TBC-CHG-001; TBC-CHG-009; TBC-DOC-018; TBC-EXT-011; TBC-EXT-026; PERF-TBC-029; TBC-NTF-024; TBC-ISS-004
004-F-002 | IMPORTANT | Crosswalk coverage | PTBC-008 (Issue/Challenge severity-priority/escalation governance, WF-07) has zero source TBCs in the 14B crosswalk, although TBC-ISS-003 (severity labels), TBC-ISS-004 (priority scale / severity→priority rules) and TBC-ISS-016 (verification waiver by category) are its subject; they were associated with PTBC-018/042/043 instead. | PTBC-008 could be "resolved" with no source TBC closed, or the WF-07 values approved under PTBC-018 without the escalation-authority part of PTBC-008. | Propose TBC-ISS-003, TBC-ISS-004 and TBC-ISS-016 as PTBC-008 source TBCs (keeping PTBC-018 where recorded); see 02_Source_TBC_Register. | Requirements governance lead | Before the F-008 signature | OPEN | TBC-ISS-003; TBC-ISS-004; TBC-ISS-016
004-F-003 | IMPORTANT | Gate coverage gap | OQ-008 (legacy project-records source, format, volume, field mapping for migration/cutover) has no PTBC theme. The only related source TBC, TBC-DOC-018 (WF-12 legacy document migration scope), is associated with PTBC-042 and so classed May Remain Configurable. | TASK-089 and TASK-102 are gated by an Open Question only; nothing in the PTBC register forces the migration scope to be approved before production cutover. | Track the migration scope under OQ-008 with gate class BEFORE PRODUCTION in this tracker (04_Open_Questions); raise a CSB-14A §19.2 change request for a records-migration theme if the requirements governance lead agrees. No new PTBC ID is created here. | Requirements governance lead / AHDA IT (Data Owner) | Before migration rehearsal (Release Checklist "Data Migration Cutover Rehearsed") | OPEN | TBC-DOC-018; OQ-008; TASK-089; TASK-102
004-F-004 | MINOR | Gate coverage gap | OQ-009 (contractual SLA table for the ~22-month operations period) has no PTBC theme. CSB-14A §19.3 lists "operational SLAs" under Before Production but no §19.2 row carries them; PTBC-037/046 cover operational thresholds and alert authority, not contractual response times. | TASK-093 SLA figures are gated by OQ-009 only. | Track under OQ-009 with gate class BEFORE PRODUCTION (04_Open_Questions); AHDA Contracts confirms the SLA table per 14B v1.1 §5.7. | AHDA Contracts / PMO Engagement Lead | Before Release Checklist "Operational Runbooks & On-Call Ready" | OPEN | OQ-009; TASK-093; RTM-19509; RTM-19514; RTM-19528
004-F-005 | DOCUMENTATION | Workbook | The Open Questions sheet names its blocking tasks by description ("TASK for WF-11 backend") rather than by ID for OQ-002 to OQ-010. | The acceptance criterion "links back … by ID" cannot be checked from the workbook alone. | IDs resolved in 04_Open_Questions column D; adopt them in the workbook at the next revision. | Workbook owner | Next workbook revision | OPEN | OQ-002 … OQ-010
004-F-006 | DOCUMENTATION | Workbook | 66 tasks touch a PTBC-gated value by direct or source-family link but do not cite the PTBC ID in their Detailed Description / Acceptance Criteria (only 17 tasks cite any PTBC). 33 DIRECT links (Open Question or ADR based) are uncited, e.g. TASK-002→PTBC-042, TASK-005→PTBC-048, TASK-006→PTBC-044, TASK-014→PTBC-048, TASK-015→PTBC-048, TASK-016→PTBC-048, TASK-017→PTBC-048, TASK-018→PTBC-048. | A reader of the workbook row cannot see the gate that governs the task. | Insert "Gated values: PTBC-xxx, … (docs/governance/ptbc-tbc-tracker.xlsx)" into each linked task's Detailed Description at the next workbook revision; 03_Task_Links column N marks the rows. | Workbook owner | Next workbook revision | OPEN | TASK-002; TASK-005; TASK-006; TASK-010; TASK-014; TASK-015; TASK-016; TASK-017; TASK-018; TASK-019; TASK-020; TASK-023; TASK-028; TASK-029; TASK-030; TASK-031; TASK-032; TASK-033; TASK-034; TASK-035; TASK-036; TASK-037; TASK-038; TASK-039; TASK-040; TASK-041; TASK-042; TASK-044; TASK-045; TASK-046; TASK-047; TASK-048; TASK-049; TASK-050; TASK-051; TASK-052; TASK-053; TASK-054; TASK-055; TASK-056; TASK-057; TASK-058; TASK-059; TASK-060; TASK-061; TASK-062; TASK-063; TASK-064; TASK-065; TASK-066; TASK-067; TASK-068; TASK-069; TASK-070; TASK-071; TASK-072; TASK-073; TASK-074; TASK-075; TASK-076; TASK-083; TASK-086; TASK-087; TASK-090; TASK-092; TASK-096
004-F-007 | DOCUMENTATION | Register wording | PTBC-026 source-family cell reads "FG-03/12/14/06"; FG-12 and FG-14 do not exist (WF-12, WF-14 intended). Already dispositioned as 14B-F-007 in 14B v1.1 §7; carried here so the expanded column is not read as a new interpretation. | None (expanded column corrects it). | Keep the as-recorded cell; the "Source specs (expanded)" column shows WF-12/WF-14. | Document-control owner | With 14B-F-007 | OPEN | PTBC-026
004-F-008 | DOCUMENTATION | Downstream citation | CSB-15 11_TBC_PTBC_Gates and CSB-17 Governance_Values cite the mapping basis as "14A §15 PTBC"; the register is CSB-14A §19.2 (§15 is a different section). | Auditors following the citation land in the wrong section. | Cite CSB-14A §19.2 at the next Step 15/17 re-issue. | Step 15 / Step 17 authors | Next re-issue | OPEN | CSB-15; CSB-17

## 07_Status_Vocabulary
Status value | Meaning
OPEN | No AHDA-approved value or decision exists. Build the mechanism only; tests use explicit non-production fixtures; nothing is seeded, hard-coded or documented as the AHDA value.
PROPOSED | The delivery team has put a candidate value/decision in front of the accountable AHDA function (reference in "Approved value / decision reference"). Still not a value for build or UAT.
APPROVED | The accountable AHDA function has recorded the value/decision (record ID, signatory and date filled). Configuration may be published through FG-04 / the relevant admin path.
IMPLEMENTED | The approved value is configured and verified in the target environment; evidence referenced.
DEFERRED | AHDA has explicitly deferred the capability (only valid for a theme whose gate is May Remain Configurable, e.g. PTBC-042), with the decision record referenced.
Gate class | Treatment (CSB-14A §19.3)
BEFORE BUILD / SIT | Resolve only what is needed to connect to real enterprise systems or to fix mandatory security architecture; generic adapters and configuration mechanisms may be built earlier (CSB-14A §19.3). SIT and performance-test gates are classed here (14B v1.1 §8).
BEFORE UAT | Populate workflow authorities, master data, matrices, thresholds, evidence rules and the dashboard/report catalogue before the affected UAT scenarios run (CSB-14A §19.3).
BEFORE PRODUCTION | Finalise security classification, privileged access, SIEM/logging, retention, backup/DR, production operators, providers and operational SLAs before go-live (CSB-14A §19.3).
MAY REMAIN CONFIGURABLE | Business labels, reminder offsets, display preferences and similar values may change after go-live if their configuration lifecycle is governed (CSB-14A §19.3).
Link strength | Meaning
DIRECT | The task text cites the PTBC ID, or the task is a blocking task of an Open Question that names the PTBC, or the task produces the ADR that carries the decision.
SPEC | The task builds a WF/FG (or Cyber-Guide-governed control) that CSB-14A §19.2 lists as a source family of the PTBC.
PACKAGE | The task delivers a Step 15 build package whose "PTBC impact" (CSB-15 02_Build_Packages / 11_TBC_PTBC_Gates) lists the PTBC. Inherited; the task must still not invent the value.